## Overview Dashboard
DecisionOS - Master Tracker
One overview for Epic 1 + Epic 2 + Epic 3 + Testing + Go-Live. Numbers roll up from the per-epic xlsx files on regeneration. Founder ask 2026-08-15.
All-epics progress: 1006 of 1129 items resolved (89%)
Epic | Theme | Done | Total | % | Status | File pointer
Epic 1 | Stability + Security + RBAC + Workflow Engine | 100 | 105 | 95% | In Progress | DecisionOS_Epic1_Stability.xlsx
Epic 2 | UX Redesign (CRM + Decision Desk + Finance + Dex + hygiene) | 73 | 73 | 100% | Done | DecisionOS_Epic2_UX_Redesign.xlsx
Epic 3 | AI Foundation & Company Intelligence (reshaped from Dex AI Persona: prompt+model+telemetry foundation, extraction engine, Company Brain RAG+agents, Dex persona, evals) | 38 | 38 | 100% | Done | DecisionOS_Epic3_AI_Foundation.xlsx
Epic 4 | Workflow Engine (turn workflows from data into an engine) | 18 | 18 | 100% | Done | DecisionOS_Epic4_Workflow_Engine.xlsx
Epic 5 | Enterprise RBAC (branches/groups/SSO/API keys/portal) -- DEFERRED to Enterprise Expansion phase; SME-first product does not need it yet | 0 | 5 | Deferred | Deferred (future) | DecisionOS_Epic5_Enterprise_RBAC.xlsx
Epic 6 | UX + UI Optimization (18 per-screen + cross-cutting sprints; Sprint 1 = Operating Score; Sprint 21 = My Work task management; Sprint 22 = Decision Desk decision flow; Sprint 23 = Settings, Team and access) | 301 | 403 | 75% | In progress | DecisionOS_Epic6_UX_UI_Optimization.xlsx
Epic 7 | Backend Optimization & Modularization (10 sprints; finishes the Phase A/B migration; Sprint 1 = modular foundation + backend analysis) | 86 | 86 | 100% | Done | DecisionOS_Epic7_Backend_Optimization.xlsx
Epic 8 | Landing Page (marketing site -- hero, problem, product tour, ICP, pricing, CEO Brief teaser, final CTA) | 55 | 59 | 93% | In Progress | DecisionOS_Epic8_Landing_Page.xlsx
Epic 9 | Admin / Platform Console (super-admin console: tenant 360, impersonation, support desk, billing, observability; Sprint 0 = shipped) | 74 | 74 | 100% | Done | DecisionOS_Epic9_Admin_Console.xlsx
Epic 10 | Testing (comprehensive scenario coverage: unit + functional + role-matrix + onboarding + multi-niche + team-scale + formula-edge + isolation + AI/extraction + concurrency + regression-health + E2E; 13 sprints) | 154 | 154 | 100% | Done | DecisionOS_Epic10_Testing.xlsx
Epic 11 | New Features -- one sprint per client-asked feature (Sprint 1 Requests; Sprint 2 Notification history; Sprint 3 Preferred name; Sprint 4 Bugs; Sprint 5 Finance delete; Sprint 6 Admin console redesign; Sprint 7 Admin console v2; Sprint 8 Phone redesign; Sprint 9 Finance periods) | 107 | 114 | 94% | In progress | DecisionOS_Epic11_New_Features.xlsx
Testing Plan | Automated + Alpha + Beta + GA |  |  |  |  | See Epic 1 Testing Plan sheet
Go-Live
Go-Live Checklist | Final SaaS-scale readiness |  |  |  |  | See Epic 1 Go-Live Checklist sheet

## Regeneration Notes
How this file stays honest
Source of truth | Each per-epic xlsx is authoritative for its own backlog. This Master rollup is DERIVED -- it reads each epic file's Backlog sheet and sums Done vs Total.
How to refresh | Re-run scratchpad/tracker_restructure.py (or its follow-up). Rollup numbers get recomputed from live epic files and re-written into the Overview Dashboard.
Testing + Go-Live | Not counted in the % total -- those are checklists, not backlog items. Rollup rows point to the Epic 1 xlsx where the actual sheets live.
New Master vs old Stability tracker | Old DecisionOS_SaaS_Stability_Tracker.xlsx stays as a read-only archive of what the split originated from. This Master tracker replaces its Dashboard role, and DecisionOS_Epic1_Stability.xlsx replaces its Backlog + Fix Log + Testing + RBAC + Go-Live role.