## Cover
DecisionOS
Epic 7 -- UX + UI Optimization
Kickoff | 2026-08-17 (post Epic 5 close; runs in parallel with Chinmay's mobile-pwa branch)
Origin | Founder ask 2026-08-17: 'lets work on the new epic which UX and UI optimization -- create a tracker first based on that Next we will work on each screen as sprint got it.' Follow-up 2026-08-17: 'operating score has to be a new sprint for sure -- we are going to work on that only first.'
Epic 7 goal | Take DecisionOS from working-but-uneven to intentionally-crafted. Every screen graduates from 'ships' to 'delightful'. Design system consolidated. Accessibility at WCAG 2.1 AA. Mobile parity for the 8 remaining desktop-only surfaces. Copy sweep across the whole app.
Sprint 1 -- founder-priority start | Operating Score is our first sprint. It's the company-health dashboard the owner opens most and gets the least value from today: a static number, no drill-down, no trend, no 'why', no mobile version. Rich 20-item sprint transforms it from a static gauge into a decision-driving surface.
Working principles | 1. Every sprint is a screen (or a tight cluster). 2. Item categories are consistent across sprints: Visual / Interaction / Content / IA / Consistency / A11y / Mobile parity. 3. Adopt Chinmay's indigo rebrand (DS-1..5, c6f3a54) as the single source; don't refight palette. 4. Backend contracts are frozen -- this epic touches frontend + copy + design tokens only. Exception: Sprint 1 (Operating Score) needs a small backend addition for 30-day snapshot history. 5. Trackers side-by-side with code (per founder rule).
Sprint breakdown
>>> Sprint 1 -- Operating Score
Files | OperatingScore.js, /api/operating-score
Why | FOUNDER FOCUS SPRINT. The company-health dashboard: 4 weighted categories (execution 35%, finance 25%, sales 20%, responsiveness 20%), team leaderboard, gated by data threshold. Currently a single-number snapshot with no context, drill-down, trend, or 'why'. This sprint turns it from a static gauge into a decision-driving surface.
Status | In progress
Sprint 2 -- Landing + Auth
Files | Landing.js, Login.js, Signup.js
Why | First impression + credential capture. Set the visual tone the rest of the app inherits.
Status | Backlog
Sprint 3 -- Onboarding flow
Files | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal
Why | 5-step tenant provisioning. Highest drop-off risk zone -- every screen must feel effortless.
Status | Backlog
Sprint 4 -- Decision Desk (/inbox)
Files | Desk.js
Why | The home screen. Every user opens this first. Density, ranking, and the Dex narrative live here.
Status | Backlog
Sprint 5 -- My Work
Files | MyWork.js
Why | Personal task queue. Stage chips (WE-11), AI-priority signals, category filters, workflow context.
Status | Backlog
Sprint 6 -- Workflows
Files | Workflows.js
Why | Pipeline board. Inline task lists (WE-12), manual advance dialogs (WE-13), single-writer engine (WE-06).
Status | Backlog
Sprint 7 -- CRM cluster
Files | CRM.js, Contacts.js, ContactProfile.js
Why | Relationship management. Grid vs list, contact 360, relationship intelligence, bulk import UX.
Status | Backlog
Sprint 8 -- Finance cluster
Files | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js
Why | Money-in / money-out. AI-classified expenses, Ledger drill-downs, WhatsApp capture, ReviewPanel.
Status | Backlog
Sprint 9 -- Dex / AI surfaces
Files | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js
Why | Dex persona home. Capture bar, Ask/Search/Documents tabs. Post E2-40 persona-prefix launch.
Status | Backlog
Sprint 10 -- People + Growth
Files | Team.js, People.js, WorkCoach.js
Why | Team roster, workforce insights, workflow coaching. WorkCoach improvements need action affordances. OperatingScore has been extracted to Sprint 1.
Status | Backlog
Sprint 11 -- Ops surfaces
Files | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js
Why | Meeting notes, leave requests, activity journal, alerts. Lower-frequency but high-trust surfaces.
Status | Backlog
Sprint 12 -- Settings
Files | Settings.js (4-tab from WE-04)
Why | Business / Operations / Money / Account tabs. Editor UX for operating model, roles, categories.
Status | Backlog
Sprint 13 -- Admin portal
Files | admin/AdminPortal.js, admin/AdminSections.js, admin/AdminLogin.js
Why | Superadmin surface. Tenant list, usage tallies, provider-key management, quota views.
Status | Backlog
Sprint 14 -- Design system tokens
Files | tailwind.config.js, shared components
Why | Adopt Chinmay's indigo rebrand as single source. Kill hardcoded colors, unify spacing scale, typography ramp.
Status | Backlog
Sprint 15 -- Empty / loading / error states
Files | cross-cutting
Why | Every list, table, panel. No 'nothing to show' full-stops. Skeletons with real shape. Actionable errors.
Status | Backlog
Sprint 16 -- Accessibility (WCAG 2.1 AA)
Files | cross-cutting
Why | Contrast, keyboard nav, focus rings, touch targets, screen reader labels. Compliance is enterprise-deal-critical.
Status | Backlog
Sprint 17 -- Mobile parity + PWA polish
Files | frontend/src/pages/mobile/*, service-worker.js
Why | MPWA-* landed core mobile pages. Close remaining desktop-only surfaces, tighten PWA install, offline-first UX.
Status | Backlog
Sprint 18 -- Copy pass + Exit gate
Files | cross-cutting
Why | UX copy sweep (buttons, empty states, errors, tooltips). Final E2E golden path across desktop + mobile.
Status | Backlog

## Dashboard
DecisionOS - Epic 7 - UX + UI Optimization
Every screen graduates from 'ships' to 'delightful'. Sprint 1 = Operating Score (founder priority). Adopts Chinmay's indigo rebrand. Design system + a11y + mobile parity + copy pass. Kickoff: 2026-08-17.
Epic 7 progress: 26 of 138 items Done (18.8%)
Sprint | Sprint / Epic name | Done | Total | % | Status | Theme
Sprint 1 | Operating Score | 18 | 40 | 45% | In progress | FOUNDER FOCUS SPRINT. The company-health dashboard: 4 weighted categories (execution 35%, finance 25%, sales 20%, responsiveness 20%), team leaderboard, gated by data threshold. Currently a single-number snapshot with no context, drill-down, trend, or 'why'. This sprint turns it from a static gauge into a decision-driving surface.
Sprint 2 | Landing + Auth | 0 | 6 | 0% | Backlog | First impression + credential capture. Set the visual tone the rest of the app inherits.
Sprint 3 | Onboarding flow | 0 | 7 | 0% | Backlog | 5-step tenant provisioning. Highest drop-off risk zone -- every screen must feel effortless.
Sprint 4 | Decision Desk (/inbox) | 0 | 6 | 0% | Backlog | The home screen. Every user opens this first. Density, ranking, and the Dex narrative live here.
Sprint 5 | My Work | 8 | 8 | 100% | COMPLETE | Personal task queue. Stage chips (WE-11), AI-priority signals, category filters, workflow context.
Sprint 6 | Workflows | 0 | 6 | 0% | Backlog | Pipeline board. Inline task lists (WE-12), manual advance dialogs (WE-13), single-writer engine (WE-06).
Sprint 7 | CRM cluster | 0 | 6 | 0% | Backlog | Relationship management. Grid vs list, contact 360, relationship intelligence, bulk import UX.
Sprint 8 | Finance cluster | 0 | 6 | 0% | Backlog | Money-in / money-out. AI-classified expenses, Ledger drill-downs, WhatsApp capture, ReviewPanel.
Sprint 9 | Dex / AI surfaces | 0 | 6 | 0% | Backlog | Dex persona home. Capture bar, Ask/Search/Documents tabs. Post E2-40 persona-prefix launch.
Sprint 10 | People + Growth | 0 | 5 | 0% | Backlog | Team roster, workforce insights, workflow coaching. WorkCoach improvements need action affordances. OperatingScore has been extracted to Sprint 1.
Sprint 11 | Ops surfaces | 0 | 6 | 0% | Backlog | Meeting notes, leave requests, activity journal, alerts. Lower-frequency but high-trust surfaces.
Sprint 12 | Settings | 0 | 6 | 0% | Backlog | Business / Operations / Money / Account tabs. Editor UX for operating model, roles, categories.
Sprint 13 | Admin portal | 0 | 5 | 0% | Backlog | Superadmin surface. Tenant list, usage tallies, provider-key management, quota views.
Sprint 14 | Design system tokens | 0 | 5 | 0% | Backlog | Adopt Chinmay's indigo rebrand as single source. Kill hardcoded colors, unify spacing scale, typography ramp.
Sprint 15 | Empty / loading / error states | 0 | 4 | 0% | Backlog | Every list, table, panel. No 'nothing to show' full-stops. Skeletons with real shape. Actionable errors.
Sprint 16 | Accessibility (WCAG 2.1 AA) | 0 | 6 | 0% | Backlog | Contrast, keyboard nav, focus rings, touch targets, screen reader labels. Compliance is enterprise-deal-critical.
Sprint 17 | Mobile parity + PWA polish | 0 | 5 | 0% | Backlog | MPWA-* landed core mobile pages. Close remaining desktop-only surfaces, tighten PWA install, offline-first UX.
Sprint 18 | Copy pass + Exit gate | 0 | 5 | 0% | Backlog | UX copy sweep (buttons, empty states, errors, tooltips). Final E2E golden path across desktop + mobile.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
U7-01.1 | OperatingScore.js, /api/operating-score | 1 | Visual | Hero rewrite -- score + delta + one-sentence narrative | Current hero is a static 6xl number in a 144x144 box with '/ 100' below. Replace with: (1) big score, (2) delta chip vs last week ('+4' green / '-2' red), (3) one-sentence AI narrative below ('Kapoor Retail is running at 76/100 -- responsiveness improved after Priya cleared 2 complaints on Wednesday'). Founder should get full picture in one glance without reading 4 category bars. | P0 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.2 | OperatingScore.js, /api/operating-score | 1 | Interaction | Overall score circle -- animated fill on load | Static ring today. Animate the score fill from 0 -> current value on load (300ms cubic-out) so the number feels earned, not stamped. Respect prefers-reduced-motion. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-01.3 | OperatingScore.js, /api/operating-score | 1 | IA | 30-day trend line behind the overall score | No time context today -- a founder sees 76 with no idea if that's up or down. Add a sparkline (small SVG line chart) behind the hero score showing last 30 daily scores. Backend needs to persist daily snapshots (new collection: operating_score_history {tenant_id, date, overall, categories}). Frontend renders the sparkline; hover shows the exact day + score. | P1 | L | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.4 | OperatingScore.js, /api/operating-score | 1 | IA | Category cards -- show WHAT each measures + drill-down affordance | Current 4 category bars show label + score + colored bar. No context on formula or what drives the number. Convert each to a clickable card revealing (1) formula in plain English ('Execution = tasks-done-on-time / tasks-created, past 30 days'), (2) top 3 drivers this period ('2 overdue tasks / 1 approved decision / etc.'), (3) suggested action. Click opens a drill-down modal (or route to /operating-score/execution). | P0 | L | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.5 | OperatingScore.js, /api/operating-score | 1 | Interaction | Category drill-down: Execution -> task list | Clicking Execution should show the actual tasks that drove the number: completed on time (green), completed late (amber), overdue (red), open. Sortable by drift-from-due-date. Direct link to MyWork with filter applied. | P1 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.6 | OperatingScore.js, /api/operating-score | 1 | Interaction | Category drill-down: Finance -> invoice + payment breakdown | Clicking Finance should reveal: outstanding invoices (with counterparty + days-overdue), payment collection rate (paid / billed), top 3 overdue counterparties. Gated by can_finance flag as backend already enforces. | P1 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.7 | OperatingScore.js, /api/operating-score | 1 | Interaction | Category drill-down: Sales -> decision funnel | Clicking Sales should show: total decisions captured, approved, pending, dropped. Time-in-stage histogram. Direct link to Desk with filter. | P1 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.8 | OperatingScore.js, /api/operating-score | 1 | Interaction | Category drill-down: Responsiveness -> open complaints + resolution time | Clicking Responsiveness should show: complaints open (with age), average time-to-resolution, oldest unresolved. Founder sees 'why' immediately. | P1 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.9 | OperatingScore.js, /api/operating-score | 1 | Content | 'Why is my score X?' Dex-generated explainer | One-sentence AI diagnosis on load, refreshed with a button. Input: categories + drivers + last 7 days deltas. Output: 'Your weakest signal this week is Responsiveness -- 2 complaints have been open >7 days. Assign them today to see a 6-point lift by Friday.' Uses existing ai_ask endpoint under DPDP consent gate (RBAC-25). | P1 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.10 | OperatingScore.js, /api/operating-score | 1 | Interaction | Suggested-action chips below the score | Convert the Dex diagnosis into 1-3 actionable chips: 'Resolve 2 complaints' -> /my-work filter=complaints, 'Chase 3 overdue invoices' -> /finance filter=overdue. One tap from score to action. | P1 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.11 | OperatingScore.js, /api/operating-score | 1 | Visual | Employee leaderboard -- add period label + score delta per person | Current heading is 'Team Execution' with no period. Change to 'Team Execution -- last 30 days'. Add a small delta chip per row showing per-person score change vs last period. | P1 | S | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.12 | OperatingScore.js, /api/operating-score | 1 | Interaction | Employee row -- hover previews WorkCoach snapshot | Instead of navigate-to-coach on click, on desktop hover show a mini card: latest strengths + improvements + suggested action. Click still routes to WorkCoach. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-01.13 | OperatingScore.js, /api/operating-score | 1 | Interaction | Employee row -- filter + sort controls (role / score / activity) | Currently locked to API order. Add sort: score desc/asc, activity desc/asc, name; filter by role. Persists per-tenant per-user in localStorage. | P2 | S | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.14 | OperatingScore.js, /api/operating-score | 1 | Content | 'Not enough data' empty state -- coaching, not stat-dump | Current 'still learning your business' block shows 3 tiles (Actionable / Completed / Decisions) -- MPWA-12i already fixed the NaN bug but the block is still cold. Replace with a checklist: [ ] Capture 3 decisions (2 of 3 done) [x] Add first invoice. Each unchecked item links to the capture flow. | P1 | M | Done |  | Shipped 2026-08-17 as Sprint 1 batch 2 (with U7-01.26). Verified: backend /operating-score returns view='owner' with my_snapshot; SelfView renders clean with all helpers; no React console errors. OwnerView visual polish (formula panel + empty-state coaching + skeleton) components compile without errors; render-path verification blocked in preview by cookie-origin quirk (localhost vs 127.0.0.1 cookie jars), will confirm on next live deploy. | Founder ask 2026-08-17
U7-01.15 | OperatingScore.js, /api/operating-score | 1 | Interaction | Empty state -- inline capture prompt | Instead of routing to Desk to capture a decision, add a mini voice/text-capture widget directly inside the empty state so first-time users don't bounce. | P2 | M | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.16 | OperatingScore.js, /api/operating-score | 1 | Content | Score explainer -- inline info tooltip per category + full formula page | Every category bar gets an (i) tooltip: what it measures + formula. A 'How is this calculated?' link at the bottom opens a full-formula page (or modal) explaining weights (35/25/20/20), formulas, and design intent. Trust matters -- opaque scores get ignored. | P1 | M | Done |  | Shipped 2026-08-17 as Sprint 1 batch 2 (with U7-01.26). Verified: backend /operating-score returns view='owner' with my_snapshot; SelfView renders clean with all helpers; no React console errors. OwnerView visual polish (formula panel + empty-state coaching + skeleton) components compile without errors; render-path verification blocked in preview by cookie-origin quirk (localhost vs 127.0.0.1 cookie jars), will confirm on next live deploy. | Founder ask 2026-08-17
U7-01.17 | OperatingScore.js, /api/operating-score | 1 | IA | Category weights -- allow tenant to customize per business | Hardcoded 35/25/20/20 today. Manufacturers weight execution higher; consultancies weight responsiveness higher. Owner-editable in Settings > Business. Backend accepts weight overrides in tenant.operating_score_weights; frontend surfaces a 'Customize weights' link on the score page. | P2 | L | Done |  | Frontend demo shipped 2026-08-17 (Sprint 1 batch 3). Hardcoded/mock data in _operatingScoreDemo.js for: 30-day trend, week-over-week delta, per-category drivers, drill-down items, Dex narrative + explainer, suggested actions, employee deltas, weight presets. Backend wiring lands next -- each demo constant carries a comment naming the endpoint it will replace. Founder ask 2026-08-17: 'in this full system just put the implement the demo only we will wire up all the backend later. implement all the frontend part'. Zero React errors on compile; both SelfView (non-owner) and OwnerView (owner) code paths compile clean; OwnerView pixel walkthrough blocked in preview by cookie-origin quirk, founder to verify on next deploy. | Founder ask 2026-08-17
U7-01.18 | OperatingScore.js, /api/operating-score | 1 | Consistency | Kill hardcoded colors -- adopt indigo tokens + semantic tokens | OperatingScore uses bg-brand-blue, bg-brand-yellow, bg-green-600, bg-purple-600, text-brand-600, text-amber-600, text-danger-600. All pre-rebrand. Migrate to Chinmay's DS-1..5 indigo palette + semantic tokens (success/warning/danger). Cross-references sprint 14. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-01.19 | OperatingScore.js, /api/operating-score | 1 | Consistency | Typography -- adopt DS-1..5 type ramp | Uses font-heading + font-mono + font-black + tracking-tight + text-6xl throughout. Pre-rebrand. Migrate to the new type ramp so the page feels native to the rest of the redesigned app. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-01.20 | OperatingScore.js, /api/operating-score | 1 | Interaction | Loading skeleton -- match final shape, not 'Computing operating score…' text | Line 28: current loading is a font-mono centered text. Replace with skeleton (score circle placeholder, 4 category bar placeholders, 4 stat tile placeholders, leaderboard row placeholders). Cross-references sprint 15. | P1 | S | Done |  | Shipped 2026-08-17 as Sprint 1 batch 2 (with U7-01.26). Verified: backend /operating-score returns view='owner' with my_snapshot; SelfView renders clean with all helpers; no React console errors. OwnerView visual polish (formula panel + empty-state coaching + skeleton) components compile without errors; render-path verification blocked in preview by cookie-origin quirk (localhost vs 127.0.0.1 cookie jars), will confirm on next live deploy. | Founder ask 2026-08-17
U7-01.21 | OperatingScore.js, /api/operating-score | 1 | A11y | Category bars + score circle -- screen-reader-friendly labels | Current bars are pure visual (background div + fill div). Add aria-label='Execution: 72 out of 100' on each and role='progressbar' with aria-valuenow/valuemin/valuemax. Same for overall score. Cross-references sprint 16. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-01.22 | OperatingScore.js, /api/operating-score | 1 | Mobile parity | Create OperatingScoreMobile.jsx | MPWA-* series left this out. Score is high-signal for owner on mobile -- deserves a proper mobile pass. Hero score compact, category cards stack vertically, drill-downs open as bottom sheets, leaderboard rows one-line. Cross-references sprint 17. | P0 | L | Backlog |  |  | Founder ask 2026-08-17
U7-01.23 | OperatingScore.js, /api/operating-score | 1 | IA | Non-owner view -- what does a team member see? | Backend uses require_role('owner') -> non-owners get 403 silently. Frontend never shows the page in nav for non-owners, but /operating-score direct link 403s. Decision: (a) route non-owners to /coach (their own score), or (b) show a stripped 'only the owner sees Operating Score -- ask them if you need it' page. Also hide the nav item for non-owners. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-01.24 | OperatingScore.js, /api/operating-score | 1 | Interaction | Weekly snapshot email to owner | 'Your Operating Score, Aug 17: 76/100 (+4). Weakest: Responsiveness (2 complaints open >7 days). Suggested: assign to Priya today.' Auto-send Monday 9am IST. Owner-opt-in in Settings > Account. | P3 | M | Backlog |  |  | Founder ask 2026-08-17
U7-01.25 | OperatingScore.js, /api/operating-score | 1 | Content | Shareable summary -- one-pager for board/advisors | '/operating-score/share?token=…' link (owner-generated, 30-day TTL) opens read-only one-pager: score + trend + 4 categories + 1 sentence narrative. No login required. No employee names -- aggregated only. | P3 | M | Backlog |  |  | Founder ask 2026-08-17
U7-02.1 | Landing.js, Login.js, Signup.js | 2 | Visual | Landing hero -- state the value in one sentence | Current hero uses stock 'AI for business' framing. Rewrite to the founder-persona sentence: what DecisionOS actually does for an owner-operator (voice capture -> decisions -> workflow). Tie to the indigo palette; give the hero a single characteristic moment, not a generic gradient. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-02.2 | Landing.js, Login.js, Signup.js | 2 | Interaction | Login form -- error states that name what to do | Current: '401 Unauthorized' bubble. Target: 'Password doesn't match this account. Reset it?' with a link. Same for OTP invalid, tenant not found, rate-limit hit. Every error names the fix. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-02.3 | Landing.js, Login.js, Signup.js | 2 | IA | Signup -- collapse company + role picker into one flow | Two-step form today (company details, then role choice). Merge into one screen with progressive reveal so first-time users see one page, not a wizard. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-02.4 | Landing.js, Login.js, Signup.js | 2 | A11y | Auth pages -- focus rings + tab order audit | Verify tab order is Email -> Password -> Submit (not scrambled by absolute positioning). Focus rings visible on both themes. Enter key submits. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-02.5 | Landing.js, Login.js, Signup.js | 2 | Consistency | Landing -- unify with in-app design tokens (post-DS-1..5) | Landing currently uses its own color palette (pre-rebrand). Adopt the indigo tokens Chinmay shipped in DS-1..5 so a logged-out user sees the same brand as a logged-in one. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-02.6 | Landing.js, Login.js, Signup.js | 2 | Mobile parity | Signup + Login on mobile -- test one-hand reach | Auth is the first touch and must work one-handed. Bottom-anchor the primary CTA on mobile viewport, verify iOS Safari address-bar overlap doesn't hide it. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-03.1 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | IA | Onboarding progress -- persistent step indicator | 5 screens (Basics -> Website -> Voice -> Mascot -> Reveal). Currently no top-level '3 of 5' indicator. Add fixed progress rail so users know how much is left. Blocks abandonment. | P0 | S | Backlog |  |  | Founder ask 2026-08-17
U7-03.2 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | Interaction | WebsiteIntel -- clarify what the AI is doing while waiting | The AI takes 15-40s to scrape + summarize a website. Show live progress with meaningful steps ('Fetching homepage...', 'Reading team page...', 'Summarizing product'). No spinner-in-void. | P0 | M | Backlog |  |  | Founder ask 2026-08-17
U7-03.3 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | Content | VoiceInterview -- rewrite Dex's questions for a first-time founder | Current questions read like an intake form. Rewrite in Dex's voice as a conversation: warm, curious, laser-focused on 1 answer per turn. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-03.4 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | Visual | BuildReveal -- the operating-model reveal moment needs delight | This is the 'magic moment' after signup. Current reveal is a static list. Add a build-in animation that unveils each pipeline card as if Dex is showing the founder around. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-03.5 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | Interaction | AI-status banner -- when generation is 'defaulted' or 'failed' | FIX-001-D added ai_setup_status per generator. Surface a friendly 'AI setup incomplete -- click to regenerate' banner post-onboarding when any generator defaulted/failed. Wire to /api/tenant/ai-setup/retry. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-03.6 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | Consistency | Onboarding screens -- shared shell + type ramp | Each of the 5 screens has slightly different padding, header size, CTA weight. Extract a shared OnboardingLayout with consistent H1/subhead/CTA slots. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-03.7 | BasicsFlow, WebsiteIntel, VoiceInterview, DexMascot, BuildReveal | 3 | Mobile parity | Onboarding -- test full flow on mobile | Some steps (VoiceInterview mic permission, WebsiteIntel URL paste, BuildReveal scroll) have never been tested on mobile viewport. Full walkthrough on iPhone SE + Pixel. | P0 | M | Backlog |  |  | Founder ask 2026-08-17
U7-04.1 | Desk.js | 4 | IA | Desk narrative -- upgrade template to LLM-generated | E3-06 tracks this in Epic 3, but the UX/UI shape belongs here: how does the narrative differ in tone/length/structure? Design the LLM output shape before Epic 3 codes it. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-04.2 | Desk.js | 4 | Visual | Chip row -- consistent height, spacing, icon weight | Needs Decision / On Fire / Due Today / Important chips are visually noisy. Tighten to a single row with unified icon size, chip padding, and count-badge treatment. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-04.3 | Desk.js | 4 | Interaction | Trends section -- deep-link rows to filtered MyWork/CRM | Sprint 6.5 wired this. Audit: do all rows actually deep-link with the right filter params? Are the target screens' filter chips visibly active on arrival? | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-04.4 | Desk.js | 4 | Content | Empty state -- 'no decisions yet' shouldn't be a full stop | Current empty state is 'You have no decisions.' Rewrite as a coaching moment: 'Capture your first decision via voice, WhatsApp, or the text box below.' with a clear CTA. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-04.5 | Desk.js | 4 | Interaction | Capture bar -- location + affordance | Post E2-30 Ingest retirement, capture lives in Dex. Verify Desk still has quick-capture affordance (or clear path). Founder muscle memory is 'open app -> talk'. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-04.6 | Desk.js | 4 | A11y | Chip counts -- screen reader labels ('3 needs decision') | Count badges are visual-only. Add aria-label so screen readers announce '3 needs decision' not just '3'. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-05.1 | MyWork.js | 5 | Visual | Stage chip (WE-11) -- design pass for the chip itself | The engine chip lands correctly but its visual weight competes with the task title. Rework: smaller chip, muted background, workflow-type icon prefix. | P1 | S | Done |  | Shipped 2026-08-17 (Sprint 5 batch 1). TaskCard collapses to a summary row by default -- title + priority + status pill + due-date OR OVERDUE (red stripe on card + red badge). Stage chip becomes a tiny inline pill in the summary; full workflow chip lives in the expanded body. Click any row toggles expand; other cards stay collapsed. Verified live: Priya's 4 sales tasks render as 4 clean rows, expand-in-place shows full detail (due, progress, actions, plan, trail). Highlighted cards (deep-link focus) auto-expand. | Founder ask 2026-08-17
U7-05.2 | MyWork.js | 5 | IA | Task card -- what's above the fold matters most | Title / assignee / due / stage / priority all render currently. Decide the 3 hero elements and demote the rest to hover/expand. | P1 | M | Done |  | Shipped 2026-08-17 (Sprint 5 batch 1). TaskCard collapses to a summary row by default -- title + priority + status pill + due-date OR OVERDUE (red stripe on card + red badge). Stage chip becomes a tiny inline pill in the summary; full workflow chip lives in the expanded body. Click any row toggles expand; other cards stay collapsed. Verified live: Priya's 4 sales tasks render as 4 clean rows, expand-in-place shows full detail (due, progress, actions, plan, trail). Highlighted cards (deep-link focus) auto-expand. | Founder ask 2026-08-17
U7-05.3 | MyWork.js | 5 | Interaction | Bulk actions -- select multiple tasks + advance/complete/reassign | No bulk operations today. Adding checkbox column + bulk-action bar unlocks power users. | P2 | M | Done |  | Shipped 2026-08-17 (Sprint 5 batch 2). Bulk select + action bar. Each TaskCard summary row now has a checkbox (outside the expand button so click doesn't toggle the card). Selecting 1+ tasks reveals a sticky bulk-action bar at the top of the list: 'N selected · Complete N · Reassign · Clear'. Complete applies status=done to all selected non-terminal tasks (Promise.all of PATCH calls). Reassign opens a dialog to pick assignee_id OR assignee_role, then applies the patch to all selected. Selection clears on scope/tab/view change. Backend batch endpoint tracked separately in Sprint 5 backlog. | Founder ask 2026-08-17
U7-05.4 | MyWork.js | 5 | Content | AI-Priority explanation -- 'why is this ranked here?' | Priority score exists but the reason is invisible. Add hover tooltip: 'High: overdue 2d, blocks 3 workflows'. | P2 | S | Done |  | Shipped 2026-08-17 (Sprint 5 batch 2). PriorityScoreBars now carries per-bar tooltips via native title attribute: Impact ('customer weight, workflow blockage, cross-team deps'), Revenue ('unpaid, overdue, deal value'), Risk ('complaints, compliance, penalties'), Urgency ('overdue days, hours-to-due, escalation'). Plus the overall priority_score has 'weighted mix of four signals below' tooltip. Users can hover any label to understand what drove the number. | Founder ask 2026-08-17
U7-05.5 | MyWork.js | 5 | Interaction | Filter chips -- persist per user, restore on return | Filters (mine/all, category, priority) reset on navigation. Persist in localStorage per tenant+user. | P2 | S | Done |  | Shipped 2026-08-17 (Sprint 5 batch 2). scope + tab + aiPriority persist in localStorage per tenant+user (key: mywork-prefs-<tid>-<uid>). Reload the page, come back tomorrow, navigate away and back -- same filters. Guarded on prefsKey so pre-login / test contexts stay no-op. Founder ask: 'remove the uneasy UX' -- resetting to 'All / Mine / no AI' every navigation was frustrating for someone who works in one category. | Founder ask 2026-08-17
U7-05.6 | MyWork.js | 5 | Mobile parity | MyWorkMobile.jsx -- verify stage chips + AI-priority parity | Chinmay's MyWorkMobile shipped. Audit that WE-11 chips, category filters, and AI-priority sort match desktop. | P1 | S | Done |  | Verified 2026-08-17 (Sprint 5 batch 2). MyWorkMobile.jsx (MPWA-08) already uses card-plus-sheet pattern (rows collapse to 3 lines, expand to sheet), so density parity holds without new changes. Only gap: AI Priority button was visible to non-owners on mobile too -- gated on isOwner to match desktop. Full bulk-actions + filter persistence for mobile deferred (mobile has its own UX pattern for these -- backlog item). | Founder ask 2026-08-17
U7-06.1 | Workflows.js | 6 | Visual | Kanban card density -- reduce chrome, elevate content | Cards currently have too much padding + drop shadow. Flatten, tighten spacing, let workflow title breathe. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-06.2 | Workflows.js | 6 | Interaction | Inline task list (WE-12) -- collapse/expand affordance | Task list expands by default under each workflow card. Add per-card collapse memory (localStorage) so the board isn't a wall of tasks. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-06.3 | Workflows.js | 6 | Interaction | Manual advance (WE-13) -- reason dialog polish | Reason dialog works but is spartan. Add: role-appropriate suggestions ('Skipping approval -- customer paid upfront'), character counter, prior-reasons dropdown. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-06.4 | Workflows.js | 6 | IA | Board vs list -- second time we've had this discussion (WE-14) | Board sub-tab was retired by WE-14. Verify: is there a genuine use case for a list view? If yes, bring it back explicitly. If no, mark this decision permanent in the Cover sheet. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-06.5 | Workflows.js | 6 | Content | Workflow type labels -- match founder's vocabulary | Types like 'purchase_payment' render literally. Wire to the lexicon.workflows table so 'Client Billing' shows for Tracole, 'Order' shows for Kapoor, etc. | P0 | M | Backlog |  |  | Founder ask 2026-08-17
U7-06.6 | Workflows.js | 6 | A11y | Kanban -- keyboard drag between stages | Drag-and-drop is mouse-only today. Add keyboard equivalent: focus card -> press M -> arrow keys move stage. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-07.1 | CRM.js, Contacts.js, ContactProfile.js | 7 | IA | Contacts vs CRM -- what's the difference to the user? | Two nav items, similar screens. Either merge (recommend) or write clear labels that separate them (Contacts = people, CRM = pipeline). Founder to decide. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-07.2 | CRM.js, Contacts.js, ContactProfile.js | 7 | Visual | ContactProfile -- 360 view density | Profile page has: header + AI relationship intel + last activity + tasks + finance history. Long scroll. Move to 2-column desktop layout with sticky header. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-07.3 | CRM.js, Contacts.js, ContactProfile.js | 7 | Interaction | Bulk CSV import (E2-72) -- error surfacing | CSV import shipped. Audit: what happens on partial failure (5 of 20 rows bad)? Show inline row-by-row errors with 'fix + retry'. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-07.4 | CRM.js, Contacts.js, ContactProfile.js | 7 | Content | AI Relationship Intelligence -- explain the score | Score renders as a number today. Add: 'Score 8/10: 5 recent touches, 2 quick replies, 1 outstanding invoice.' | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-07.5 | CRM.js, Contacts.js, ContactProfile.js | 7 | Consistency | Contact card -- one shape across CRM / MyWork / Desk / ContactProfile | The mini contact card renders 4+ ways in the app. Extract a ContactChip component with size variants; retire the duplicates. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-07.6 | CRM.js, Contacts.js, ContactProfile.js | 7 | Mobile parity | CRMMobile + ContactProfileMobile -- feature parity check | MPWA-10 shipped both. Verify bulk import, AI intel, and filter chips work identically on mobile. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-08.1 | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js | 8 | IA | Finance hero -- what's the one number the founder needs? | Current: 6 tiles (revenue, expenses, receivables, payables, cash, KPI). Decide the hero metric per persona and elevate; demote the rest to a strip. | P0 | M | Backlog |  |  | Founder ask 2026-08-17
U7-08.2 | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js | 8 | Interaction | Ledger AI insight cards -- add 'Ask Dex about this' chip | E3-01 in Epic 3 backlog. UX/UI shape (chip placement, hover, tap target) belongs here. Design before Epic 3 codes. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-08.3 | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js | 8 | Visual | ReviewPanel -- classify + approve UX | AI-classified expense review has a busy layout with amount / category / reason / actions all on one row. Restructure with clear left-to-right reading order. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-08.4 | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js | 8 | Content | WhatsAppCard -- explain what happens when user replies to nudge | The WhatsApp capture card doesn't tell the user what happens if they reply. Add a one-liner + example. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-08.5 | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js | 8 | Interaction | Expense drill-down -- from summary to line-item in one tap | Currently: click summary -> new page -> scroll to find. Add inline drawer that reveals line items in place. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-08.6 | Finance.js, Ledger.js, finance/ReviewPanel.js, finance/WhatsAppCard.js | 8 | Mobile parity | FinanceMobile.jsx -- receipt scan / voice-capture flow | MPWA-09 shipped Finance mobile. Verify receipt-scan camera capture + voice-expense flow work on iOS Safari (camera permissions differ from Android). | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-09.1 | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js | 9 | Visual | Dex avatar / persona presence throughout the app | Post E2-40 persona prefix, Dex has a voice but no visual presence. Add a subtle avatar chip next to every AI-generated answer + narrative section. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-09.2 | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js | 9 | Interaction | Ask panel -- streaming responses with clear stop control | AI answers stream today. Add visible 'Stop generating' button, retry button, and copy-to-clipboard on the completed response. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-09.3 | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js | 9 | IA | Documents tab -- from list to searchable + previewable | BrainDocuments is a flat list. Add search-by-content, preview-on-hover, and 'ask Dex about this doc' action. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-09.4 | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js | 9 | Content | Dex empty state -- coaching, not silence | New tenant opens Dex -> empty search screen. Show 3-5 example prompts specific to their industry (from operating_model). | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-09.5 | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js | 9 | Interaction | Context chip persistence -- ?context= URL param behavior | E3-01..04 will land 'Ask Dex about this' chips. Design the context handling: does the chip prefill and stay pinned? Clearable? Persists across turns in the conversation? | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-09.6 | Brain.js (/dex), BrainDocuments.js, AskAI.js, Captures.js | 9 | A11y | Voice capture -- transcript live-region announcement | Screen reader users need to know transcription is happening. Add aria-live region on the transcript preview. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-10.1 | Team.js, People.js, WorkCoach.js | 10 | IA | Team vs People -- clarify or merge | Same pattern as Contacts/CRM. Two nav items with overlap. Decide + document. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-10.2 | Team.js, People.js, WorkCoach.js | 10 | Interaction | WorkCoach -- action affordance per improvement | Each 'improvement' item is text-only. Add per-item 'Ask Dex to coach me on this' (E3-03) + 'Mark as working on'. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-10.3 | Team.js, People.js, WorkCoach.js | 10 | Content | Team roster -- role labels match tenant lexicon | Currently 'sales', 'operations', etc. hardcoded. Wire to tenant lexicon so custom roles ('Consignee liaison' for Tracole) render. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-10.4 | Team.js, People.js, WorkCoach.js | 10 | Consistency | Person card -- unify with ContactChip | Team person card duplicates ContactChip shape. Merge under one component. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-10.5 | Team.js, People.js, WorkCoach.js | 10 | Mobile parity | TeamMobile.jsx -- role editor UX on small screens | MPWA-10 shipped. Role editing on mobile needs specific attention -- verify custom role add flow works. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-11.1 | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js | 11 | IA | Notifications -- collapse by source + persist read state | Current: flat list. Group by source (workflow, task, decision, mention) with unread count per group. Persist read state properly. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-11.2 | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js | 11 | Visual | Calendar -- density + weekend treatment | Calendar reads as a wall of blocks today. Add zebra-striping for weekends, tighter row height, muted past days. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-11.3 | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js | 11 | Interaction | Leave -- request flow one-tap-to-submit | 3-field form. Simplify: type (dropdown), dates (range picker), reason (optional). Auto-submit on valid state, one confirmation toast. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-11.4 | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js | 11 | Content | Journal -- headline + first-line preview per entry | Journal entries render title-only. Add first-line preview so the founder can scan without opening each. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-11.5 | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js | 11 | Interaction | Notification bell -- unread badge sync + click behavior | Bell shows count but click behavior varies. Standardize: click = open notification panel, mark visible items as read after 3s. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-11.6 | Calendar.js, (Meetings), Leave.js, Journal.js, Notifications.js | 11 | A11y | Meetings -- audio recording indicator + permission fallback | If mic permission denied, current UX just fails silently. Show 'Recording unavailable -- enable mic in browser settings' with link. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-12.1 | Settings.js (4-tab from WE-04) | 12 | Interaction | Business tab -- lexicon editor with live preview | Editing lexicon (Customer -> Consignee) affects labels everywhere. Add a live preview panel showing 3-4 sample labels updating as user types. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-12.2 | Settings.js (4-tab from WE-04) | 12 | Interaction | Operations tab -- stage editor (WE-04) polish | WE-04 shipped stage tasks/approval/side-effects editors. Audit: are the JSON side-effect params user-friendly? Add form-based param editor per side-effect type. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-12.3 | Settings.js (4-tab from WE-04) | 12 | Visual | Settings -- section headers + save-state indication | Each tab has multiple sections; unclear when changes save (autosave? save button?). Add explicit save indicator per section. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-12.4 | Settings.js (4-tab from WE-04) | 12 | Content | Account tab -- 2FA + session mgmt copy | TOTP setup (RBAC-23) works but copy is technical. Rewrite for a non-technical founder: 'Add a second lock to your account'. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-12.5 | Settings.js (4-tab from WE-04) | 12 | Consistency | Settings tabs -- consistent form pattern (label above, help text below) | Some forms label-inline, some label-above. Pick one, apply everywhere. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-12.6 | Settings.js (4-tab from WE-04) | 12 | Mobile parity | SettingsMobile.jsx -- WE-04 tab structure on mobile | MPWA-11 wrapped Settings with useIsMobile() early return. Verify each of 4 tabs renders + saves on mobile. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-13.1 | admin/AdminPortal.js, admin/AdminSections.js, admin/AdminLogin.js | 13 | IA | Admin dashboard -- what does a superadmin need first? | Current landing is a tenant list. Add hero: total tenants / active this week / usage $ this month / support tickets. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-13.2 | admin/AdminPortal.js, admin/AdminSections.js, admin/AdminLogin.js | 13 | Visual | Tenant list -- search, filter, bulk actions | Currently a flat table. Add search-by-name/email, filter by plan/status, bulk action bar. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-13.3 | admin/AdminPortal.js, admin/AdminSections.js, admin/AdminLogin.js | 13 | Interaction | Usage tally -- per-tenant + per-provider breakdown | Usage total renders but no breakdown. Add: expand row to see per-tenant AI/SMS/storage costs; per-provider (Anthropic/Twilio) split. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-13.4 | admin/AdminPortal.js, admin/AdminSections.js, admin/AdminLogin.js | 13 | Content | Admin actions -- confirm dialogs that name the blast radius | 'Deprovision tenant' / 'Reset AI keys' need dialogs that name what breaks. 'This will remove access for 12 users and revoke 2 API keys. Type CONFIRM to proceed.' | P0 | S | Backlog |  |  | Founder ask 2026-08-17
U7-13.5 | admin/AdminPortal.js, admin/AdminSections.js, admin/AdminLogin.js | 13 | A11y | Admin -- keyboard-driven bulk actions | Admin power users work keyboard-only. Ensure all bulk actions have keyboard shortcuts + shortcut hint. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-14.1 | tailwind.config.js, shared components | 14 | Consistency | Kill all hardcoded hex + shadow values in src/ | Post-Chinmay indigo rebrand, ensure every color reference is a token. Run grep for #[0-9A-Fa-f]{3,6} in JS/JSX and refactor. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-14.2 | tailwind.config.js, shared components | 14 | Consistency | Type scale -- one ramp, one line-height ramp | Currently mixed: text-sm, text-base, [11px], custom leading. Consolidate to a documented type scale (H1/H2/H3/body/caption/mono). | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-14.3 | tailwind.config.js, shared components | 14 | Consistency | Spacing scale -- 4pt grid enforcement | Ad-hoc padding values throughout (p-3, p-4, p-5). Standardize on 4pt spacing tokens; document exceptions. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-14.4 | tailwind.config.js, shared components | 14 | Visual | Icon system -- one library, consistent stroke weight | Currently mixing Heroicons + inline SVG + emoji. Pick one (recommend Lucide or Heroicons), unify weight, document. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-14.5 | tailwind.config.js, shared components | 14 | Content | Design system docs page (in-app) | Extend DesignLab.js or add a /design-system page documenting: colors, type, spacing, components, do/don't examples. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-15.1 | cross-cutting | 15 | Interaction | Every list has a real empty state (no full stops) | MPWA-12i started this on mobile. Extend to desktop: every list/table/panel gets a domain-specific empty state with an action. | P1 | L | Backlog |  |  | Founder ask 2026-08-17
U7-15.2 | cross-cutting | 15 | Interaction | Skeleton loaders that match final shape | Currently mix of spinners and generic gray blocks. Every load state should be a skeleton that matches the final layout so users see 'oh, that's a task card loading' not 'oh, something is loading'. | P1 | L | Backlog |  |  | Founder ask 2026-08-17
U7-15.3 | cross-cutting | 15 | Interaction | Error states -- what went wrong + what to do | Every error surface (network, permission, validation) gets: what broke, why, one-click retry or fallback path. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-15.4 | cross-cutting | 15 | Content | Loading text -- specific, occasionally playful | 'Loading...' everywhere. Replace with domain-specific + tone-aware: 'Rounding up your decisions', 'Sorting your inbox'. Keep serious contexts boring (finance, admin). | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-16.1 | cross-cutting | 16 | A11y | Color contrast -- automated audit + fix pass | Run axe-core / Lighthouse over every page. Fix all AA failures. Document minimum contrast (4.5:1 body, 3:1 large text) in design system. | P0 | M | Backlog |  |  | Founder ask 2026-08-17
U7-16.2 | cross-cutting | 16 | A11y | Keyboard navigation -- every interactive element reachable + activatable | Tab order sensible, no keyboard traps, custom widgets (kanban, calendar) have equivalent keyboard interaction. Document per widget. | P0 | L | Backlog |  |  | Founder ask 2026-08-17
U7-16.3 | cross-cutting | 16 | A11y | Focus rings -- visible on both themes | Currently focus ring is often :focus:ring-2 with a color that vanishes in dark mode. Standardize a focus token that reads in both. | P0 | M | Backlog |  |  | Founder ask 2026-08-17
U7-16.4 | cross-cutting | 16 | A11y | Screen reader labels -- icons, buttons, dynamic content | Icon-only buttons need aria-label. Live regions for AI streaming, toasts, notification counts. Test with NVDA + VoiceOver. | P1 | L | Backlog |  |  | Founder ask 2026-08-17
U7-16.5 | cross-cutting | 16 | A11y | Touch targets -- 44x44 minimum on mobile | Audit mobile viewport for tap targets < 44px. Bump hitboxes without changing visual size where needed. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-16.6 | cross-cutting | 16 | A11y | Reduced motion -- respect prefers-reduced-motion | Any transition/animation > 200ms should be disabled when user prefers reduced motion. Add global handler + audit. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-17.1 | frontend/src/pages/mobile/*, service-worker.js | 17 | Mobile parity | Screens without a *Mobile.jsx yet -- prioritize + ship | MPWA shipped 7 mobile pages (CRM, ContactProfile, Desk, Finance, MyWork, Settings, Team). Missing: Workflows, Dex/Brain, Journal, Calendar, Leave, Notifications, WorkCoach, OperatingScore. Rank + ship in priority order. | P1 | L | Backlog |  |  | Founder ask 2026-08-17
U7-17.2 | frontend/src/pages/mobile/*, service-worker.js | 17 | Interaction | PWA install prompt -- when + how | Currently no controlled install prompt. Add a coach-mark after 3rd session: 'Install DecisionOS for one-tap access + push notifications'. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-17.3 | frontend/src/pages/mobile/*, service-worker.js | 17 | Interaction | Offline-first for read-heavy screens | MyWork, Desk, ContactProfile should be readable offline (cached last-known state). Service worker (service-worker.js) needs fine-tuned cache strategy per route. | P1 | L | Backlog |  |  | Founder ask 2026-08-17
U7-17.4 | frontend/src/pages/mobile/*, service-worker.js | 17 | Visual | Splash + app icons -- brand-aligned | Post-rebrand, PWA splash + icons need refresh. Generate full icon set (16, 32, 180, 192, 512, maskable) from the indigo lockup. | P1 | S | Backlog |  |  | Founder ask 2026-08-17
U7-17.5 | frontend/src/pages/mobile/*, service-worker.js | 17 | A11y | Mobile gestures -- ensure keyboard/switch-control equivalents | Swipe-to-dismiss, long-press menus need button equivalents for switch-control + external-keyboard users. | P2 | M | Backlog |  |  | Founder ask 2026-08-17
U7-18.1 | cross-cutting | 18 | Content | Button labels -- audit for action verbs (not 'Submit') | Sweep every button. 'Submit' becomes 'Publish' / 'Send' / 'Save changes'. Confirmations then say 'Published' / 'Sent' / 'Saved'. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-18.2 | cross-cutting | 18 | Content | Error messages -- rewrite the top 20 into human sentences | Grep for common error messages, list top 20 by frequency, rewrite each into: what happened + why + what to do. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-18.3 | cross-cutting | 18 | Content | Onboarding + Dex + WorkCoach voice consistency | Dex speaks in one voice, WorkCoach in another, onboarding in a third. Pick the primary voice + rewrite outliers. | P1 | M | Backlog |  |  | Founder ask 2026-08-17
U7-18.4 | cross-cutting | 18 | Consistency | Toast + dialog vocabulary -- 'Confirm', 'Cancel', 'Discard' standardized | 'OK / Yes / Confirm / Save' vary across the app. Pick pairs (Save/Discard, Confirm/Cancel) and enforce. | P2 | S | Backlog |  |  | Founder ask 2026-08-17
U7-18.5 | cross-cutting | 18 | Interaction | Epic 7 exit gate -- full E2E across desktop + mobile | Golden path: signup -> onboarding -> capture decision -> workflow advances -> finance reviewed -> team assigned. Run desktop + iPhone SE + Pixel + tablet. Zero P0/P1 bugs. | P0 | L | Backlog |  |  | Founder ask 2026-08-17
U7-01.26 | OperatingScore.js, /api/operating-score | 1 | IA | Phase A -- role-aware payload dispatcher + SelfView + PersonalSnapshot | STRUCTURAL FOUNDATION for Sprint 1 -- shipped 2026-08-17. Backend /api/operating-score dropped require_role('owner') and now dispatches by role: owner keeps the company payload plus a new my_snapshot widget; every non-owner gets a self-focused view (self, stats, my_open_work, my_active_workflows, peer_context). Frontend OperatingScore.js became a dispatcher that renders OwnerView vs SelfView based on the payload's view discriminator. Reuses compute_employee_stats so the richer signals (proof-upload rate, plan adoption) that the WorkCoach path already computed are now the IC's landing view. Also dropped the frontend ownerOnly nav gate + route protection so the page is visible to every authenticated user. Peer context hides when role has <2 ranked peers. Founder ask 2026-08-17: 'if the team person login and go the ops it have to show the individuals person metrics'. | P0 | M | Done | (none) | Verified live in preview against Kapoor demo tenant: Owner (Rajesh) sees company view + personal snapshot; Finance (Sunita) sees personal 0/100 + 5 open tasks + WorkCoach link; Sales (Priya) sees personal 0/100 + 4 open tasks with sales-specific titles. 5/5 pytest guards green (test_operating_score_role_split.py). | Founder ask 2026-08-17
U7-01.27 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: 30-day operating-score snapshot history + daily cron | NEW COLLECTION operating_score_history: {tenant_id, date, overall, categories: {execution, finance, sales, responsiveness}, employees: [{id, score}], stats}. Daily cron writes one row per tenant per day at 03:00 IST. GET /api/operating-score-history?days=30 returns the last 30. Replaces _operatingScoreDemo.demoTrend. Starts fresh on ship day (per open decision #5 in the analysis doc); sparkline appears from day 1 as a single dot and fills out over 30 days. | P1 | M | Backlog | U7-01.3 | Wire target: HeroCard sparkline (U7-01.3 shipped as demo). | Founder ask 2026-08-17
U7-01.28 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: week-over-week delta computation from history | Compute this_week_avg - last_week_avg from operating_score_history. Return in /api/operating-score as company.delta = {value, sign, period}. First 7 days after ship day: return null (not enough data). Replaces _operatingScoreDemo.demoDelta. | P1 | S | Backlog | U7-01.27 | Wire target: HeroCard DeltaChip (U7-01.1 shipped as demo). Also enables per-employee deltas (U7-01.33). | Founder ask 2026-08-17
U7-01.29 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: per-category drivers in /operating-score payload | Extend /operating-score response with drivers per category. Owner view: company.drivers = {execution: [3 items], finance: [3 items], sales: [3 items], responsiveness: [3 items]} where each driver is {label, value, tone: good¦warn¦bad¦neutral}. Values derived from same tasks/invoices/decisions/complaints queries already in _company_operating_view -- new work is just picking the top 3 signals per category and formatting them. Replaces _operatingScoreDemo.demoDrivers. | P1 | M | Backlog | U7-01.4 | Wire target: CategoryCard drivers (U7-01.4 shipped as demo). | Founder ask 2026-08-17
U7-01.30 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: category drill-down endpoint | GET /api/operating-score/drill/{category} where category in {execution, finance, sales, responsiveness}. Returns {title, hero, items: [{title, meta, tone}], action: {label, to}}. Execution: top 5 tasks by status/overdue. Finance: top 5 invoices by overdue/paid. Sales: top 5 decisions by status/latency. Responsiveness: top 5 complaints by age. Owner-only. Replaces _operatingScoreDemo.demoDrilldowns. | P1 | M | Backlog | U7-01.5, U7-01.6, U7-01.7, U7-01.8 | Wire target: CategoryDrillModal (U7-01.5..8 shipped as demo). | Founder ask 2026-08-17
U7-01.31 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: Dex operating-score-explain AI endpoint | POST /api/ai/operating-score-explain -> returns {headline: str (one sentence), explainer: str (2-3 sentences, actionable), focus: category_key}. Inputs: current scores + top drivers + week-over-week deltas. Uses claude_chat under DPDP consent gate (RBAC-25). Under quota control (FIX-005-B). Cached per-tenant for 15 min (see U7-01.36). Replaces the two _operatingScoreDemo.demoDex fields (headline + explainer). Prompt design: warm, honest, names the biggest lever + estimated point-lift. | P1 | M | Backlog | U7-01.1, U7-01.9, RBAC-25 | Wire targets: HeroCard narrative (U7-01.1) + DexExplainerCard (U7-01.9). Both shipped with hardcoded demo text. | Founder ask 2026-08-17
U7-01.32 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: suggested-actions derivation from stats | Compute top 3 leverage points from current stats. Simple heuristic first (not AI): overdue_tasks > 0 -> 'Clear N overdue' with lift = min(20, N*3); open_complaints > 0 -> 'Resolve N complaints' with lift = min(15, N*5); waiting_decisions > 0 -> 'Approve N decisions' with lift = min(10, N*2); overdue_invoices > 0 -> 'Chase N invoices' with lift = min(12, N*3). Rank by lift desc, take top 3. Return in /operating-score as company.actions = [{label, to, icon, lift}]. Replaces _operatingScoreDemo.demoActions. | P1 | S | Backlog | U7-01.10 | Wire target: SuggestedActions chip row (U7-01.10 shipped as demo). | Founder ask 2026-08-17
U7-01.33 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: per-employee week-over-week delta snapshots | Extend _score_employees to also compute delta = current_score - last_week_score by reading operating_score_history[7 days ago].employees. Return per-employee: {id, name, role, score, delta}. Frontend already renders DeltaChip when delta is non-null. Replaces _operatingScoreDemo.demoEmpDeltas. | P2 | S | Backlog | U7-01.11, U7-01.27 | Wire target: Leaderboard per-row delta (U7-01.11 shipped as demo). | Founder ask 2026-08-17
U7-01.34 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: persist tenant.operating_score_weights | New field tenant.operating_score_weights: {execution: 35, finance: 25, sales: 20, responsiveness: 20} (default matches current hardcoded weights). PATCH /api/tenant extends to accept operating_score_weights (owner only). Weighted-average formula in _company_operating_view reads from tenant instead of hardcoded WEIGHTS dict. Validation: each weight in [0, 100], sum == 100. Frontend WeightsEditor (U7-01.17) posts here on save instead of local-only state. | P2 | M | Backlog | U7-01.17 | Wire target: FormulaExplainer weights editor (U7-01.17 shipped as demo). Also unlocks per-tenant score tuning (Manufacturer vs Services vs Distributor presets). | Founder ask 2026-08-17
U7-01.35 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: wire InlineCapture to POST /api/voice-notes | InlineCapture in NotEnoughDataEmptyState currently fake-sends. Wire to existing POST /api/voice-notes with {kind: 'text', source: 'ops-empty-state', transcript: <text>}. Reuse existing capture pipeline (process_voice_note -> ai_extract -> decision creation). On success, invalidate ['operating-score'] query so the score gate flips green. | P2 | S | Backlog | U7-01.15 | Wire target: InlineCapture form (U7-01.15 shipped as demo). | Founder ask 2026-08-17
U7-01.36 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: cache Dex operating-score-explain per tenant 15min | Add tenant.operating_score_explain_cache = {generated_at, headline, explainer, focus, score_snapshot}. On POST /api/ai/operating-score-explain: if cache < 15min old AND scores unchanged, return cached. Otherwise call Claude + store. Frontend refresh button forces cache bypass (via ?force=true query). Keeps AI cost bounded on the hot path (every owner page load). | P2 | S | Backlog | U7-01.31 | Companion to U7-01.31 -- ship together to keep cost bounded. | Founder ask 2026-08-17
U7-01.37 | OperatingScore.js + services/* | 1 | Backend wiring | Phase B: better metric formulas (from analysis doc) | The analysis doc's Phase B formula upgrades, batched. Execution: add first_pass_yield (% of done tasks NOT reopened within 7 days) + plan_adoption (% of tasks with accepted execution plan, from compute_employee_stats) + proof_upload_rate (already computed for IC, surface at company level). Finance: add days_sales_outstanding (avg age of unpaid invoices) + expense_ratio_trend (30-day rolling). Sales: add decision_latency (median hours capture -> approved). Responsiveness: SPLIT into complaint_response_time (median hours raised -> first response) as its own metric, and remove task overdue penalty (that's execution's job already). Founder review before coding formulas -- Phase B open decision #4 in the analysis doc. | P2 | L | Backlog | U7-01.29, docs/Epic7_Sprint1_OperatingScore_Analysis.md | This is the analysis doc's Phase B in one item. Needs founder sign-off on formula shapes before implementation -- open decision #4. | Founder ask 2026-08-17
U7-01.38 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: weekly snapshot email to owner (cron + template) | Owner-opt-in weekly digest email. Setting: tenant.owner_prefs.weekly_ops_email = true. Cron every Monday 09:00 IST: for each opt-in tenant, compose HTML email with score + delta + Dex 2-sentence narrative + top 3 actions. Uses existing SES/SendGrid provider (whichever S3-01 landed on). Skip if score unchanged in 7 days. | P3 | M | Backlog | U7-01.24, U7-01.27 | Wire target: U7-01.24 (frontend for the setting toggle + email template). Requires an email provider chosen and quota tracked. | Founder ask 2026-08-17
U7-01.39 | OperatingScore.js + services/* | 1 | Backend wiring | Backend: shareable public one-pager endpoint (signed link) | GET /public/operating-score/{token} where token is a signed JWT with tenant_id + owner_id + exp (30 days). Returns aggregated score + trend + 4 categories + Dex narrative. No employee names (aggregated only). No login required. Owner generates the link from Settings > Business with 'Share company score' button; can revoke by regenerating. | P3 | M | Backlog | U7-01.25, U7-01.27 | Wire target: U7-01.25 (frontend share page + generator UI). Board-of-directors friendly one-pager, no auth needed. | Founder ask 2026-08-17
U7-01.40 | OperatingScore.js, /api/operating-score | 1 | IA | Owner drills into teammate's full ops view (view-as) | Founder ask 2026-08-17: 'from the owner side if i click the team member is it working better or not will show their tasks all the things the individual ops has right'. Answer was NO -- leaderboard clicks went to /coach (WorkCoach) which shows only stats + AI review, no open work list, no active workflows, no peer context. Now: leaderboard click routes to /operating-score?user=X. Backend accepts ?user_id=X (owner-only, non-owners 403). Endpoint returns the target's full self-view payload plus view_as: {id, name, role} metadata so the frontend can render a 'Viewing <name> · <role> [Back to company view]' breadcrumb + a header shift ('X's operating view' instead of 'Hi X'). Owner still has a separate Coach affordance per row for jumping straight to AI coaching. Verified live: Meera drills into Sunita -> sees her 5 open tasks + workflows + stats + Dex explainer. Privacy: Priya tries to drill into Sunita -> 403 as designed. | P0 | S | Done | U7-01.26 (role split), U7-01.11 (leaderboard) | Shipped 2026-08-17 as Sprint 1 batch 4. 4 new pytest guards (view-as accepted, owner-only 403, view_as metadata present) all green -- 8/8 in test_operating_score_role_split.py. Frontend: OperatingScore.js reads ?user=X via useSearchParams; ViewAsBanner shown at top of SelfView when view_as is set; leaderboard rows now link to /operating-score?user=X (was /coach?user=X); Coach kept as secondary affordance so owner can still jump straight to WorkCoach. | Founder ask 2026-08-17
U7-05.7 | MyWork.js | 5 | IA | AI Priority button owner-only | Founder ask 2026-08-17: 'ai priority also right only for owner got it'. The ranker is a whole-team judgment tool -- for an IC it hides which of their tasks they picked to work on based on someone else's AI score. Wrapped the AI Priority toggle in `isOwner` so ICs never see it. Also does not fetch /tasks/prioritize for non-owners. | P1 | S | Done | U7-05.1, U7-05.2 | Verified live: Sales (Priya) view shows New Task / My Work / Workflows / Leave -- no AI Priority chip. Owner still gets it. | Founder ask 2026-08-17
U7-05.8 | MyWork.js | 5 | Interaction | Replace window.prompt() for reject + clarify with real Dialog | Anti-pattern cleanup. rejectTask() and clarifyTask() previously used window.prompt() which (a) blocks the browser thread, (b) returns null in some embed contexts and looks like a silent no-op (FUP-49 hit the same pattern for confirm and fixed it there), (c) has no room for helpful placeholder text or context. Now: openReasonDialog() opens a proper Dialog with a textarea, contextual placeholder ('e.g. Please add unit prices per line item.'), disabled-during-submit state, and a cancel button. Clarify requires text; reject accepts empty (matches backend contract). Shared by both actions to keep the dialog reusable. | P1 | S | Done | U7-05.1 | Anti-pattern was inconsistent with the rest of the app which uses Dialog for all reason capture. Approve+Reject+Clarify approver actions now all use the same interaction model. | Own audit 2026-08-17

## Moving to Next Epic
Moving to Next Epic - parked items
Items scoped in Epic 7 but deferred. Empty at kickoff.
ID | Origin sprint | Title | Status | Why parked