## Cover
DecisionOS
Epic 9 -- Landing Page
Kickoff | 2026-08-17 (built locally on the DecisionOS-landingpage repo; vendored into DecisionOS main repo on 2026-08-21)
Origin | Founder ask 2026-08-17: 'stand up a marketing landing page for DecisionOS -- reference-site content architecture mapped onto the Vision PDF, brand pulled from the live MVP, ship it as static HTML/CSS/JS.'
Epic 9 goal | Ship a production-quality marketing landing page (hero, problem framing, product tour, ICP, pricing, CEO Brief teaser, final CTA) that presents DecisionOS honestly, performs on mobile, and can be hosted with zero infra.
Sprint 1 -- Discovery & Planning | Content architecture + brand extraction + hero video treatment + build-vs-deploy decision. Sign off structure before any code.
Working principles | 1. Static-first: no build step, no framework, no server dependency. 2. Ship the surface honestly -- every claim maps to an actual product capability. 3. Motion serves narrative, not decoration; every animation has a job. 4. Mobile is the default; desktop is the wide-screen variant.
Note on backlog | This tracker is retrospective for Sprints 1-7 -- the landing page shipped as one continuous build over 4 days, and the sprint boundaries reflect the natural work phases in landing-page-build-tracker.md. Sprint 8 (Open Items) is forward-looking.
Sprint breakdown
>>> Sprint 1 -- Discovery & Planning
Scope | Studied a reference sites content architecture and mapped the DecisionOS Vision PDF into a matching structure. Extracted brand tokens (colours, typography) from the live MVP. Scripted a hero background video treatment for AI generation. Decided to build locally first with server deployment deferred.
Why | FOUNDATION SPRINT. Before any HTML, agree the story shape and the visual language so the build phase is execution rather than exploration.
Status | Done
>>> Sprint 2 -- Initial Build
Scope | Hero (image background, left-aligned copy, contrast typography), glassmorphism nav that hides on the hero and swipes in on scroll, local dev server, Problem section as a rounded container with individual cards and brand-colour parallax grid, pre-footer clouds-and-stars CTA, four-container comparison table with DecisionOS lifted. 71 em-dash rewrites to strip the AI-copy tell.
Why | Establish the page skeleton and the two set-piece sections (hero + problem) so later sprints have the visual language to lean on.
Status | Done
>>> Sprint 3 -- Section-by-Section Dynamic Redesign
Scope | WhisperFlow-style slice transition for the "business at scale" section. How It Works rebuilt as a 10-second counter with bento cards. Roadmap as an orbit / solar-system visual with merged stage copy. DNA section day-1-to-month-12 curve with animated dot field. CEO Brief with auto-cycling tabs, animated score dial, and ask bar. Pricing with glassmorphism cards + early-access modal. New DecisionOS logo in navbar + hero. Four-container ICP/roles section with hover interactions. Standalone Company Brain section removed, content merged elsewhere.
Why | Turn the flat sections from Sprint 2 into narrative set-pieces -- each one earns attention rather than being scrolled past.
Status | Done
>>> Sprint 4 -- First Bug-Fix Pass
Scope | Heredoc escaping bug garbling checkmarks. Invisible orbit capability pills (white on white). Broken HTML nesting in flow-lane pills. Seam line between Problem and Scale sections. Pill overlap in flow animations shared lane. DNA dot-loop glitch. DNA endpoint drifting outside its box. Ask bar resizing as text cycled. Parallax handler conflict on ghost text. Hero logo optical alignment against the headline.
Why | First honest look after Sprint 3 -- ten defects that only surface when you actually use the page. Ship-quality demands they get fixed before audit.
Status | Done
>>> Sprint 5 -- Full Audit & Top 5 Fixes
Scope | Full UX / UI / product audit with consistency ratings. Standardized the border-radius scale to four steps. Reordered nav and added a Pricing link. Cut the animation motion budget from 148 running loops down to 13. Split overloaded copy in two sections. Added a hero background video (later reverted). Compressed hero image and ICP photos by ~97%.
Why | One professional pass to catch what building-in-flow misses -- consistency drift, motion cost, information architecture, and asset weight.
Status | Done
>>> Sprint 6 -- Refinement Round
Scope | Reverted hero video to static photo. Section dividers rebuilt as matching rounded-corner overlap transitions. Hero pinned so it blurs as the next section scrolls over it. Scribble rebuilt as one smooth brush loop (later removed entirely). DNA endpoint ring redrawn as a hand-drawn pencil oval. Shared scroll-inertia driver so all scroll animation eases instead of snaps. Fixed unstyled "10 seconds" tail line, trust-strip spacing, hero logo re-alignment, "10" numeral clipping. Pricing redesigned to match sites dark/indigo language instead of a mismatched rainbow. Comparison scribble removed entirely.
Why | The pass after the audit -- go from "correct" to "considered". Where Sprint 5 measured, Sprint 6 tunes.
Status | Done
>>> Sprint 7 -- Version Control & Hosting
Scope | Initialized a git repo scoped to the landing-page folder only. Committed and pushed the site to GitHub (quazrelevate-god/DecisionOS-landingpage). Landing-page folder later vendored into the DecisionOS main repo on Backend_optimization branch (nested .git removed, files tracked as part of DecisionOS from 2026-08-21).
Why | Get the code out of a single machine and into version control before anything else lands on top.
Status | Done
>>> Sprint 8 -- Open Items
Scope | FAQ section direction -- awaiting founder sign-off on which questions belong. Logo colour vs brand colour mismatch -- flagged, unresolved. GitHub Pages hosting -- awaiting go-ahead. Production deployment beyond GitHub Pages -- deferred until traffic / SEO warrants it.
Why | The known-unknowns after Sprints 1-7 shipped. Kept as a live sprint rather than a checklist so status stays honest.
Status | In progress
>>> Sprint 9 -- Hero v2 (layered parallax + video mockup)
Scope | Rebuilt the hero from a static single-photo composition into a three-plane layered scene. Background (hero-bg.jpg -- sunset valley), middle plane (copy + video card + trust band), foreground (hero-fg.webp -- desk with laptop / notebook / glass, alpha-preserved). Replaced the 6-card metric grid with a single curved card playing a 10-second product-tour video (hero-mockup.webm + .mp4 fallback), top-cropped to hide the browser Chrome. Trust band lifted from the hero bottom into a mid-band marquee (right-to-left seamless loop, fade-edge masks, 780px contained width). Per-layer parallax on scroll -- each of the six visible elements counter-translates at its own rate (bg 30% apparent speed, fg 100%, copy 70%, video card 68%, dex 60%, trust band 55%) with an independent blur curve. Nav bar always visible on the hero (removed hide-until-scroll behaviour). Dex bubble and scroll cue removed. Autoplay hardened with 250ms poll + first-interaction fallback.
Why | The static amber-wall hero didn't communicate what DecisionOS actually IS -- it read as a motivational poster, not a product. A layered scene with an in-frame video demo tells the story in the first paint, and the parallax gives the composition three-dimensional depth without asking the visitor to interact.
Status | Done -- shipped 2026-08-28 (commit 15b51cc)
Supersedes | S5-06 (hero background video, added then reverted) and S6-03 (sticky-pin hero + blur on next-section overlap) are effectively replaced by S9. The pin-and-recede model was rebuilt as per-layer lag parallax with each plane parallaxing independently as the hero scrolls up.

## Dashboard
DecisionOS - Epic 9 - Landing Page
Static marketing landing page for DecisionOS. Static HTML/CSS/JS, no build step, no server dependency. Kickoff: 2026-08-17.
Epic 9 status: IN PROGRESS. Sprints 1-7 shipped (55/59). S9 -- Hero v2 layered parallax + video mockup -- shipped 2026-08-28 (15/15). Sprint 8 (Open Items) still tracks FAQ sign-off, logo colour mismatch, GitHub Pages hosting, and post-Pages production deployment. Total: 70/74 (95%).
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 1 | Discovery & Planning | 4 | 4 | 100% | Done | FOUNDATION SPRINT. Content architecture mapped from DecisionOS Vision PDF. Brand extracted from live MVP. Hero video treatment scripted. Build-vs-deploy decision.
Sprint 2 | Initial Build | 10 | 10 | 100% | Done | Hero + nav + Problem section + comparison table + pre-footer CTA. Page skeleton with two set-piece sections. 71 em-dash rewrites.
Sprint 3 | Section-by-Section Dynamic Redesign | 10 | 10 | 100% | Done | Every section rebuilt as a narrative set-piece: WhisperFlow slice, How It Works counter, roadmap orbit, DNA curve, CEO Brief, pricing modal, ICP tiles, logo integration.
Sprint 4 | First Bug-Fix Pass | 10 | 10 | 100% | Done | Ten defects surfaced by real use: escaping bugs, invisible pills, HTML nesting, section seams, animation glitches, hero logo alignment.
Sprint 5 | Full Audit & Top 5 Fixes | 7 | 7 | 100% | Done | Full UX/UI audit + top 5 fixes: radius scale, nav + Pricing link, motion budget 148->13, copy split, image compression ~97%.
Sprint 6 | Refinement Round | 12 | 12 | 100% | Done | Refinement pass: dividers, hero pin+blur, DNA pencil oval, scroll-inertia driver, pricing colour language, scribble removal, misc polish.
Sprint 7 | Version Control & Hosting | 2 | 2 | 100% | Done | Init git, commit + push to standalone DecisionOS-landingpage repo. Later vendored into DecisionOS main repo on Backend_optimization branch.
Sprint 8 | Open Items | 0 | 4 | 0% | In progress | FAQ direction (awaiting sign-off), logo vs brand colour mismatch (flagged), GitHub Pages hosting (awaiting go-ahead), production deployment beyond Pages (deferred).
Sprint 9 | Hero v2 (layered parallax + video mockup) | 15 | 15 | 100% | Done | Three-plane hero: sunset bg + product-tour video card + desk fg, per-layer parallax + blur, right-to-left trust marquee, autoplay hardened. Supersedes S5-06 + S6-03.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
U9-01.1 | index.html (structure) | 1 | Planning | Content-architecture mapping from Vision PDF | Studied a reference sites content architecture and mapped the DecisionOS Vision PDF into a matching structure. Sign-off before any code. | P0 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-01.2 | styles.css (tokens) | 1 | Planning | Brand extraction from live MVP | Pulled colours + typography tokens from the running DecisionOS MVP so the landing pages visual language stays consistent with the product. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-01.3 | assets/img/hero-photo.jpg | 1 | Planning | Hero background video treatment (scripted) | Scripted a hero background video treatment for AI video generation. (Video later added in Sprint 5 and reverted in Sprint 6 in favour of the static photo.) | P2 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-01.4 | deployment | 1 | Planning | Build locally first, defer server deployment | Decided to build locally against a plain HTTP dev server, ship to a static host later. No infra dependency during the build phase. | P1 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.1 | index.html (hero) | 2 | Build | Hero section | Image background, left-aligned copy, contrast typography. | P0 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.2 | index.html (nav) | 2 | Build | Glassmorphism nav header | Header hides on the hero and swipes in on scroll. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.3 | dev-server | 2 | Infra | Local dev server | Static-file dev server so hot iteration doesnt require a build step. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.4 | index.html (hero) | 2 | Build | Simplify hero to pre-header + header + CTA | Cut the hero back to three elements to stop it competing with the sections below. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.5 | index.html (all sections) | 2 | Build | Kill the slide-deck feel: remove per-section pre-headers | Removed the pre-header line from every section so the page reads as one narrative rather than nine slides. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.6 | index.html (problem) | 2 | Build | Problem section as rounded container + cards | Rebuilt the Problem section as a rounded container holding individual problem cards. | P0 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.7 | index.html (problem) | 2 | Build | Brand-colour grid background + parallax | Added a brand-colour grid background with parallax to the Problem section. | P2 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.8 | all copy | 2 | Content | Remove all em dashes (71 rewrites) | Rewrote 71 lines to eliminate em dashes across the page -- the giveaway that copy came from a model. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.9 | index.html (pre-footer) | 2 | Build | Pre-footer / final CTA -- clouds-and-stars parallax | Rebuilt the pre-footer / final CTA in a clouds-and-stars parallax style. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-02.10 | index.html (comparison) | 2 | Build | Comparison table as four vertical containers | Rebuilt the comparison table as four vertical containers with DecisionOS lifted and floating. | P0 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.1 | index.html (scale) | 3 | Redesign | WhisperFlow slice transition -- business-at-scale | Built the WhisperFlow-style slice transition for the "business at scale" section. | P1 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.2 | index.html (comparison) | 3 | Redesign | Scroll-drawn scribble behind comparison | Added a scroll-drawn scribble behind the comparison section. (Removed entirely in Sprint 6 -- too visually noisy.) | P2 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.3 | index.html (how-it-works) | 3 | Redesign | How It Works -- 10-second counter + bento cards | Rebuilt "How It Works" as a 10-second counter section with bento cards. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.4 | index.html (roadmap) | 3 | Redesign | Roadmap as orbit / solar-system visual | Rebuilt the roadmap as an orbit / solar-system visual with merged stage copy. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.5 | index.html (dna) | 3 | Redesign | DNA section curve graph + animated dot field | Built the DNA sections day-1-to-month-12 curve graph with an animated dot field. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.6 | index.html (ceo-brief) | 3 | Redesign | CEO Brief -- auto-cycling tabs, score dial, ask bar | Built the CEO Brief section with auto-cycling tabs, an animated score dial, and an ask bar. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.7 | index.html (pricing) | 3 | Redesign | Pricing -- glassmorphism cards + early-access modal | Built the pricing section with glassmorphism cards and an early-access modal. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.8 | index.html (nav + hero) | 3 | Redesign | New DecisionOS logo in navbar + hero | Added the new DecisionOS logo to the navbar and hero. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.9 | index.html (icp) | 3 | Redesign | ICP / roles -- four-container section w/ hover | Built the four-container ICP / roles section with hover interactions. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-03.10 | index.html (info-arch) | 3 | Redesign | Merge Company Brain into other sections | Removed the standalone Company Brain section and merged its content elsewhere. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.1 | build tooling | 4 | Bug | Heredoc escaping bug garbling checkmark characters | Fixed a heredoc escaping bug in the build script that was garbling checkmark characters in the rendered HTML. | P0 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.2 | index.html (roadmap) | 4 | Bug | Invisible orbit capability pills (white on white) | Fixed invisible orbit capability pills -- white text on white background. | P0 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.3 | index.html (flow) | 4 | Bug | Broken HTML nesting in flow-lane pills | Fixed broken HTML nesting in the flow-lane pills. | P0 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.4 | index.html (problem/scale) | 4 | Bug | Seam line between Problem and Scale sections | Fixed the visible seam line between the Problem and Scale sections. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.5 | index.html (flow) | 4 | Bug | Pill overlap in flow animations shared lane | Fixed pill overlap in the flow animations shared lane. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.6 | index.html (dna) | 4 | Bug | DNA dot-loop animation glitch | Fixed a glitch in the DNA dot-loop animation. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.7 | index.html (dna) | 4 | Bug | DNA endpoint drifting outside its bounding box | Fixed the DNA endpoint drifting outside its bounding box. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.8 | index.html (ceo-brief) | 4 | Bug | Ask bar resizing as text cycled | Fixed the ask bar resizing as its text cycled through examples. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.9 | index.html (parallax) | 4 | Bug | Parallax handler conflict on ghost text | Fixed a parallax handler conflict on the ghost text. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-04.10 | index.html (hero) | 4 | Bug | Hero logo optical alignment against headline | Fixed the hero logos optical alignment against the headline. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.1 | all sections | 5 | Audit | Full UX / UI / product audit + consistency rating | Ran a full UX / UI / product audit and rated consistency across the page. Produced the top-5 fix list executed below. | P0 | L | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.2 | styles.css (radii) | 5 | Consistency | Standardize border-radius to four steps | Standardized the border-radius scale to four steps -- kills the "every card is a different roundness" drift. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.3 | index.html (nav) | 5 | IA | Reorder nav + add Pricing link | Reordered the nav and added a Pricing link. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.4 | js/main.js (motion) | 5 | Performance | Cut motion budget from 148 loops down to 13 | Cut the animation motion budget from 148 running loops down to 13. Frees CPU and stops the fan on lower-spec laptops. | P0 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.5 | copy (two sections) | 5 | Content | Split overloaded copy in two sections | Split overloaded copy in two sections for clarity. | P1 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.6 | assets/img (hero.mp4) | 5 | Build | Hero background video (later reverted) | Added a hero background video. Reverted in Sprint 6 in favour of the static photo (motion pulled attention away from the headline). | P2 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-05.7 | assets/img/* | 5 | Performance | Compress hero + ICP photos by ~97% | Compressed the hero image and ICP photos by roughly 97% -- ~800KB before vs the 40-60KB tiles now. | P0 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.1 | index.html (hero) | 6 | Refinement | Revert hero video to static photo | Reverted the hero video back to the static photo. | P1 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.2 | index.html (dividers) | 6 | Refinement | Rebuild section dividers as matching rounded overlaps | Rebuilt the section dividers as matching rounded-corner overlap transitions. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.3 | index.html (hero) | 6 | Refinement | Pin hero + blur on next-section overlap | Pinned the hero so it blurs as the next section scrolls over it. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.4 | js/main.js (scribble) | 6 | Refinement | Rebuild scribble as one smooth brush loop | Rebuilt the scribble as one smooth brush loop. Later removed entirely. | P2 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.5 | index.html (dna) | 6 | Refinement | Redraw DNA endpoint ring as pencil oval | Redrew the DNA endpoint ring as a hand-drawn pencil oval -- warmer than the geometric ring. | P2 | S | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.6 | js/main.js (scroll) | 6 | Refinement | Shared scroll-inertia driver | Added a shared scroll-inertia driver so all scroll animation eases instead of snapping. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.7 | index.html (how-it-works) | 6 | Bug | Fix unstyled "10 seconds" tail line | Fixed the unstyled "10 seconds" tail line. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.8 | index.html (trust-strip) | 6 | Refinement | Fix trust-strip spacing (above + within) | Fixed the trust-strip spacing above and within the band. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.9 | index.html (hero) | 6 | Refinement | Re-align hero logo (again) | Re-aligned the hero logo again after further review. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.10 | index.html (how-it-works) | 6 | Bug | Fix "10" numeral visually clipped | Fixed the "10" numeral being visually clipped. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.11 | index.html (pricing) | 6 | Refinement | Redesign pricing to match dark / indigo language | Redesigned the pricing section to match the sites dark / indigo language instead of a mismatched rainbow background. | P1 | M | Done |  |  | landing-page/landing-page-build-tracker.md
U9-06.12 | index.html (comparison) | 6 | Refinement | Remove comparison-section scribble entirely | Removed the comparison-section scribble entirely. Cleaner section, no motion overhead. | P2 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-07.1 | landing-page/.git | 7 | Infra | Initialize git repo scoped to landing-page folder | Initialized a git repo scoped to the landing-page folder only, so the site had its own history separate from DecisionOS. | P1 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-07.2 | github.com/quazrelevate-god/DecisionOS-landingpage | 7 | Infra | Commit + push to GitHub | Committed and pushed the site to GitHub as quazrelevate-god/DecisionOS-landingpage. (Later vendored into DecisionOS main repo, Backend_optimization branch, 2026-08-21 -- nested .git removed.) | P1 | XS | Done |  |  | landing-page/landing-page-build-tracker.md
U9-08.1 | index.html (faq) | 8 | Content | FAQ section direction -- awaiting sign-off | FAQ direction -- which questions belong, how many, tone. Awaiting founder sign-off before building. | P1 | M | Backlog |  |  | landing-page/landing-page-build-tracker.md
U9-08.2 | assets/img/logo*, styles.css | 8 | Design | Logo colour vs brand colour mismatch | The logo colour does not match the brand colour used elsewhere on the page. Flagged, unresolved -- needs a design call. | P2 | S | Flagged |  |  | landing-page/landing-page-build-tracker.md
U9-08.3 | deployment | 8 | Infra | GitHub Pages hosting | GitHub Pages hosting for the landing page. Awaiting go-ahead. | P1 | XS | Blocked |  |  | landing-page/landing-page-build-tracker.md
U9-08.4 | deployment | 8 | Infra | Production deployment beyond GitHub Pages | A production deployment beyond GitHub Pages (custom domain / CDN / analytics). Deferred until traffic or SEO warrants it. | P2 | M | Deferred |  |  | landing-page/landing-page-build-tracker.md
U9-09.1 | assets/img/hero-photo-v2.jpg | 9 | Build | V2 hero image swap (sunset with figure) | Swapped the amber-wall guy hero for a sunset-mountain photo with a woman at a desk. Compressed source PNG (1.9MB) to hero-photo-v2.jpg (~240KB). Later superseded by V3 (people-free scene) so the composition would work equally well with the incoming foreground desk plane in front of it. | P1 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.2 | assets/img/hero-bg.jpg | 9 | Build | V3 background image (sunset valley, no figure) | Adopted the layered-source bottom image as the final hero background. Sunset over a mountain valley, no people, so the desk foreground reads as the viewer's own workspace. 323KB after sips-JPEG compression. | P0 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.3 | assets/img/hero-fg.webp | 9 | Build | Foreground desk plane (alpha PNG -> WebP) | Encoded the desk foreground with transparency (WebP 113KB with alpha, PNG 983KB fallback for old browsers). Positioned at z:3 so the desk edge sits in front of the video card, making the mockup feel like it's floating in the sky. | P0 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.4 | index.html, styles.css (planes) | 9 | Structure | Three-plane depth composition | Restructured the hero markup into hero-bg (z:0) + hero-content middle (z:2) + hero-fg (z:3). Cards and copy sit between the sky and the desk. isolation:isolate on .hero contains the stacking context. | P0 | M | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.5 | assets/img/hero-mockup.{webm,mp4} | 9 | Build | Product-tour video card replaces the 6-card grid | Removed the six static metric mockup cards. Replaced with a single curved card (clamp(12px,1.4vw,20px) radius, glass rim, 700px wide, ~1.87:1 aspect) playing the DecisionOS product tour on autoplay muted loop. Video source: Hero 2.mp4 re-encoded to WebM (997KB, VP9) + MP4 (768KB, H.264), audio stripped, 30fps. | P0 | L | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.6 | assets/img/hero-mockup.* | 9 | Build | Video top-crop tuned to reveal mockup nav bar | Iterated the video crop: 12% top crop removed the browser chrome (URL bar) but also hid the DecisionOS product nav bar. Reduced to 5% top crop, which drops the browser Chrome while keeping the mockup's own nav (Decision Desk / My Work / Ops / CRM / ...) visible. | P1 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.7 | index.html (autoplay script) | 9 | Infra | Autoplay hardened for policy-blocked browsers | Chrome's autoplay policy sometimes defers .play() past the initial DOMContentLoaded. Retries on loadedmetadata / loadeddata / canplay / canplaythrough / window.load, plus a 250ms poll for up to 6s. First user interaction (pointerdown) unblocks permanently. | P1 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.8 | styles.css (parallax) | 9 | Motion | Per-layer parallax on scroll (no sticky pin) | Rebuilt the hero scroll model. Hero is position:relative (not sticky). As it scrolls, each layer counter-translates to lag behind the natural scroll at its own rate: bg 70vh (30% apparent speed), fg 0 (100% -- anchor), copy 30vh (70%), video card 32vh (68%), partners 45vh (55%). Layers slide past each other so the composition reads as three-dimensional depth. Uses the existing --hp scroll variable set by main.js Sprint 6. | P0 | M | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.9 | styles.css (parallax) | 9 | Motion | Independent blur curve per layer | Each parallax layer blurs at its own rate as --hp grows: bg 15px, fg 10px, copy 5px, video card 5px, trust band 10px. Softens the recede without pausing the video. prefers-reduced-motion: reduce disables both parallax and blur. | P1 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.10 | styles.css (nav) | 9 | IA | Nav bar always visible on hero (was hidden until scroll) | Removed the "swipe in from top when scrolled 55% of hero height" behaviour on .site-header. The nav is now visible from page load so the DecisionOS logo and links sit in the top-left the whole time, matching the reference mockup. | P1 | XS | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.11 | index.html, styles.css (trust band) | 9 | Content | Trust band as contained right-to-left marquee | Lifted the "Trusted by founder-led businesses" strip from the hero bottom (where the desk foreground was hiding it) into a mid-hero band. 780px wide, centred, positioned with balanced headroom above and below the video card. Brand list duplicated twice for a seamless 28s right-to-left loop with fade-edge mask-image on both sides. | P0 | M | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.12 | index.html (dex bubble) | 9 | Cleanup | Remove Dex bubble from hero | The Dex-today's-read floating callout was compact-styled once and then removed entirely -- the video card itself carries the "here's the product" moment. | P2 | XS | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.13 | index.html (scroll cue) | 9 | Cleanup | Remove scroll cue anchor | The scroll indicator at the bottom of the hero was removed. The composition already has enough motion to signal there's more below. | P2 | XS | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.14 | index.html (video card) | 9 | Bug | Fix: video card wasn't parallaxing (reveal class override) | .hero-video-card had class="reveal" whose fade-in animation runs with fill-mode:forwards, ending at transform:none. That fill-mode-held value silently overrode the per-layer parallax translate3d on the same element -- so it was the only middle-plane element not visibly moving on scroll. Dropped the reveal class from the video card (hero-copy and hero-partners carry reveal only on their children, so their parallax kept working). | P0 | S | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md
U9-09.15 | styles.css (trust band transform) | 9 | Bug | Fix: trust band centering + parallax translate3d fought each other | .hero-partners had two transform declarations -- translateX(-50%) for centering, and translate3d(...) for parallax. Second overrode the first, leaving the band 390px off-centre. Merged into a single transform: translate(-50%, calc(var(--hp)*45vh)) so it centres AND parallaxes. | P0 | XS | Done |  |  | commit 15b51cc (hero v10) + landing-page/landing-page-build-tracker.md