## Cover
DecisionOS
Epic 10 -- Admin / Platform Console
Kickoff | 2026-08-23. The platform super-admin console already ships; this epic hardens + extends it. Builds on the Epic 8 modular backend (routers/admin.py + integrations/).
Origin | Founder ask 2026-08-23: 'there is a separate admin section where we can check all the tenants, logs, support, etc. -- create this as a new epic; check what we already cover.'
Epic 10 goal | Grow the shipped platform super-admin console into a full operations + SUPPORT console: tenant 360, secure impersonation, a support desk, billing/subscriptions administration, and deep observability -- so the team can run, support, and bill the SaaS from one place.
Current state (already shipped) | A platform super-admin app is in production: separate /admin login + dos_admin_token cookie (sits ABOVE all tenants, 5-attempt lockout, immutable platform_audit log). 24 API routes (routers/admin.py) + an 8-tab portal (Overview, Usage, AI Keys, Workspaces, Users, Maintenance, Audit Log, Health -- pages/admin/, 947 lines). Captured as Sprint 0 (Done) in the Backlog.
Working principles | 1. Extend, don't rebuild -- the shipped console is the foundation; each sprint adds to it. 2. Super-admin sits ABOVE tenants: separate auth, its own audit trail, least-privilege. 3. Every privileged action (impersonate, suspend, refund, flag-flip, key rotate) is audited immutably. 4. Support tooling must be SAFE: time-boxed, consented, read-first impersonation. 5. Zero tenant-facing behavior change from admin work.
Note on backlog | This tracker records what already ships (Sprint 0 = Done) and lays out the forward sprint plan at SCOPE level. Task-level backlog rows are filled in per sprint as each is picked up (same convention as Epic 8).
Sprint breakdown
Sprint 0 -- Current state (SHIPPED / COMPLETE)
Scope | The platform super-admin console already in production. Auth: separate /admin login (dos_admin_token, 5-attempt lockout, immutable platform_audit). Portal (8 tabs): Overview + platform metrics + provider alerts; Usage (AI credit by range+provider); AI Keys (get/put + live status probes for Anthropic/OpenAI/Gemini/WhatsApp/Sarvam); Workspaces (list/suspend/reactivate/delete+file-cleanup); Users (list/suspend/reactivate/reset-access); Audit log; Health; Maintenance (migrations/scheduler-locks/reclassify-purchases). 24 routes + 8 UI sections.
Why | This is the baseline the epic builds on -- enumerated as Done rows so 'what we already cover' is explicit.
Sprint 1 -- Tenant 360 & cross-tenant search
Scope | A deep per-workspace view: its users, plan+usage, config (operating model / lexicon / roles), recent activity, health signals and logs on ONE screen. Plus global search across tenants/users/contacts and a tenant activity timeline.
Why | Today admin lists tenants and users separately; supporting a customer means stitching that together by hand. One 360 view is where every support/ops task starts.
Sprint 2 -- Support impersonation ("view as tenant")
Scope | Secure, time-boxed, fully-audited impersonation: a super-admin opens a support session INTO a tenant (read-only by default; read-write only with an explicit reason), with a persistent support-session banner, auto-expiry, and a complete audit trail. Owner consent model.
Why | The #1 support capability -- reproduce a customer's exact screen to debug -- without it, support is guesswork over screenshots.
Sprint 3 -- Support desk & tickets
Scope | A ticket inbox: create / triage / assign / resolve tickets, each linked to its tenant (+ one-click jump to impersonation), status + SLA timers, canned responses, and an inbound channel (in-app 'Contact support' + email intake).
Why | 'Supporting' needs a system of record for customer issues -- tied to the tenant and the audit log, not scattered across chats.
Sprint 4 -- Billing & subscriptions admin
Scope | MRR / revenue dashboard, per-tenant plan + manual override, Razorpay reconciliation (webhook + payment history), trial & dunning state, and credits / refunds -- on the India-primary Razorpay stack.
Why | Usage telemetry exists but there's nowhere to see revenue, fix a mis-charged tenant, extend a trial, or reconcile a Razorpay webhook.
Sprint 5 -- Observability & logs
Scope | A structured request / error-log viewer, provider-outage history + timeline (beyond the current point-in-time alerts), rate-limit / abuse monitoring, and scheduler / worker run status.
Why | When something breaks for a tenant, admin needs the logs + provider timeline in-console, not an SSH session.
Sprint 6 -- Feature flags & config
Scope | A UI over per-tenant + global feature flags (tenant.feature_flags already exists in the schema), plan-gated capabilities, staged rollout, and kill-switches for risky features.
Why | Ship features to a subset, gate by plan, and disable a misbehaving feature without a deploy.
Sprint 7 -- Admin RBAC & security
Scope | Multiple admin roles (super-admin / support / billing / read-only) with scoped permissions, admin 2FA, optional IP allowlist, and admin session management / revocation.
Why | A support agent shouldn't be able to delete a tenant or rotate provider keys. Least-privilege for the console itself.
Sprint 8 -- Announcements & comms
Scope | In-app broadcast + maintenance banners to tenants, targeted email to workspace owners, and a changelog / release-notes surface.
Why | One place to tell customers about maintenance, incidents, and new features.
Sprint 9 -- Compliance & data ops (DPDP / GDPR)
Scope | Per-tenant data export, retention policy + purge scheduling, consent / audit exports, and a structured deletion workflow (hard-delete exists; add export-before-delete + retention).
Why | DPDP/GDPR require export + retention + a documented deletion path, not just a delete button.
Sprint 10 -- Admin polish, tests & QA
Scope | UX consistency + responsive / mobile admin, automated tests for every admin endpoint + the RBAC matrix, and an admin API-parity gate.
Why | The console is now business-critical -- it needs the same test rigor as the tenant app.

## Dashboard
DecisionOS - Epic 10 - Admin / Platform Console
Grow the shipped platform super-admin console into a full ops + support console: tenant 360, secure impersonation, support desk, billing/subscriptions, and observability. Kickoff: 2026-08-23.
Epic 10 STARTED. Sprint 0 (current state) COMPLETE (10/10): the platform super-admin console already ships -- 24 API routes + an 8-tab portal (Overview/Usage/AI-Keys/Workspaces/Users/Maintenance/Audit/Health), separate /admin auth + immutable platform_audit. Forward sprints S1-S10 planned (scope-level): tenant 360, impersonation, support desk, billing, observability, flags, admin RBAC, comms, DPDP, QA.
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 0 | Current state (shipped) | 10 | 10 | 100% | COMPLETE | Already in production: separate /admin auth + dos_admin_token + platform_audit; 8-tab portal (Overview/metrics/alerts, Usage, AI Keys+probes, Workspaces CRUD, Users lifecycle, Maintenance, Audit, Health). 24 routes.
Sprint 1 | Tenant 360 & cross-tenant search | 7 | 7 | 100% | COMPLETE | One per-workspace view (users+plan+usage+config+activity+health+logs) + global search across tenants/users/contacts + tenant timeline.
Sprint 2 | Support impersonation (view as tenant) | 6 | 6 | 100% | COMPLETE | Secure, time-boxed, audited read-first impersonation with a support-session banner, auto-expiry + consent. The core support capability.
Sprint 3 | Support desk & tickets | 0 | 7 | 0% | Planned | Ticket inbox tied to tenants (+ jump to impersonation): create/triage/assign/resolve, SLA timers, canned responses, in-app + email intake.
Sprint 4 | Billing & subscriptions admin | 0 | 7 | 0% | Planned | MRR/revenue dashboard, per-tenant plan + override, Razorpay reconciliation (webhook/payment history), trials & dunning, credits/refunds.
Sprint 5 | Observability & logs | 0 | 6 | 0% | Planned | Request/error-log viewer, provider-outage history + timeline, rate-limit/abuse monitoring, scheduler/worker run status.
Sprint 6 | Feature flags & config | 0 | 7 | 0% | Planned | UI over per-tenant + global feature flags, plan-gated capabilities, staged rollout, kill-switches.
Sprint 7 | Admin RBAC & security | 0 | 6 | 0% | Planned | Admin roles (super-admin/support/billing/read-only), admin 2FA, IP allowlist, admin session management/revocation.
Sprint 8 | Announcements & comms | 0 | 5 | 0% | Planned | In-app broadcast + maintenance banners, targeted email to owners, changelog/release-notes surface.
Sprint 9 | Compliance & data ops (DPDP/GDPR) | 0 | 6 | 0% | Planned | Per-tenant data export, retention + purge, consent/audit exports, structured deletion workflow (export-before-delete).
Sprint 10 | Admin polish, tests & QA | 0 | 6 | 0% | Planned | Responsive/mobile admin, automated tests for every admin endpoint + RBAC matrix, admin API-parity gate.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
U10-00.1 | routers/admin.py | 0 | Auth | Platform super-admin auth | Separate /admin login + logout + me on a dos_admin_token cookie (distinct from tenant auth), 5-attempt lockout, get_platform_admin dependency, and an immutable platform_audit action log. | P0 | M | Done |  | Ships. login/logout/me + log_admin_action. | Epic 10 S0 (audit)
U10-00.2 | AdminPortal / Overview | 0 | Overview | Platform metrics + provider alerts | Overview tab: platform-wide counts (tenants, users, decisions, tasks, captures, workflows, contacts, tasks_done) + provider-outage alerts. | P1 | S | Done |  | GET /admin/metrics + /admin/alerts; OverviewSection. | Epic 10 S0 (audit)
U10-00.3 | AdminPortal / Usage | 0 | Usage | AI credit usage by workspace | Usage tab: AI credit consumption filterable by range (today/7d/30d/all) and provider (Sarvam/Claude/Emergent/OpenAI/Gemini), per workspace. | P1 | M | Done |  | GET /admin/usage; UsageSection. | Epic 10 S0 (audit)
U10-00.4 | AdminPortal / AI Keys | 0 | Providers | AI provider keys + live probes | AI Keys tab: view (masked) + set platform provider keys, and a 'Test All Keys' live status probe for Anthropic, OpenAI, Gemini, WhatsApp and Sarvam. | P1 | M | Done |  | GET/PUT /admin/ai-keys + /admin/ai-keys/status (5 probes); AiKeysSection. | Epic 10 S0 (audit)
U10-00.5 | AdminPortal / Workspaces | 0 | Tenants | Workspace administration | Workspaces tab: list all tenants, suspend, reactivate, and delete a tenant (with obj_store file cleanup for DPDP compliance). | P1 | M | Done |  | GET /admin/tenants + suspend/reactivate/DELETE; TenantsSection. | Epic 10 S0 (audit)
U10-00.6 | AdminPortal / Users | 0 | Users | User lifecycle administration | Users tab: list users (optionally by tenant), suspend, reactivate, and reset-access for a user across the platform. | P1 | M | Done |  | GET /admin/users + suspend/reactivate/reset-access; UsersSection. | Epic 10 S0 (audit)
U10-00.7 | AdminPortal / Audit Log | 0 | Audit | Platform audit log | Audit Log tab: the immutable platform_audit trail of every super-admin action (who/what/target/when). | P1 | S | Done |  | GET /admin/audit; AuditSection. | Epic 10 S0 (audit)
U10-00.8 | AdminPortal / Health | 0 | Ops | Platform health | Health tab: platform health signals (DB, providers, service). | P2 | S | Done |  | GET /admin/health; HealthSection. | Epic 10 S0 (audit)
U10-00.9 | AdminPortal / Maintenance | 0 | Ops | Maintenance jobs | Maintenance tab: migration ledger, scheduler leader-locks, and the reclassify-purchases backfill job (+status). | P2 | M | Done |  | GET /admin/migrations + /admin/scheduler-locks + POST /admin/reclassify-purchases(+status); MaintenanceSection. | Epic 10 S0 (audit)
U10-00.10 | pages/admin/ | 0 | Frontend | Admin portal shell (8 tabs) | The admin SPA: AdminLogin + AdminPortal shell with 8 nav tabs wiring the sections above (Overview/Usage/AI Keys/Workspaces/Users/Maintenance/Audit/Health). Warm dark admin theme. | P1 | M | Done |  | pages/admin/{AdminLogin,AdminPortal,AdminSections}.js (947 lines); routes /admin + /admin/*. | Epic 10 S0 (audit)
U10-06.1 | Admin console + AI model routing | 6 | Config | Admin model switcher -- change model-per-task at runtime | Runtime, DB-backed override of MODEL_ROUTES per AI task from the super-admin console (no redeploy). model_for() reads an override layer first: env -> DB override -> MODEL_ROUTES -> default. Admin picks the model per task from the MODELS catalog; the change is audited. Pairs with the AI quality dashboard (E3-10.2) so the effect of a switch is visible. | P2 | M | Backlog | E3-01.2 | Added 2026-08-25. Deferred from the Epic 3 model-routing discussion to Epic 10 per founder. TODAY models change only via config.py MODELS + MODEL_ROUTE_<TASK> env override (needs a redeploy). Sibling to U10-00.4 AI provider keys. | Epic 10 S6
U10-06.2 | Admin console + STT/TTS config | 6 | Config | Sarvam STT + TTS model/mode/voice admin config | Runtime, DB-backed admin config for the Sarvam voice stack (no redeploy): STT model (saaras:v3 / v4), STT mode (transcribe / translate / codemix -- codemix best for Tanglish), and Bulbul TTS voice model + speaker. Read by the integrations/stt.py + TTS layer, override order env -> DB -> default. Sibling to U10-06.1 (LLM model switcher) and U10-00.4 (AI provider keys). | P2 | M | Backlog | E3-07.1 | Added 2026-08-25 per founder: STT is Sarvam-only; make Sarvam model/mode + Bulbul voice admin-configurable here rather than in Epic 3. Today SARVAM_STT_MODEL + mode are env/hardcoded (saaras:v3, mode=translate). | Epic 10 S6
U10-01.1 | Admin / Tenant 360 | 1 | Feature | Cross-tenant search | GET /api/admin/search?q= -- find a workspace (name/id) or user (name/email/phone/id) across all tenants; returns tenants + users with workspace names attached. Gated by get_platform_admin, read-only. | P1 | M | Done |  | routers/admin_tenant360.py | Epic 10 S1
U10-01.2 | Admin / Tenant 360 | 1 | Feature | Tenant 360 aggregate endpoint | GET /api/admin/tenants/{id}/360 -- one consolidated per-workspace payload: plan+entitlements, entity counts (users/decisions/tasks/workflows/contacts/invoices/complaints), members, AI spend (30d+all-time), recent activity, health. Parallel queries via asyncio.gather. | P1 | M | Done | U10-01.1 | routers/admin_tenant360.py | Epic 10 S1
U10-01.3 | Admin / Tenant 360 | 1 | Feature | Per-tenant members + roles | Members list (name/email/role/suspended/created) + active-membership count in the 360 payload. | P1 | S | Done | U10-01.2 | part of 360 | Epic 10 S1
U10-01.4 | Admin / Tenant 360 | 1 | Feature | Per-tenant AI spend | AI spend rollup (calls/tokens/cost) for last-30d and all-time from usage_events, in the 360 payload. | P1 | S | Done | U10-01.2 | part of 360 | Epic 10 S1
U10-01.5 | Admin / Tenant 360 | 1 | Feature | Per-tenant config + entitlements view | Plan, seat limit(+override), feature_flags, usage_quotas, AI consent, GST, industry/region/currency surfaced in the 360. | P1 | S | Done | U10-01.2 | part of 360 | Epic 10 S1
U10-01.6 | Admin / Tenant 360 | 1 | Feature | Activity timeline + health signals | Recent db.activity timeline (20) + health (last_activity, suspended, ai_consent) in the 360. | P1 | S | Done | U10-01.2 | part of 360 | Epic 10 S1
U10-01.7 | Admin portal | 1 | Frontend | Tenant 360 tab (search + drill-in) | New AdminPortal tab: search box -> workspace/user results -> click to open the consolidated 360 view (counts grid, spend, entitlements, health, members, activity). Self-contained Tenant360Section.js matching the admin dark theme. | P1 | M | Done | U10-01.2 | frontend/src/pages/admin/Tenant360Section.js | Epic 10 S1
U10-02.1 | Admin / Impersonation | 2 | Security | Impersonation token + session model | create_impersonation_token (core/security): a short-lived target-user JWT with an `imp` claim {admin, session_id, read_only}, exp<=240m, bound to an impersonation_sessions record {admin_email, tenant, target, read_only, reason, granted/expires, revoked}. | P1 | M | Done |  | core/security.py | Epic 10 S2
U10-02.2 | core/deps | 2 | Security | get_current_user impersonation recognition | get_current_user detects the `imp` claim, verifies the impersonation_sessions record is live (not revoked / not expired) -- session-based revocation replaces the jti check -- and loads the target user with membership projection. | P1 | M | Done | U10-02.1 | core/deps.py | Epic 10 S2
U10-02.3 | core/deps | 2 | Security | Read-first enforcement | When the session is read_only, any mutating request (non GET/HEAD/OPTIONS) is blocked with 403 'writes are blocked'. Verified end-to-end: GET reads as tenant, POST -> 403, revoke -> 401. | P1 | S | Done | U10-02.2 | core/deps.py | Epic 10 S2
U10-02.4 | Admin / Impersonation | 2 | Feature | Grant / list / revoke endpoints + audit | POST /admin/tenants/{id}/impersonate (reason/target/minutes/read_only) -> session+token; GET /admin/impersonation -> sessions with live/expired/revoked status; POST /admin/impersonation/{id}/revoke. Every grant+revoke written to platform_audit. | P1 | M | Done | U10-02.1 | routers/admin_impersonation.py | Epic 10 S2
U10-02.5 | Admin / Impersonation | 2 | Feature | Impersonation flags for banner + audit | get_current_user stamps _impersonated_by / _read_only / _impersonation_session on the user (survives project_membership_onto_user), so /me exposes them for an in-app banner and downstream audit. | P1 | S | Done | U10-02.2 | core/deps.py + /me | Epic 10 S2
U10-02.6 | Admin portal | 2 | Frontend | Impersonation tab + 'View as tenant' | New Impersonation admin tab (sessions list with status + End/revoke). 'View as tenant' button in Tenant 360 starts a 30m read-only session (audited, prompts for reason). Seamless browse-as-tenant + in-app banner noted as a follow-on UX refinement. | P1 | M | Done | U10-02.4 | frontend/src/pages/admin/ImpersonationSection.js | Epic 10 S2