## Dashboard
DecisionOS - Epic 3 - Dashboard
Dex AI Persona + Product decisions parked from Epic 2 ¦ Kickoff: pending Epic 2 push ¦ Rollup live from Backlog
Epic 3 progress: 0 of 13 items Done (0%)
Sprint | Sprint / Epic name | Done | Total | % | Status | Theme
Sprint 1 | Dex Ask persona-integration chips | 0 | 5 | 0% | Backlog | Every context-carrying 'Ask Dex' chip that survives Epic 2's 'AI part moves to Epic 3' rule. Chips carry surface-specific context (Ledger AI insight, ContactProfile, WorkCoach improvement, Task Execution Plan) into Dex Ask with a prompt tuned to that context type.
Sprint 2 | Dex narrative + Important chip | 0 | 2 | 0% | Backlog | Two AI product decisions bundled: (a) upgrade Desk Dex narrative from template to LLM-generated with 15-min cache; (b) decide whether the Important chip stays as a 4th Desk chip, moves to Dex, or dies. Both need prompt design + cost budget + fail-open thresholds reasoned about together.
Sprint 3 | Role-based navigation model | 0 | 1 | 0% | Backlog | Decide the role/persona nav question. What is the DEFAULT landing tab for Sales vs Production vs Finance vs Owner? Should nav reorder-per-role or hide-per-role? Ships as either tenant-level config (owner picks) or system defaults.
Sprint 4 | Dex knowledge + retrieval | 0 | 5 | 0% | Backlog | Ingest-time embeddings, RAG, agent loop, agent memory, auto-assign

## Moving to Next Epic
Moving to Next Epic - parked items
Items scoped in Epic 3 but deferred to Epic 4 (or superseded). Not counted against Epic 3 progress. Empty at kickoff.
ID | Origin sprint | Title | Status | Why parked / what we need to decide | Decision needed from founder

## Cover
DecisionOS - Epic 3
Dex AI Persona + Product decisions
Kickoff | 2026-08-15 (Epic 2 close-out)
Predecessor | Epic 2 (DecisionOS_Epic2_UX_Redesign.xlsx) - 64 items shipped, 8 parked here, 1 dropped
Style | Same tracker structure as Epic 2: Dashboard first, then 'Moving to Next Epic' parking lot, then Cover, Backlog, Page Redesign Log. Same ID convention (E3-XX), Sprint column, Status (Backlog ¦ In Progress ¦ Done ¦ Parked - next epic ¦ Dropped).
Epic 3 goal
Complete the Dex AI persona arc that Epic 2 deferred, and resolve two role/persona product decisions that need founder ideation before code (Important chip fate + role-based nav model). Every item here either (a) requires new prompt work Epic 2 explicitly deferred, or (b) needs a founder-side product decision before implementation.
Working principles | 1. Every prompt gets a written system-prompt spec + cost budget BEFORE code. No 'cheap LLM call, see what happens'. 2. Every AI feature has a fail-open path -- if the LLM errors or times out, the UI still renders something sensible (template fallback, empty state, or hide). 3. Product decisions get their own docs (or a shared one) with the options laid out BEFORE we build. Kill features whose 'do we need this' question can't get a clear yes. 4. Same tracker discipline as Epic 2 -- side-by-side sheet updates per push, Dashboard reflects reality, 'Moving to Next Epic' is the discipline for anything that needs more thought.
Sprint breakdown
Sprint 1 -- Dex Ask persona-integration chips
Status | Backlog (kickoff pending)
Items | E3-01, E3-02, E3-03, E3-04, E3-05
Why | Every context-carrying 'Ask Dex' chip that survives Epic 2's 'AI part moves to Epic 3' rule. Chips carry surface-specific context (Ledger AI insight, ContactProfile, WorkCoach improvement, Task Execution Plan) into Dex Ask with a prompt tuned to that context type.
Sprint 2 -- Dex narrative + Important chip
Status | Backlog (kickoff pending)
Items | E3-06, E3-07
Why | Two AI product decisions bundled: (a) upgrade Desk Dex narrative from template to LLM-generated with 15-min cache; (b) decide whether the Important chip stays as a 4th Desk chip, moves to Dex, or dies. Both need prompt design + cost budget + fail-open thresholds reasoned about together.
Sprint 3 -- Role-based navigation model
Status | Backlog (kickoff pending)
Items | E3-08
Why | Decide the role/persona nav question. What is the DEFAULT landing tab for Sales vs Production vs Finance vs Owner? Should nav reorder-per-role or hide-per-role? Ships as either tenant-level config (owner picks) or system defaults.
Sprint 4 -- Dex knowledge + retrieval
Status | Backlog (imported from Stability tracker 2026-08-15)
Items | E3-09, E3-10, E3-11, E3-12, E3-13
Why | Sprint 4 -- Dex knowledge + retrieval (5 items imported from Epic 1 Stability tracker on 2026-08-15). Ingest-time document extraction + chunk + embed, vector search + hybrid retrieval, bounded planner-executor loop with native function-calling, per-conversation agent memory, auto-assign AI-generated tasks. Sits alongside the persona work in Sprint 1-3 -- this sprint is the 'how does Dex actually know things' layer.
Sprint 4 -- Dex knowledge + retrieval
Status | Backlog (imported from Stability tracker 2026-08-15)
Items | E3-09, E3-10, E3-11, E3-12, E3-13
Why | Sprint 4 -- Dex knowledge + retrieval (5 items imported from Epic 1 Stability tracker on 2026-08-15). Ingest-time document extraction + chunk + embed, vector search + hybrid retrieval, bounded planner-executor loop with native function-calling, per-conversation agent memory, auto-assign AI-generated tasks. Sits alongside the persona work in Sprint 1-3 -- this sprint is the 'how does Dex actually know things' layer.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends on | Notes / evidence | Source
E3-01 |  | 1 | Persona integration | 'Ask Dex about this' chip on every Ledger AI insight | Each Ledger AI panel (overview/revenue/expenses/assets/inventory) currently answers within its own scope. Add a chip next to each AI insight that carries the context ('this insight from the expenses AI') into Dex and lets the founder keep the conversation going there. Chip href = /dex?context=<serialised>. Dex Ask panel reads the context param + prefills the input. Prompt work required: Dex Ask system prompt needs to honour the ?context= as a first-turn setup ('The user is looking at this insight from Ledger:{ctx}. Answer their follow-up in that scope') rather than treating it as a plain user turn. | P2 | M | Backlog |  | Imported from Epic 2 E2-36 (parked) | Epic 2 close-out 2026-08-15
E3-02 |  | 1 | Persona integration | 'Ask Dex about this relationship' chip on ContactProfile | The 360-degree ContactProfile page already shows AI Relationship Intelligence scoring. Add an 'Ask Dex about this relationship' chip in the header that opens Dex with the contact name + type + last-3-touches as context. Founders can ask 'why did Kapoor Retail's payment slow down?' without re-typing the whole context. Prompt work required: Dex Ask needs to handle relationship-type context (contact + recent activity + current outstanding) and answer questions grounded in that snapshot. | P2 | M | Backlog |  | Imported from Epic 2 E2-37 (parked) | Epic 2 close-out 2026-08-15
E3-03 |  | 1 | Persona integration | 'Ask Dex to coach me on X' chip on WorkCoach | WorkCoach shows AI-generated headline + strengths + improvements. Add an 'Ask Dex to coach me on X' chip per improvement item that opens Dex with the specific improvement text preloaded so the founder can drill into how to act on it. Prompt work required: Dex Ask needs a coaching-mode prompt that expands a WorkCoach improvement item into actionable next-steps rather than answering it generically. | P3 | S | Backlog |  | Imported from Epic 2 E2-38 (parked) | Epic 2 close-out 2026-08-15
E3-04 |  | 1 | Persona integration | 'Ask Dex to re-plan this' chip on Task Execution Plan | Task cards with AI Execution Plans already have a per-step 'Ask AI' button. Rename that button to 'Ask Dex' + carry the full plan context. Also add a card-level 'Ask Dex to re-plan this task' chip so founders can ask for a regeneration with a specific constraint (e.g. 'faster', 'safer', 'more junior-friendly'). Prompt work required: re-plan mode -- takes existing plan JSON + user constraint, emits a valid execution plan structure honouring the constraint. | P3 | S | Backlog |  | Imported from Epic 2 E2-39 (parked) | Epic 2 close-out 2026-08-15
E3-05 |  | 1 | Milestone | Sprint 1 exit gate -- full E2E of Dex persona chips | Ship after E3-01..04 land. Test flow: (a) sidebar + bottom-nav both show 'Dex', (b) /dex renders capture bar + Ask/Search/Documents, (c) 'Ask Dex' chips from Ledger + ContactProfile + WorkCoach + MyWork all deep-link into Dex with context, (d) each context type produces a scoped, useful answer, (e) responses show the Dex persona prefix (already shipped via E2-40), (f) admin usage shows a 'dex' provider tally. | P2 | S | Backlog |  | Imported from Epic 2 E2-42 (parked) | Epic 2 close-out 2026-08-15
E3-06 |  | 2 | AI upgrade | Upgrade Dex narrative on Desk to LLM-generated with 15-min cache | Replace the template narrative in routers/desk.py::_narrative with an LLM call to Dex. Input: the same counters computed today (delayed, completed_yday, cash_flow, complaints). Output: richer, tone-aware, situation-specific prose. Cache per-tenant per-15-minutes to keep LLM cost bounded. Fail-open: if the LLM call errors, fall back to the template so the header always renders. Design decisions before shipping: 1. Dex system prompt (voice + safety + do-not-hallucinate rules). 2. Cache key strategy (tenant+user+hour? or tenant+15-min bucket?). 3. Fail-open threshold (LLM latency > N ms -> fall back to template). 4. Cost budget per tenant per day (upper bound on cache misses). | P2 | M | Backlog |  | Imported from Epic 2 E2-48 (parked) | Epic 2 close-out 2026-08-15
E3-07 |  | 2 | Product decision + AI | Decide + implement (or kill) the 'Important' chip on Decision Desk | The 'Important' chip on Decision Desk shows 0 today because the ranker is fail-open. Three-way decision: a) KILL -- Desk goes from 4 chips to 3 (Needs Decision, On Fire, Due Today). Cleaner. b) MOVE TO DEX -- surface 'important but not urgent' as a Dex prompt/panel rather than a Desk chip. c) KEEP + BUILD -- implement the AI ranker in services/ai/priorities.py. Signals: high monetary amount, strategic keyword match, brain_context pattern of prior founder-approved decisions, days quiet without action. Cached 15 min per tenant per user. Founder decides before we code. | P2 | M | Backlog |  | Imported from Epic 2 E2-21 (parked) | Epic 2 close-out 2026-08-15
E3-08 |  | 3 | Navigation / product decision | Bottom-nav ownership audit -- which tab per role? | Ideation ticket. Today all users see the same 4 slots (subject to perm gates). Founder-vs-teammate flows are different: teammates almost never open BRIEF, founders rarely open MyWork task cards. Founder to decide: 1. Reordering per role (softer) OR hiding per role (clearer but confuses cross-role handoffs)? 2. DEFAULT landing tab for Sales / Production / Finance / Owner on login? (Today all land on /inbox.) 3. Ships as tenant-level config (owner picks per role) or as system defaults? Might land as 'primary tab per role' config, or as simple reordering, or as a fresh default-landing rule. | P3 | S | Backlog |  | Imported from Epic 2 E2-12 (parked) | Epic 2 close-out 2026-08-15
E3-09 |  | 4 | AI/Brain | Extract + chunk + embed documents at ingest | Uploaded documents are stored as metadata only; body text is never read at ingest. Add server-side extraction + chunking + embeddings into a new brain_chunks collection. | P1 | L | Backlog |  | Imported from Stability tracker S4-05. Origin sprint: Sprint 4. File ref: routers/brain_docs.py:147-213 | Stability tracker split 2026-08-15
E3-10 |  | 4 | AI/Brain | Adopt vector search + hybrid retrieval | Move from keyword-only BM25/regex to embeddings (Atlas Vector Search if on Atlas, else Qdrant/pgvector) fused with existing text search. | P1 | L | Backlog |  | Imported from Stability tracker S4-06. Origin sprint: Sprint 4. File ref: (new infra) | Stability tracker split 2026-08-15
E3-11 |  | 4 | AI/Brain | Add bounded planner-executor loop + native function-calling | /brain/agent is single-turn (plan -> fan-out -> synthesize, no re-plan). Add an observe-then-replan loop and migrate to Anthropic tools=[...]. | P2 | L | Backlog |  | Imported from Stability tracker S4-08. Origin sprint: Sprint 4. File ref: routers/brain_router.py:266-277,481-482 | Stability tracker split 2026-08-15
E3-12 |  | 4 | AI/Brain | Add per-conversation agent memory | Every LLM call gets a fresh random session_id; planner and synthesizer don't even share context. | P2 | M | Backlog |  | Imported from Stability tracker S4-09. Origin sprint: Sprint 4. File ref: routers/brain_router.py:95,353 | Stability tracker split 2026-08-15
E3-13 |  | 4 | AI / Task routing | Auto-assign AI-generated tasks when one user matches the role | AI sets assignee_role but leaves assignee_id null. For tenants with 1 person per role, auto-assign deterministically. For 2+ show a 'pick a person' chip. For 0 fall back to owner + notify. | P2 | M | Backlog |  | Imported from Stability tracker FUP-47. Origin sprint: Follow-up. File ref: | Stability tracker split 2026-08-15

## Page Redesign Log
Date | Ticket | Page | What changed | Before | After | Screenshot | Commit
2026-08-15 | Epic 3 kickoff | (no code -- planning) | Epic 3 tracker created from Epic 2 close-out. 8 items imported from the Epic 2 'Moving to Next Epic' parking lot: 5 Dex Ask persona chips + exit gate (Sprint 1), Dex narrative LLM + Important chip decision (Sprint 2), role-based nav model (Sprint 3). Each carries the origin ticket ID from Epic 2 in the Notes column for audit trail. | Epic 2 closed at 73/73 resolved with 8 items parked awaiting prompt work or product decisions -- no Epic 3 file existed yet. | Fresh Epic 3 workbook. Same structure as Epic 2 for continuity. Backlog ready for founder to prioritise / re-scope. | N/A (planning) | (next commit)