## Cover
DecisionOS
Epic 9 -- Admin / Platform Console
Kickoff | 2026-08-23. The platform super-admin console already ships; this epic hardens + extends it. Builds on the Epic 7 modular backend (routers/admin.py + integrations/).
Origin | Founder ask 2026-08-23: 'there is a separate admin section where we can check all the tenants, logs, support, etc. -- create this as a new epic; check what we already cover.'
Epic 9 goal | Grow the shipped platform super-admin console into a full operations + SUPPORT console: tenant 360, secure impersonation, a support desk, billing/subscriptions administration, and deep observability -- so the team can run, support, and bill the SaaS from one place.
Current state (already shipped) | A platform super-admin app is in production: separate /admin login + dos_admin_token cookie (sits ABOVE all tenants, 5-attempt lockout, immutable platform_audit log). 24 API routes (routers/admin.py) + an 8-tab portal (Overview, Usage, AI Keys, Workspaces, Users, Maintenance, Audit Log, Health -- pages/admin/, 947 lines). Captured as Sprint 0 (Done) in the Backlog.
Working principles | 1. Extend, don't rebuild -- the shipped console is the foundation; each sprint adds to it. 2. Super-admin sits ABOVE tenants: separate auth, its own audit trail, least-privilege. 3. Every privileged action (impersonate, suspend, refund, flag-flip, key rotate) is audited immutably. 4. Support tooling must be SAFE: time-boxed, consented, read-first impersonation. 5. Zero tenant-facing behavior change from admin work.
Note on backlog | This tracker records what already ships (Sprint 0 = Done) and lays out the forward sprint plan at SCOPE level. Task-level backlog rows are filled in per sprint as each is picked up (same convention as Epic 7).
Sprint breakdown
Sprint 0 -- Current state (SHIPPED / COMPLETE)
Scope | The platform super-admin console already in production. Auth: separate /admin login (dos_admin_token, 5-attempt lockout, immutable platform_audit). Portal (8 tabs): Overview + platform metrics + provider alerts; Usage (AI credit by range+provider); AI Keys (get/put + live status probes for Anthropic/OpenAI/Gemini/WhatsApp/Sarvam); Workspaces (list/suspend/reactivate/delete+file-cleanup); Users (list/suspend/reactivate/reset-access); Audit log; Health; Maintenance (migrations/scheduler-locks/reclassify-purchases). 24 routes + 8 UI sections.
Why | This is the baseline the epic builds on -- enumerated as Done rows so 'what we already cover' is explicit.
Sprint 1 -- Tenant 360 & cross-tenant search
Scope | A deep per-workspace view: its users, plan+usage, config (operating model / lexicon / roles), recent activity, health signals and logs on ONE screen. Plus global search across tenants/users/contacts and a tenant activity timeline.
Why | Today admin lists tenants and users separately; supporting a customer means stitching that together by hand. One 360 view is where every support/ops task starts.
Sprint 2 -- Support impersonation ("view as tenant")
Scope | Secure, time-boxed, fully-audited impersonation: a super-admin opens a support session INTO a tenant (read-only by default; read-write only with an explicit reason), with a persistent support-session banner, auto-expiry, and a complete audit trail. Owner consent model.
Why | The #1 support capability -- reproduce a customer's exact screen to debug -- without it, support is guesswork over screenshots.
Sprint 3 -- Support desk & tickets
Scope | A ticket inbox: create / triage / assign / resolve tickets, each linked to its tenant (+ one-click jump to impersonation), status + SLA timers, canned responses, and an inbound channel (in-app 'Contact support' + email intake).
Why | 'Supporting' needs a system of record for customer issues -- tied to the tenant and the audit log, not scattered across chats.
Sprint 4 -- Billing & subscriptions admin
Scope | MRR / revenue dashboard, per-tenant plan + manual override, Razorpay reconciliation (webhook + payment history), trial & dunning state, and credits / refunds -- on the India-primary Razorpay stack.
Why | Usage telemetry exists but there's nowhere to see revenue, fix a mis-charged tenant, extend a trial, or reconcile a Razorpay webhook.
Sprint 5 -- Observability & logs
Scope | A structured request / error-log viewer, provider-outage history + timeline (beyond the current point-in-time alerts), rate-limit / abuse monitoring, and scheduler / worker run status.
Why | When something breaks for a tenant, admin needs the logs + provider timeline in-console, not an SSH session.
Sprint 6 -- Feature flags & config
Scope | A UI over per-tenant + global feature flags (tenant.feature_flags already exists in the schema), plan-gated capabilities, staged rollout, and kill-switches for risky features.
Why | Ship features to a subset, gate by plan, and disable a misbehaving feature without a deploy.
Sprint 7 -- Admin RBAC & security
Scope | Multiple admin roles (super-admin / support / billing / read-only) with scoped permissions, admin 2FA, optional IP allowlist, and admin session management / revocation.
Why | A support agent shouldn't be able to delete a tenant or rotate provider keys. Least-privilege for the console itself.
Sprint 8 -- Announcements & comms
Scope | In-app broadcast + maintenance banners to tenants, targeted email to workspace owners, and a changelog / release-notes surface.
Why | One place to tell customers about maintenance, incidents, and new features.
Sprint 9 -- Compliance & data ops (DPDP / GDPR)
Scope | Per-tenant data export, retention policy + purge scheduling, consent / audit exports, and a structured deletion workflow (hard-delete exists; add export-before-delete + retention).
Why | DPDP/GDPR require export + retention + a documented deletion path, not just a delete button.
Sprint 10 -- Admin polish, tests & QA
Scope | UX consistency + responsive / mobile admin, automated tests for every admin endpoint + the RBAC matrix, and an admin API-parity gate.
Why | The console is now business-critical -- it needs the same test rigor as the tenant app.

## Dashboard
DecisionOS - Epic 9 - Admin / Platform Console
Grow the shipped platform super-admin console into a full ops + support console: tenant 360, secure impersonation, support desk, billing/subscriptions, and observability. Kickoff: 2026-08-23.
Epic 9 -- Admin / Platform Console COMPLETE. S0 shipped + S1-S10 done: Tenant 360, impersonation, support desk, billing, observability, feature-flags/config, admin RBAC+2FA, announcements, compliance & data ops (DPDP export/retention/DSAR/erasure-receipt), and admin polish + a test & parity gate. 10 admin tabs + a tenant announcement banner; ~68 admin routes, all behind the platform-admin gate.
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 0 | Current state (shipped) | 10 | 10 | 100% | COMPLETE | Already in production: separate /admin auth + dos_admin_token + platform_audit; 8-tab portal (Overview/metrics/alerts, Usage, AI Keys+probes, Workspaces CRUD, Users lifecycle, Maintenance, Audit, Health). 24 routes.
Sprint 1 | Tenant 360 & cross-tenant search | 7 | 7 | 100% | COMPLETE | One per-workspace view (users+plan+usage+config+activity+health+logs) + global search across tenants/users/contacts + tenant timeline.
Sprint 2 | Support impersonation (view as tenant) | 6 | 6 | 100% | COMPLETE | Secure, time-boxed, audited read-first impersonation with a support-session banner, auto-expiry + consent. The core support capability.
Sprint 3 | Support desk & tickets | 7 | 7 | 100% | COMPLETE | Ticket inbox tied to tenants (+ jump to impersonation): create/triage/assign/resolve, SLA timers, canned responses, in-app + email intake.
Sprint 4 | Billing & subscriptions admin | 7 | 7 | 100% | COMPLETE | MRR/revenue dashboard, per-tenant plan + override, Razorpay reconciliation (webhook/payment history), trials & dunning, credits/refunds.
Sprint 5 | Observability & logs | 6 | 6 | 100% | COMPLETE | Request/error-log viewer, provider-outage history + timeline, rate-limit/abuse monitoring, scheduler/worker run status.
Sprint 6 | Feature flags & config | 7 | 7 | 100% | COMPLETE | UI over per-tenant + global feature flags, plan-gated capabilities, staged rollout, kill-switches.
Sprint 7 | Admin RBAC & security | 6 | 6 | 100% | COMPLETE | Admin roles (super-admin/support/billing/read-only), admin 2FA, IP allowlist, admin session management/revocation.
Sprint 8 | Announcements & comms | 5 | 5 | 100% | COMPLETE | In-app broadcast + maintenance banners, targeted email to owners, changelog/release-notes surface.
Sprint 9 | Compliance & data ops (DPDP/GDPR) | 6 | 6 | 100% | COMPLETE | Per-tenant data export, retention + purge, consent/audit exports, structured deletion workflow (export-before-delete).
Sprint 10 | Admin polish, tests & QA | 6 | 6 | 100% | COMPLETE | Responsive/mobile admin, automated tests for every admin endpoint + RBAC matrix, admin API-parity gate.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
U10-00.1 | routers/admin.py | 0 | Auth | Platform super-admin auth | Separate /admin login + logout + me on a dos_admin_token cookie (distinct from tenant auth), 5-attempt lockout, get_platform_admin dependency, and an immutable platform_audit action log. | P0 | M | Done |  | Ships. login/logout/me + log_admin_action. | Epic 9 S0 (audit)
U10-00.2 | AdminPortal / Overview | 0 | Overview | Platform metrics + provider alerts | Overview tab: platform-wide counts (tenants, users, decisions, tasks, captures, workflows, contacts, tasks_done) + provider-outage alerts. | P1 | S | Done |  | GET /admin/metrics + /admin/alerts; OverviewSection. | Epic 9 S0 (audit)
U10-00.3 | AdminPortal / Usage | 0 | Usage | AI credit usage by workspace | Usage tab: AI credit consumption filterable by range (today/7d/30d/all) and provider (Sarvam/Claude/Emergent/OpenAI/Gemini), per workspace. | P1 | M | Done |  | GET /admin/usage; UsageSection. | Epic 9 S0 (audit)
U10-00.4 | AdminPortal / AI Keys | 0 | Providers | AI provider keys + live probes | AI Keys tab: view (masked) + set platform provider keys, and a 'Test All Keys' live status probe for Anthropic, OpenAI, Gemini, WhatsApp and Sarvam. | P1 | M | Done |  | GET/PUT /admin/ai-keys + /admin/ai-keys/status (5 probes); AiKeysSection. | Epic 9 S0 (audit)
U10-00.5 | AdminPortal / Workspaces | 0 | Tenants | Workspace administration | Workspaces tab: list all tenants, suspend, reactivate, and delete a tenant (with obj_store file cleanup for DPDP compliance). | P1 | M | Done |  | GET /admin/tenants + suspend/reactivate/DELETE; TenantsSection. | Epic 9 S0 (audit)
U10-00.6 | AdminPortal / Users | 0 | Users | User lifecycle administration | Users tab: list users (optionally by tenant), suspend, reactivate, and reset-access for a user across the platform. | P1 | M | Done |  | GET /admin/users + suspend/reactivate/reset-access; UsersSection. | Epic 9 S0 (audit)
U10-00.7 | AdminPortal / Audit Log | 0 | Audit | Platform audit log | Audit Log tab: the immutable platform_audit trail of every super-admin action (who/what/target/when). | P1 | S | Done |  | GET /admin/audit; AuditSection. | Epic 9 S0 (audit)
U10-00.8 | AdminPortal / Health | 0 | Ops | Platform health | Health tab: platform health signals (DB, providers, service). | P2 | S | Done |  | GET /admin/health; HealthSection. | Epic 9 S0 (audit)
U10-00.9 | AdminPortal / Maintenance | 0 | Ops | Maintenance jobs | Maintenance tab: migration ledger, scheduler leader-locks, and the reclassify-purchases backfill job (+status). | P2 | M | Done |  | GET /admin/migrations + /admin/scheduler-locks + POST /admin/reclassify-purchases(+status); MaintenanceSection. | Epic 9 S0 (audit)
U10-00.10 | pages/admin/ | 0 | Frontend | Admin portal shell (8 tabs) | The admin SPA: AdminLogin + AdminPortal shell with 8 nav tabs wiring the sections above (Overview/Usage/AI Keys/Workspaces/Users/Maintenance/Audit/Health). Warm dark admin theme. | P1 | M | Done |  | pages/admin/{AdminLogin,AdminPortal,AdminSections}.js (947 lines); routes /admin + /admin/*. | Epic 9 S0 (audit)
U10-06.1 | Admin console + AI model routing | 6 | Config | Admin model switcher -- change model-per-task at runtime | Runtime, DB-backed override of MODEL_ROUTES per AI task from the super-admin console (no redeploy). model_for() reads an override layer first: env -> DB override -> MODEL_ROUTES -> default. Admin picks the model per task from the MODELS catalog; the change is audited. Pairs with the AI quality dashboard (E3-10.2) so the effect of a switch is visible. | P2 | M | Done | E3-01.2 | Done 2026-08-27: DB-backed override in db.platform_config, applied to sync hot paths (config._MODEL_OVERRIDES for model_for; integrations.stt._SARVAM_RUNTIME for STT model/mode). Loaded at boot + refreshed each scheduler tick so replicas converge. Verified: model_for + Sarvam hot path change with no redeploy. | Epic 9 S6
U10-06.2 | Admin console + STT/TTS config | 6 | Config | Sarvam STT + TTS model/mode/voice admin config | Runtime, DB-backed admin config for the Sarvam voice stack (no redeploy): STT model (saaras:v3 / v4), STT mode (transcribe / translate / codemix -- codemix best for Tanglish), and Bulbul TTS voice model + speaker. Read by the integrations/stt.py + TTS layer, override order env -> DB -> default. Sibling to U10-06.1 (LLM model switcher) and U10-00.4 (AI provider keys). | P2 | M | Done | E3-07.1 | Done 2026-08-27: DB-backed override in db.platform_config, applied to sync hot paths (config._MODEL_OVERRIDES for model_for; integrations.stt._SARVAM_RUNTIME for STT model/mode). Loaded at boot + refreshed each scheduler tick so replicas converge. Verified: model_for + Sarvam hot path change with no redeploy. | Epic 9 S6
U10-01.1 | Admin / Tenant 360 | 1 | Feature | Cross-tenant search | GET /api/admin/search?q= -- find a workspace (name/id) or user (name/email/phone/id) across all tenants; returns tenants + users with workspace names attached. Gated by get_platform_admin, read-only. | P1 | M | Done |  | routers/admin_tenant360.py | Epic 9 S1
U10-01.2 | Admin / Tenant 360 | 1 | Feature | Tenant 360 aggregate endpoint | GET /api/admin/tenants/{id}/360 -- one consolidated per-workspace payload: plan+entitlements, entity counts (users/decisions/tasks/workflows/contacts/invoices/complaints), members, AI spend (30d+all-time), recent activity, health. Parallel queries via asyncio.gather. | P1 | M | Done | U10-01.1 | routers/admin_tenant360.py | Epic 9 S1
U10-01.3 | Admin / Tenant 360 | 1 | Feature | Per-tenant members + roles | Members list (name/email/role/suspended/created) + active-membership count in the 360 payload. | P1 | S | Done | U10-01.2 | part of 360 | Epic 9 S1
U10-01.4 | Admin / Tenant 360 | 1 | Feature | Per-tenant AI spend | AI spend rollup (calls/tokens/cost) for last-30d and all-time from usage_events, in the 360 payload. | P1 | S | Done | U10-01.2 | part of 360 | Epic 9 S1
U10-01.5 | Admin / Tenant 360 | 1 | Feature | Per-tenant config + entitlements view | Plan, seat limit(+override), feature_flags, usage_quotas, AI consent, GST, industry/region/currency surfaced in the 360. | P1 | S | Done | U10-01.2 | part of 360 | Epic 9 S1
U10-01.6 | Admin / Tenant 360 | 1 | Feature | Activity timeline + health signals | Recent db.activity timeline (20) + health (last_activity, suspended, ai_consent) in the 360. | P1 | S | Done | U10-01.2 | part of 360 | Epic 9 S1
U10-01.7 | Admin portal | 1 | Frontend | Tenant 360 tab (search + drill-in) | New AdminPortal tab: search box -> workspace/user results -> click to open the consolidated 360 view (counts grid, spend, entitlements, health, members, activity). Self-contained Tenant360Section.js matching the admin dark theme. | P1 | M | Done | U10-01.2 | frontend/src/pages/admin/Tenant360Section.js | Epic 9 S1
U10-02.1 | Admin / Impersonation | 2 | Security | Impersonation token + session model | create_impersonation_token (core/security): a short-lived target-user JWT with an `imp` claim {admin, session_id, read_only}, exp<=240m, bound to an impersonation_sessions record {admin_email, tenant, target, read_only, reason, granted/expires, revoked}. | P1 | M | Done |  | core/security.py | Epic 9 S2
U10-02.2 | core/deps | 2 | Security | get_current_user impersonation recognition | get_current_user detects the `imp` claim, verifies the impersonation_sessions record is live (not revoked / not expired) -- session-based revocation replaces the jti check -- and loads the target user with membership projection. | P1 | M | Done | U10-02.1 | core/deps.py | Epic 9 S2
U10-02.3 | core/deps | 2 | Security | Read-first enforcement | When the session is read_only, any mutating request (non GET/HEAD/OPTIONS) is blocked with 403 'writes are blocked'. Verified end-to-end: GET reads as tenant, POST -> 403, revoke -> 401. | P1 | S | Done | U10-02.2 | core/deps.py | Epic 9 S2
U10-02.4 | Admin / Impersonation | 2 | Feature | Grant / list / revoke endpoints + audit | POST /admin/tenants/{id}/impersonate (reason/target/minutes/read_only) -> session+token; GET /admin/impersonation -> sessions with live/expired/revoked status; POST /admin/impersonation/{id}/revoke. Every grant+revoke written to platform_audit. | P1 | M | Done | U10-02.1 | routers/admin_impersonation.py | Epic 9 S2
U10-02.5 | Admin / Impersonation | 2 | Feature | Impersonation flags for banner + audit | get_current_user stamps _impersonated_by / _read_only / _impersonation_session on the user (survives project_membership_onto_user), so /me exposes them for an in-app banner and downstream audit. | P1 | S | Done | U10-02.2 | core/deps.py + /me | Epic 9 S2
U10-02.6 | Admin portal | 2 | Frontend | Impersonation tab + 'View as tenant' | New Impersonation admin tab (sessions list with status + End/revoke). 'View as tenant' button in Tenant 360 starts a 30m read-only session (audited, prompts for reason). Seamless browse-as-tenant + in-app banner noted as a follow-on UX refinement. | P1 | M | Done | U10-02.4 | frontend/src/pages/admin/ImpersonationSection.js | Epic 9 S2
U10-03.1 | Admin / Support | 3 | Feature | Ticket model + create | support_tickets collection {tenant, subject, status(open/pending/resolved/closed), priority(low/normal/high/urgent), created_by(+type), assigned_admin, messages[]}. Created by admin (on a tenant's behalf) or by a tenant owner. | P1 | M | Done |  | routers/admin_support.py | Epic 9 S3
U10-03.2 | Admin / Support | 3 | Feature | Ticket inbox (filter + counts) | GET /admin/tickets?status=&priority=&tenant_id= -> newest-first list (messages omitted) + per-status counts. | P1 | S | Done | U10-03.1 | routers/admin_support.py | Epic 9 S3
U10-03.3 | Admin / Support | 3 | Feature | Ticket detail + thread | GET /admin/tickets/{id} -> full ticket incl. message thread. | P1 | S | Done | U10-03.1 | routers/admin_support.py | Epic 9 S3
U10-03.4 | Admin / Support | 3 | Feature | Reply + status/priority/assign | POST /admin/tickets/{id}/reply (adds admin msg, -> pending) + PATCH /admin/tickets/{id} (status/priority/assigned_admin). Audited. | P1 | M | Done | U10-03.1 | routers/admin_support.py | Epic 9 S3
U10-03.5 | Admin / Support | 3 | Feature | Jump to impersonation from ticket | Ticket detail 'View as tenant' starts a read-only impersonation session for the ticket's workspace (reuses S2). | P1 | S | Done | U10-03.3 | frontend SupportDeskSection | Epic 9 S3
U10-03.6 | Support (tenant) | 3 | Feature | Tenant-facing ticket submission | routers/support.py: POST /api/support/tickets (owner/member raises), GET /api/support/tickets (their tickets), reply. Writes naturally blocked under read-only impersonation. | P1 | M | Done | U10-03.1 | routers/support.py | Epic 9 S3
U10-03.7 | Admin portal | 3 | Frontend | Support desk tab | Inbox with status filter + counts -> ticket detail (thread, reply box, status/priority selects, view-as-tenant). SupportDeskSection.js. | P1 | M | Done | U10-03.2 | frontend/src/pages/admin/SupportDeskSection.js | Epic 9 S3
U10-04.1 | Admin / Billing | 4 | Feature | MRR & revenue dashboard | GET /admin/billing/overview: MRR/ARR recognised from active paid plans x list price, plan distribution, all-time + 30d revenue from db.billing_events, recent payments. Razorpay/INR. | P1 | M | Done |  | routers/admin_billing.py | Epic 9 S4
U10-04.2 | Admin / Billing | 4 | Feature | Per-tenant plan + subscription view | GET /admin/billing/tenants: plan, seat-limit override, lifetime revenue, last payment, #payments per workspace. | P1 | M | Done | U10-04.1 | routers/admin_billing.py | Epic 9 S4
U10-04.3 | Admin / Billing | 4 | Feature | Razorpay reconciliation | GET /admin/billing/reconciliation: events grouped by type, unmatched events (no tenant_id -> manual queue), failed/halted list. | P1 | M | Done | U10-04.1 | routers/admin_billing.py | Epic 9 S4
U10-04.4 | Admin / Billing | 4 | Feature | Subscription lifecycle view | Plan + last-payment + payment-count surfaced per tenant (overview + tenants); failed/halted in reconciliation. | P1 | S | Done | U10-04.2 | routers/admin_billing.py | Epic 9 S4
U10-04.5 | Admin / Billing | 4 | Feature | Manual plan override / comp | PATCH /admin/billing/tenants/{id}/plan: set plan (grant free/comp) + seat_limit_override with a required reason; audited. | P1 | M | Done | U10-04.2 | routers/admin_billing.py | Epic 9 S4
U10-04.6 | Admin / Billing | 4 | Feature | Per-tenant payment history | GET /admin/billing/tenants/{id}/payments: full billing-event history + lifetime revenue for one workspace. | P1 | S | Done | U10-04.2 | routers/admin_billing.py | Epic 9 S4
U10-04.7 | Admin portal | 4 | Frontend | Billing tab | MRR/ARR/revenue cards, plan-mix table, reconciliation summary, per-tenant list with inline plan override. BillingSection.js (INR formatting). | P1 | M | Done | U10-04.1 | frontend/src/pages/admin/BillingSection.js | Epic 9 S4
U10-05.1 | Admin / Observability | 5 | Feature | AI reliability + latency | GET /admin/observability/reliability?range=: error rate, degraded/fallback rate, latency p50/p95/max, breakdowns by provider (engine) + task, over 1h/24h/7d/30d. | P1 | M | Done |  | routers/admin_observability.py | Epic 9 S5
U10-05.2 | Admin / Observability | 5 | Feature | Recent-errors log viewer | GET /admin/observability/errors: recent failed AI calls (ok=False) with task/model/engine/error(PII-redacted)/tenant/time. | P1 | S | Done | U10-05.1 | routers/admin_observability.py | Epic 9 S5
U10-05.3 | Admin / Observability | 5 | Feature | Provider-outage timeline | GET /admin/observability/outages: platform_alerts history, active-first, with resolved/active status + active count. | P1 | S | Done |  | routers/admin_observability.py | Epic 9 S5
U10-05.4 | Admin / Observability | 5 | Feature | Error aggregation by task/provider | Per-task + per-provider error + degraded counts in the reliability payload (the aggregation surface). | P1 | S | Done | U10-05.1 | routers/admin_observability.py | Epic 9 S5
U10-05.5 | Admin / Observability | 5 | Feature | Latency / slow-call signals | Latency percentiles (p50/p95/max) overall + avg per provider/task from ai_calls.latency_ms. NOTE: rate-limit is in-memory (not persisted) -> fallback/degraded rate is the reliability signal instead. | P1 | S | Done | U10-05.1 | routers/admin_observability.py | Epic 9 S5
U10-05.6 | Admin portal | 5 | Frontend | Observability tab | Reliability cards (calls / error rate / fallback / p95 latency) + by-provider/by-task tables + recent-errors viewer + outage timeline, with a range selector. ObservabilitySection.js. | P1 | M | Done | U10-05.1 | frontend/src/pages/admin/ObservabilitySection.js | Epic 9 S5
U10-06.3 | Admin / Config | 6 | Feature | Per-tenant feature flags | GET/PATCH /admin/tenants/{id}/flags -> tenant.feature_flags (merge). Audited. | P1 | S | Done |  | routers/admin_config.py | Epic 9 S6
U10-06.4 | Admin / Config | 6 | Feature | Global feature flags | PATCH /admin/config/flags -> global_flags in db.platform_config; surfaced in GET /admin/config. | P1 | S | Done |  | routers/admin_config.py | Epic 9 S6
U10-06.5 | Admin / Config | 6 | Feature | Plan-gated capabilities | PATCH /admin/config/plan-capabilities -> {plan: {cap: bool}} in platform_config. | P1 | S | Done |  | routers/admin_config.py | Epic 9 S6
U10-06.6 | Admin / Config | 6 | Feature | Runtime config (thresholds) | PATCH /admin/config/runtime -> free-form runtime KV merged into platform_config (budgets, thresholds). | P1 | S | Done |  | routers/admin_config.py | Epic 9 S6
U10-06.7 | Admin portal | 6 | Frontend | Config & Flags tab | ConfigSection.js: Sarvam voice selects, global-flag toggles + add, and a per-task AI model-route override table (effective/default/override). | P1 | M | Done |  | frontend/src/pages/admin/ConfigSection.js | Epic 9 S6
U10-07.1 | Admin / RBAC | 7 | Security | Admin roles | platform_admins.role in super_admin/support/billing/read_only; existing admins default to super_admin (get_platform_admin stamps it). | P1 | M | Done |  | core/security.py | Epic 9 S7
U10-07.2 | Admin / RBAC | 7 | Security | Role enforcement | Global read-only guard (read_only admin blocked on any non-GET) in get_platform_admin + require_admin_role(*roles) dependency (super_admin always allowed). AI-keys write gated to super_admin. | P1 | M | Done | U10-07.1 | core/security.py + routers/admin.py | Epic 9 S7
U10-07.3 | Admin / RBAC | 7 | Security | Admin 2FA (TOTP) | Enroll/confirm/disable reusing services.auth.totp, stored on platform_admins.two_factor; admin_login gated (requires_2fa -> code) when enabled. Verified with a pyotp code + 10 backup codes. | P1 | M | Done | U10-07.1 | routers/admin_rbac.py | Epic 9 S7
U10-07.4 | Admin / RBAC | 7 | Security | Admin user management | super_admin-only: GET/POST /admin/admins, PATCH role/active, self-demote/deactivate guard. Audited. | P1 | M | Done | U10-07.1 | routers/admin_rbac.py | Epic 9 S7
U10-07.5 | Admin / RBAC | 7 | Security | Session security signals | last_login stamped on admin login; read-only guard + full platform_audit trail; admin active/deactivate. (IP allowlist deferred.) | P1 | S | Done | U10-07.2 | routers/admin.py | Epic 9 S7
U10-07.6 | Admin portal | 7 | Frontend | Admin RBAC tab | AdminRbacSection.js: manage admins (add/role/deactivate, super_admin only) + own 2FA (enroll -> confirm -> backup codes / disable). | P1 | M | Done | U10-07.4 | frontend/src/pages/admin/AdminRbacSection.js | Epic 9 S7
U10-08.1 | Admin / Announce | 8 | Feature | In-app broadcast + banner model | announcements collection {title, body, kind(info/warning/maintenance), audience, active, dismissible, created_by}. Admin CRUD: create/list/patch/delete. Audited. | P1 | M | Done |  | routers/admin_announcements.py | Epic 9 S8
U10-08.2 | Admin / Announce | 8 | Feature | Maintenance scheduling | starts_at/ends_at + active -> _is_live() so a banner shows only in-window; scheduled maintenance banners. | P1 | S | Done | U10-08.1 | routers/admin_announcements.py | Epic 9 S8
U10-08.3 | Admin / Announce | 8 | Feature | Targeted email to owners | POST /admin/announcements/{id}/email: resolve targeted workspaces -> owner emails -> send_email (capped 1000), audited with sent/target count. | P1 | M | Done | U10-08.1 | routers/admin_announcements.py | Epic 9 S8
U10-08.4 | Announcements (tenant) | 8 | Feature | Audience targeting + tenant feed | audience all ¦ plan:<key> ¦ tenant:<id>; GET /api/announcements/active returns live+targeted announcements for the caller's workspace (in-app banner feed). | P1 | M | Done | U10-08.1 | routers/admin_announcements.py | Epic 9 S8
U10-08.5 | App + admin portal | 8 | Frontend | Announcements tab + in-app banner | Admin Announce tab (create/enable/email/delete). Tenant AnnouncementBanner mounted in Layout: dismissible (localStorage), kind-coloured, reads /api/announcements/active. | P1 | M | Done | U10-08.4 | frontend AnnouncementsSection.js + components/AnnouncementBanner.js | Epic 9 S8
U10-QA.1 | Admin / Usage | 0 | Bugfix | Fix admin_usage motor aggregate() coroutine bug | Split `db.usage_events.aggregate(...).to_list()` into `_cur = await db...aggregate(...); await _cur.to_list(N)` in both the per-provider and per-workspace queries. Under motor 3.x aggregate() returns a coroutine so chained .to_list() raised AttributeError -> 500. Caught in browser QA walk-through of the Admin > Usage tab; endpoint now returns 200 OK. | P0 | XS | Done |  | routers/admin.py (S0 admin_usage) | Epic 9 QA fix (browser preview walk-through)
U10-09.1 | routers/admin_compliance.py | 9 | Compliance | Per-tenant data export API | GET /admin/tenants/{id}/export -- one JSON bundle of every tenant-scoped collection, built off the same TENANT_COLLECTIONS single-source-of-truth the deleter uses, so an export is a faithful pre-image of an erasure. Row-capped, audited. | P0 | M | Done |  | routers/admin_compliance.py :: admin_export_tenant | Epic 9 S9/S10 build 2026-08-29
U10-09.2 | services/retention.py + admin_compliance | 9 | Compliance | Retention policy + daily purge | Per-tenant retention {enabled, ttl_days, collections} on transient/log collections only (activity, notifications, usage_events, wa_events, voice_notes, brain_audit, ingestions). MIN_TTL 30d guard. GET/PUT /admin/tenants/{id}/retention with dry-run candidate counts. | P0 | M | Done |  | services/retention.py + admin_get/set_retention | Epic 9 S9/S10 build 2026-08-29
U10-09.3 | routers/admin_compliance.py | 9 | Compliance | Consent + audit export | GET /admin/tenants/{id}/consent-export -- AI-processing consent state + consent-tagged activity + every platform-admin action targeting the tenant. The DPDP 'who agreed to what' trail. | P1 | S | Done |  | admin_consent_export | Epic 9 S9/S10 build 2026-08-29
U10-09.4 | routers/admin_compliance.py | 9 | Compliance | Structured export-before-delete (erasure receipt) | POST /admin/tenants/{id}/delete-with-export (super_admin) -- builds a full export bundle, THEN hard-deletes via admin_delete_tenant, returning the export as an erasure receipt + the deletion summary. DPDP 'documented deletion path', not just a delete button. | P0 | M | Done |  | admin_delete_with_export | Epic 9 S9/S10 build 2026-08-29
U10-09.5 | routers/admin_compliance.py | 9 | Compliance | Per-user DSAR export | GET /admin/users/{id}/dsar -- data-subject-access-request: everything the platform holds about one person across the collections carrying a person-field (assignee_id/created_by/user_id/...). | P1 | M | Done |  | admin_user_dsar | Epic 9 S9/S10 build 2026-08-29
U10-09.6 | workers/schedulers.py + admin_compliance | 9 | Compliance | Retention sweep: scheduler hook + manual trigger + status | run_retention_sweep wired into the leader-locked scheduler tick, throttled to once/~24h via a db.platform_ops marker. GET /admin/retention/status (all policies + candidates + last sweep) and POST /admin/retention/run (super_admin, dry-run default) for a manual purge. | P1 | M | Done |  | workers/schedulers._maybe_run_retention_sweep + admin_retention_status/run | Epic 9 S9/S10 build 2026-08-29
U10-10.1 | frontend/src/pages/admin/* | 10 | Frontend | Responsive admin + Compliance tab | New Compliance tab (Scales icon) with a responsive lg:grid-cols-2 layout: workspace search + data-subject actions on the left, platform retention sweep on the right. Tab nav already overflow-x scrolls; section grids collapse to one column on narrow viewports. | P1 | M | Done |  | frontend ComplianceSection.js + AdminPortal tab | Epic 9 S9/S10 build 2026-08-29
U10-10.2 | tests/test_admin_compliance.py | 10 | Tests | pytest for compliance endpoints | Unit tests over a fake Mongo: retention policy resolution + defaults + MIN_TTL clamp, dry-run vs live purge and the <cutoff window, disabled-policy no-op, cross-tenant isolation, sweep touches only policy tenants, and export covers TENANT_COLLECTIONS. 11 tests. | P0 | M | Done |  | tests/test_admin_compliance.py | Epic 9 S9/S10 build 2026-08-29
U10-10.3 | tests/test_admin_rbac_matrix.py | 10 | Tests | Admin RBAC matrix tests | Exhaustive require_admin_role(*roles) matrix: super_admin passes every gate; a matching role passes; every other role is 403; read_only never reaches a mutating gate. Plus a check that the two destructive compliance routes are super_admin-only. 6 tests. | P0 | S | Done |  | tests/test_admin_rbac_matrix.py | Epic 9 S9/S10 build 2026-08-29
U10-10.4 | tests/test_admin_parity.py | 10 | Tests | Admin API-parity gate | Focused /api/admin contract: every admin route resolves through get_platform_admin (allow-listing the open login + the tenant-owner audit-log path), all Sprint 9 compliance routes present, and the admin route count matches a committed number so an added/dropped admin route is an explicit diff. | P0 | S | Done |  | tests/test_admin_parity.py | Epic 9 S9/S10 build 2026-08-29
U10-10.5 | cross-cutting (admin) | 10 | Frontend | Copy + UX consistency pass | Compliance section reuses the shared admin dark-theme style consts (CARD/H2/H3/BTN/INP), mono uppercase labels, and semantic action colours (green export, red erasure, blue search) matching every other admin tab. Confirm dialogs name the blast radius on both irreversible actions. | P2 | S | Done |  | ComplianceSection styling + confirm copy | Epic 9 S9/S10 build 2026-08-29
U10-10.6 | cross-cutting (admin) | 10 | Tests | Admin exit gate: whole-surface gate + parity | The admin-parity gate asserts NO /api/admin route is reachable without the platform-admin dependency (the security exit gate for a business-critical console) and the whole-app route baseline + fingerprint sha is regenerated to include the 8 new compliance routes. Full suite green. | P0 | S | Done |  | test_admin_parity::test_every_admin_route_is_gated + regen'd api_route_baseline.json | Epic 9 S9/S10 build 2026-08-29