## Cover
DecisionOS
Epic 8 -- Backend Optimization & Modularization
Kickoff | 2026-08-20 (post karma UI merge; runs on the Backend_optimization branch)
Origin | Founder ask 2026-08-20: 'create a new epic -- complete backend optimization, code review, modular code approaches, readable. First sprint = make big-block code into a SaaS-ready folder approach, modular approach for FastAPI. Add the other sprints too but don't add the backlogs and tasks yet. For the first sprint, completely analyse our complete backend folder -- how to make it better and readable.'
Epic 8 goal | Take the backend from working-but-monolithic (a 6,665-line server.py holding 86 endpoints + 35 models + business logic + a ~900-line bootstrap; a 775-line kitchen-sink core.py) to a clean, domain-modular, SaaS-ready FastAPI codebase that is readable, testable, and safe to scale -- with ZERO change to external API behavior. This finishes the migration that Phase A/B started and stalled.
Sprint 1 -- foundation start | Modular foundation & architecture. Agree the SaaS-ready package-by-feature target, stand up the empty app/ skeleton, and split app-assembly out of server.py -- without moving a single endpoint yet. The full current-state analysis lives in DecisionOS_Epic8_Sprint1_Backend_Analysis.md.
Working principles | 1. Strangler-fig: new structure grows beside the old; nothing deleted until its replacement is proven. 2. One domain per PR -- small, reviewable, reversible. 3. API parity is the contract: same routes, status codes, payloads before and after. 4. Every move is test-guarded by the 60+ test_iteration suite. 5. Package by feature, not by technical layer. 6. A module never imports another module's internals -- shared logic goes to shared/. 7. Delete every compat shim by the end -- no half-finished migration this time.
Note on backlog | Per the founder ask, this tracker defines the sprint plan only. Task-level backlog rows are filled in per sprint as each is picked up -- not front-loaded.
Sprint breakdown
>>> Sprint 1 -- Modular foundation & architecture
Scope | Stand up the SaaS-ready app/ skeleton (core/ shared/ modules/ integrations/ workers/ bootstrap/) and split app-assembly (FastAPI(), middleware, include_router, startup/shutdown) out of server.py. No endpoints moved.
Why | FOUNDATION SPRINT. Agree the target architecture and lay the empty modular structure before any code moves. Carries the full backend current-state analysis (DecisionOS_Epic8_Sprint1_Backend_Analysis.md).
Status | Analysis / sign-off
Sprint 2 -- Core decomposition & typed settings
Scope | Break the 775-line kitchen-sink core.py into core/ (config, db, security, deps, permissions, logging, errors). Adopt pydantic BaseSettings. Delete the top-level + services/ compat shims.
Why | core.py mixes infra + auth + authz + AI client + billing telemetry + domain normalizers; everything imports all of it. A thin, layered core kills the circular-import hacks.
Status | Planned
Sprint 3 -- Domain router extraction
Scope | Move the 86 endpoints still inline in server.py's api router into per-domain modules/*/router.py (auth, tenant, capture, decisions, tasks, workflows, crm, finance, brain, operating_score, brief, people, whatsapp, billing, admin).
Why | Half the public API still lives in the file that should only assemble the app. Extracting it retires the God router and makes each domain reasoned about in isolation.
Status | Planned
Sprint 4 -- Service-layer isolation
Scope | Pull business logic out of routers into domain services: AI helpers, STT/transcription, the voice-note pipeline, document ingestion, capture/triage, finance rules. Routers become thin transport.
Why | Logic welded to endpoints can't be unit-tested without FastAPI or reused by a worker/CLI. Thin routers + fat services is the testable, reusable shape.
Status | Planned
Sprint 5 -- Schema & model consolidation
Scope | Gather the 35+ Pydantic models scattered in server.py and routers into modules/*/schemas.py. Populate the near-empty models/. Standardize request/response contracts and shared base models.
Why | There is no single place to see a domain's API contract today. Consolidated schemas make the surface reviewable and enable contract tests in S10.
Status | Planned
Sprint 6 -- Integration adapters
Scope | Isolate every external provider behind one adapter: OpenAI STT, Gemini, Sarvam, WhatsApp API, Razorpay, SMTP email, object store. Centralize timeouts, retries, and SSRF guarding.
Why | Provider calls are sprinkled through server.py. One adapter per provider gives a single seam to mock in tests, swap a vendor, or enforce timeouts.
Status | Planned
Sprint 7 -- Background jobs & bootstrap lifecycle
Scope | Extract the ~900-line _bootstrap, the follow-up/finance schedulers, seed and migration routines into workers/ + bootstrap/. Replace @app.on_event with a clean lifespan.
Why | Startup logic and one-time migrations sit in the request-path file. Moving them out shrinks server.py to nothing and makes startup auditable.
Status | Planned
Sprint 8 -- Code review & readability pass
Scope | Naming, full type hints, module/function docstrings, dead-code removal, consistent error envelope, logging discipline. Wire ruff + black + an import-linter into CI.
Why | 'Readable' has to be enforced, not hoped for: size ceilings, typed signatures, no bare excepts, no late imports. CI makes the standard non-negotiable.
Status | Planned
Sprint 9 -- Performance & data-access optimization
Scope | N+1 query audit, Mongo index review, async correctness (no blocking calls on async paths), pagination on list endpoints, caching of hot reads.
Why | Modularization exposes the data-access seams; this is where we make them fast and index-backed before scale, without changing behavior.
Status | Planned
Sprint 10 -- Test restructure, API-parity gate & CI exit
Scope | Restructure the 60+ test_iteration tests to mirror modules/. Add contract tests proving before/after API parity. CI exit gate: lint + types + tests + import rule. Define epic exit criteria.
Why | The epic's promise is 'no external behavior change.' Parity tests prove it, and the exit gate stops the refactor stalling half-done the way Phase A/B did.
Status | Planned

## Dashboard
DecisionOS - Epic 8 - Backend Optimization & Modularization
Finish the Phase A/B migration: a domain-modular, SaaS-ready FastAPI backend that is readable, testable, and safe to scale -- with zero change to external API behavior. Kickoff: 2026-08-20.
Epic 8 status: IN PROGRESS. S1 modular foundation done (7/8). S2 core decomposition COMPLETE (8/8): core.py 917-line kitchen sink split into core/ (permissions, security, deps, ai_keys, usage) + shared/ (ids, json, normalizers) + integrations/llm; all 11 compat shims retired. core/__init__ now 117 lines of re-exports. 59 unit tests + live smokes; full regression at epic end.
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 1 | Modular foundation & architecture | 7 | 8 | 88% | In progress | FOUNDATION SPRINT. SaaS-ready package-by-feature skeleton + app-assembly split out of the 6,665-line server.py. Current-state analysis + target folder tree + safe migration order. No endpoint moved yet.
Sprint 2 | Core decomposition & typed settings | 8 | 8 | 100% | COMPLETE | core.py -> core/ package (config, db, security, deps, permissions, logging). Typed settings via BaseSettings. Retire obj_store/brain_context/brain_rbac compat shims left over from Phase A/B.
Sprint 3 | Domain router extraction | 13 | 16 | 6% | In progress | The headline move: 86 inline endpoints (35 GET/31 POST/12 PATCH/5 DELETE/2 PUT) out of server.py into domain modules. server.py stops being a feature file. One domain per PR, strangler-fig.
Sprint 4 | Service-layer isolation |  |  |  | Planned | Business logic (ai_extract, transcribe_audio, process_voice_note, ingestion, capture engine, finance signals) moves router -> service. Routers only validate, call a service, and shape the response.
Sprint 5 | Schema & model consolidation |  |  |  | Planned | 35 BaseModel classes inline in server.py + more in routers -> per-domain schemas.py. Fill the ~123-line models/ package. One obvious home for every request/response shape.
Sprint 6 | Integration adapters |  |  |  | Planned | OpenAI/Gemini/Sarvam/WhatsApp/Razorpay/SMTP/obj_store -> integrations/ adapters. Resilient LLM wrapper and SSRF guard centralized. Providers become mockable seams, not inline SDK calls.
Sprint 7 | Background jobs & bootstrap lifecycle |  |  |  | Planned | _bootstrap (~900 lines), _followup_scheduler_loop, run_finance_actions, seed_demo, migrate_* -> workers/ + bootstrap/. Lifespan-based startup/shutdown. server.py finishes at ~zero lines.
Sprint 8 | Code review & readability pass |  |  |  | Planned | The readability standard (file <400 lines, typed signatures, docstrings, one error envelope, import hygiene) applied across the tree and enforced by ruff + black + import-linter in CI.
Sprint 9 | Performance & data-access optimization |  |  |  | Planned | N+1 audit across enrich_* fan-outs, Mongo index review, kill blocking calls in async handlers, paginate list endpoints, cache hot reads (operating score, dashboard). Behavior-preserving.
Sprint 10 | Test restructure, API-parity gate & CI exit |  |  |  | Planned | Tests mirror modules/. API-parity contract tests (same routes/status/payloads before vs after). CI gate = lint + types + tests + cross-module import rule. Exit: 0 endpoints in server.py, 0 shims.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
U8-01.1 | server.py, bootstrap/ | 1 | Structure | Stand up modular package skeletons | Create bootstrap/, integrations/, workers/, shared/ as siblings of routers/services/models/utils, each with an __init__ docstring stating purpose + import rule. Target stays a flat backend/ root (not nested app/) so server:app and existing imports keep working. | P1 | S | Done |  |  | Epic 8 S1
U8-01.2 | server.py, bootstrap/ | 1 | Refactor | Extract router registration -> bootstrap/routing.py | Move app.include_router(api) + the 19 domain-router includes out of server.py into register_api_routers(app, api). Include order + prefixes unchanged. | P1 | M | Done |  |  | Epic 8 S1
U8-01.3 | server.py, bootstrap/ | 1 | Refactor | Extract middleware -> bootstrap/middleware.py | Move CORS + CSRF setup into register_middleware(app), preserving add-order so the Starlette stack stays [CSRF, CORS]. | P1 | S | Done |  |  | Epic 8 S1
U8-01.4 | server.py, bootstrap/ | 1 | Refactor | Wire server.py to bootstrap; keep server:app entry | server.py calls register_api_routers + register_middleware. Entry point unchanged (Dockerfile / Procfile / test_dockerfile all still assert 'uvicorn server:app'). | P1 | S | Done |  |  | Epic 8 S1
U8-01.5 | server.py, bootstrap/ | 1 | Verification | Route-fingerprint parity harness | Import server.app before/after and compare a SHA-256 over the sorted route table + middleware order. Result: 260 routes, identical fingerprint, [CSRF, CORS] unchanged. Zero behaviour change. | P0 | S | Done |  |  | Epic 8 S1
U8-01.6 | server.py, bootstrap/ | 1 | Docs | Backend current-state analysis (Sprint 1 doc) | DecisionOS_Epic8_Sprint1_Backend_Analysis.md: server.py 6,665-line monolith map (86 endpoints, 35 models, ~900-line _bootstrap), core.py kitchen sink, target domain-modular architecture + strangler-fig order. | P1 | M | Done |  |  | Epic 8 S1
U8-01.7 | server.py, bootstrap/ | 1 | Docs | Align target to flat root + update ARCHITECTURE.md | Reconcile Epic 8 target with the existing Phase A/B flat structure; fix the corrupted tail of ARCHITECTURE.md; document the bootstrap/ split + layering rule. | P2 | S | Done |  |  | Epic 8 S1
U8-01.8 | server.py, bootstrap/ | 1 | Testing | Full regression suite green in CI | Run the test_iteration* suite against the shared preview backend (pytest -n 2 --dist loadscope). Pending: preview backend not reachable from the dev box; compile + dockerfile + route-parity checks pass locally. | P1 | S | Backlog |  |  | Epic 8 S1
U8-02.1 | core.py, shared/, core/ | 2 | Refactor | Extract pure normalizers -> shared/normalizers.py | Move blueprint/lexicon/operating-model coercion (normalize_os_blueprint, normalize_lexicon, normalize_operating_model + helpers, DEFAULT_OPERATING_MODEL/LEXICON) out of core.py into shared/. core.py re-exports them. core.py 917->628 lines (-32%). | P1 | M | Done |  | Verified byte-identical: normalizer golden SHA + 260-route fingerprint unchanged + compile. Pure functions, no db/auth. + 12 unit tests (tests/test_epic8_s2_normalizers.py). | Epic 8 S2
U8-02.2 | core.py, shared/, core/ | 2 | Refactor | Extract auth primitives -> core/security.py | Move hash_password, verify_password, create_token, create_admin_token, auth/CSRF/admin cookies, and get_platform_admin into core/security.py (renamed the HTTPBearer instance to bearer_scheme to avoid shadowing the module). core re-exports all. | P1 | M | Done |  | Unit-tested: tests/test_epic8_s2_security.py (10). Live: login 200, protected 200 (Bearer), wrong-pw 401, no-auth 401. Fingerprint 260. | Epic 8 S2
U8-02.3 | core.py, shared/, core/ | 2 | Refactor | Split auth request-dependencies -> core/deps.py | Move get_current_user, require_role, require_perm, tenant_role_keys into core/deps.py; re-exported at end of core/__init__ so set_usage_tenant is available. core/__init__ 400->280 lines. | P1 | M | Done |  | Unit-tested: tests/test_epic8_s2_deps.py (8, factory checkers). Live: login 200, 6 protected 200 (Bearer), no-auth 401. Fingerprint 260. | Epic 8 S2
U8-02.4 | core.py, shared/, core/ | 2 | Refactor | Split usage telemetry + AI keys + resilient LLM | AI keys -> core/ai_keys.py; usage/cost telemetry + provider alerts -> core/usage.py; _ResilientChat/claude_chat -> integrations/llm.py (first integrations/ module). core/__init__ 280->117 lines (917 at S2 start). | P2 | M | Done |  | Unit-tested: tests/test_epic8_s2_usage_llm.py (9). Live: usage+ai-keys 200, real POST /api/ask 200 via claude_chat. Fingerprint 260. 59/59 all S2 tests. | Epic 8 S2
U8-02.5 | core.py, shared/, core/ | 2 | Refactor | Convert core.py -> core/ package | git mv core.py -> core/__init__.py so core becomes a package (re-exports everything). Enables per-concern submodules. Behaviour-identical. | P2 | M | Done |  | Verified: import + 260-route fingerprint unchanged; live login smoke green. Shim retirement tracked as U8-02.9. | Epic 8 S2
U8-02.6 | core.py, shared/ | 2 | Refactor | Extract generic pure helpers (ids + json) -> shared/ | Move now_iso, new_id -> shared/ids.py and _extract_json -> shared/json_utils.py. core.py re-exports. Pure, dependency-free. | P1 | S | Done |  | Unit-tested: tests/test_epic8_s2_shared_helpers.py (8 tests). Route fingerprint 260 unchanged. | Epic 8 S2
U8-02.7 | core/ | 2 | Refactor | Extract pure permission logic -> core/permissions.py | Move user_perms, clean_perms, _BASE_PERMS, ROLE_DEFAULT_PERMS (pure RBAC resolution) into core/permissions.py; core re-exports. core/__init__ 612->537 lines. | P1 | M | Done |  | Unit-tested: tests/test_epic8_s2_permissions.py (12 tests, full precedence). Live auth smoke: 8 gated endpoints 200, no-auth 401. | Epic 8 S2
U8-02.9 | core/ | 2 | Cleanup | Retire compat shims | Rewrote 22 files (14 app + 8 test) from shim paths to real modules (services.ai.*, services.auth.*); deleted all 11 compat shims (top-level obj_store/brain_context/brain_rbac + 8 services/ stubs). | P2 | S | Done |  | Verified: fingerprint 260, all deferred-import targets resolve, 159 tests collect, zero leftover refs. Live: login->logout->revoked (200/200/401). | Epic 8 S2
U8-03.1 | server.py -> routers/ | 3 | Refactor | Workflows domain (4 endpoints) -> routers/workflows.py | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/workflows.py; fingerprint 260 + live smoke (GET/POST/DELETE 200). server.py 7333->7170 lines. | Epic 8 S3
U8-03.2 | server.py -> routers/ | 3 | Refactor | Tenant / settings domain (19: lexicon, operating-model, finance-cats, roles, ai-keys, ai-consent, usage, plan, owner-exclusions, invites, audit-log) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/tenant_settings.py (24 endpoints + 11 inline models + _slug_role). AI-gen helpers stay in server. Live: 6 GETs 200 + POST lexicon/regenerate AI 200. Fingerprint 260. server.py 6094->5484 (-610). | Epic 8 S3
U8-03.3 | server.py -> routers/ | 3 | Refactor | Contacts / CRM domain (6: list/create/update/delete + profile/rescore) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/contacts.py (4 CRUD + rename cascade). Live GET/POST/DELETE 200. Fingerprint 260. | Epic 8 S3
U8-03.4 | server.py -> routers/ | 3 | Refactor | Voice / capture-notes domain (6: voice-notes, transcribe, text, clarify) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/voice_notes.py (6 endpoints + ClarifyInput + ai_clarify_directive). Live: list 200, clarify AI 200. Fingerprint 260. | Epic 8 S3
U8-03.5 | server.py -> routers/ | 3 | Refactor | Meetings domain (4) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/meetings.py (4 endpoints). Fingerprint 260 + live GET 200 / 404. server.py 7170->7116. | Epic 8 S3
U8-03.6 | server.py -> routers/ | 3 | Refactor | Operating score + work coach (3) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/operating_score.py (operating-score + work-coach x2; scoring helpers stay in server). Live 200. Fingerprint 260. | Epic 8 S3
U8-03.7 | server.py -> routers/ | 3 | Refactor | Auth / OTP domain (4: otp request/verify, invite info/start) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/auth_otp.py (request/verify OTP + invite info/start + _mask_phone). OTP infra stays in server. Live: unknown phone/token 404 (no SMS). Fingerprint 260. | Epic 8 S3
U8-03.8 | server.py -> routers/ | 3 | Refactor | Brain search endpoint (1) -> fold into brain router | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/brain_search.py (2 helpers + search). Live GET 200 (needed import re). Fingerprint 260. | Epic 8 S3
U8-03.9 | server.py -> routers/ | 3 | Refactor | Dashboard endpoint (1) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/dashboard.py (daily-brief aggregate). Live 200 (run_followup + enrich_* + tenant pipelines). Fingerprint 260. | Epic 8 S3
U8-03.10 | server.py -> routers/ | 3 | Refactor | HR domain (5: complaints, memory, follow-up/run) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/complaints.py (complaints x3 + memory x2). Live GET 200. Fingerprint 260. | Epic 8 S3
U8-03.11 | server.py -> routers/ | 3 | Refactor | Files domain (4: upload, download, get, brochure) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Backlog |  |  | Epic 8 S3
U8-03.12 | server.py -> routers/ | 3 | Refactor | Finance / ingestion domain (10: ingest, invoices, payments) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/finance.py (9 endpoints + IngestCommitInput). AI-extract/commit engine stays in server; enrich_tasks + add_inbox_item imported. Live: invoices/payments/ingest + contact profile 200. Fingerprint 260. server.py 5484->5226. | Epic 8 S3
U8-03.13 | server.py -> routers/ | 3 | Refactor | Calendar + leave-approvers (2) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/calendar.py (business calendar + leave-approvers). Live GET /calendar 200. (Fixed an over-grab: end anchor now the next @api endpoint, not a far # --- comment.) Fingerprint 260. | Epic 8 S3
U8-03.14 | server.py -> routers/ | 3 | Refactor | WhatsApp domain (4: webhook verify/receive, status, logs) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Backlog |  |  | Epic 8 S3
U8-03.15 | server.py -> routers/ | 3 | Refactor | Captures domain (7: list, count, edit, reassign/reject/clarify/approve) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/captures.py (2 models + _get_draft + 7 endpoints). Fingerprint 260 + live GET 200. server.py 7116->6959. | Epic 8 S3
U8-03.16 | server.py -> routers/ | 3 | Refactor | Health / root (2) + retire the in-file api router | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Backlog |  |  | Epic 8 S3