## Cover
DecisionOS — Epic 2
UX · Redesign · CRM
Started | 2026-08-13
Predecessor | Epic 1 (DecisionOS_SaaS_Stability_Tracker.xlsx) — stability, RBAC, Brain, Workflow-Engine spec, live E2E findings
Epic 2 goal
Turn DecisionOS from a functionally-complete founder tool into a product founders enjoy opening. Epic 1 made it correct; Epic 2 makes it obvious. Every change here is a UX / information-architecture / redesign call — no new backend features unless they are directly required by a redesigned surface (e.g. CRM activity log).
Working principles
1. One page, one job. If a page tries to do two things (People = employees + contacts today), split it.
2. Every workflow-linked object shows its live stage from the Workflow Engine. No stale copies.
3. Founder-first, teammate-close-second. Owner navigation stays fastest; teammates get a clean scoped view.
4. No dead buttons. Every visible control fires an API + shows toast on success/error (kills the FUP-45/46/49 pattern for good).
5. Ship one page at a time. Full walk-through in the browser after each surface lands, screenshots in the Page Redesign Log sheet.
6. Nothing here duplicates Epic 1 open items. FUP-45/46/47/48/49/50/51 + WE-* sprint stay in Epic 1.
Sprint breakdown
Sprint 1 -- CRM & People split
Status | Shipping (Sprint A partial live)
Items | E2-01, E2-02, E2-03, E2-04, E2-05, E2-06, E2-07, E2-08, E2-09, E2-10
What | Split the old three-tab /contacts People page into two purposeful surfaces: /crm (customers + suppliers, relationship-first, workflow-engine-integrated) and /team (employees only, HR/admin). Build the CRM v1 shell with filter chips, search, card grid; wire the right-pane detail feed to the Workflow Engine (depends on WE-06); ship activity log, lifecycle stage, owner-per-relationship, tags.
Why | Founder ask 2026-08-13: 'separate the people section first because I wanted to create CRM for the supplier and customer -- not high-level, manage the details, scoped under our workflow engine.' Today the People page tries to do two jobs and the Add button changes meaning by tab. Splitting also unlocks role-specific perm defaults (sales can see CRM without seeing Team). Every workflow-linked row on the CRM detail will read its live stage from the Workflow Engine -- kills the FUP-48 class of stale-copy bug at the source. SHIPPED so far: /crm shell + /team page + /contacts redirect + PEOPLE bottom-nav slot renamed to CRM.
Sprint 2 -- Decision Desk redesign
Status | Backlog -- ideating
Items | E2-16, E2-17, E2-18, E2-19, E2-20, E2-21, E2-22
What | Rebuild /inbox as a decision-only surface with four chips exactly as the founder mocks show: Needs Your Decision, On Fire, Due Today, Important. Card anatomy matches the mocks (title + context line + amount + primary CTA). Ship a single /api/desk aggregation endpoint that replaces the three separate fetches (/inbox + /decisions + /tasks?mine=true). Migrate the 'Needs Your Attention' cards under the 'On Fire' chip with the reply composer preserved. Delete the mixed 'Tasks & Activity' feed, the classification chips row, and the mic/text/file capture UI from the Desk. Move capture to /ingest as its single home. Add a Nudge / Chase primary action that sends WhatsApp (fallback email) to the person we are waiting on. Ship an AI ranker for the Important chip.
Why | Founder ask 2026-08-14 with three annotated screenshots: the Decision Desk should surface only decisions the founder owes today -- nothing else. Today the /inbox page mixes a unified activity feed (invoices, payments, complaints, tasks, approvals, reminders) with capture UI and a Pending Approvals grid. Founder said 'I wanted to remove the task list from decision desk because I think we already have that in the work section' -- audit confirmed MyWork covers all task-management needs richer than the Desk feed; keeping tasks on the Desk is duplication that dilutes the founder's most important surface. Also 'we will have the approval of decision option here alone' -- the Desk earns its slot in the founder's cognitive map by being the single place for 'what decisions am I holding up?'. Consolidating capture at /ingest kills the 'two places to record a voice note' confusion. The 4-chip structure matches how a founder actually triages the day (urgent vs important vs today vs raised-to-me). Nudge/Chase turns a passive list into one-tap action -- one click sends the WhatsApp instead of 'I should follow up later'.
Sprint 3 -- Brief & Navigation polish
Status | Partial (E2-11 + E2-15 Done)
Items | E2-11 (Done), E2-12, E2-13, E2-14, E2-15 (Done)
What | Sharpen the surfaces the founder opens most. Remove the Operating Score shortcut from the CEO Brief header so the Brief stays a pure dashboard (E2-11, Done). Add Ops as a first-class owner-only sidebar entry pointing at /operating-score (E2-15, Done). Ship empty-state CTAs and skeleton loaders across every list page. Audit the bottom-nav ownership per role (founders and teammates open different tabs).
Why | Founder ask 2026-08-13: 'remove the operating score from the brief to new page.' The Brief header cards were competing with the KPI grid for attention. Operating Score deserves its own room. Also every list surface today shows 'Nothing here' on a fresh tenant with zero next-step CTA -- founders finish onboarding and land on empty dashboards not knowing where to start (retention-value fix). Skeleton loaders replace 'Loading...' text and stop layout jumping when data arrives.
Backlog columns
ID | E2-<n> ticket ID
Screen / Feature | Which page or feature this touches -- sort/filter by this to see all work on /inbox at once
Sprint | 1 / 2 / 3 (see blocks above)
Category | Info architecture / New page / Data model / Navigation / AI feature / Polish / Milestone / Backend
Title | Short imperative summary
Description | The what and why
Priority / Effort / Status | P1..P3 / XS..L / Backlog¦In Progress¦Done
Depends on | Prereq ticket IDs (e.g. WE-06 from the Workflow Engine sprint in Epic 1)
Notes / evidence | Live-test evidence, screenshot references, shipping notes
Source | Where the ask came from (founder ask, CRM Ideation, Sprint plan, etc.)

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends on | Notes / evidence | Source
E2-01 | /crm + /team + /contacts (retired) | 1 | Info architecture | Split People page — employees off, CRM concept opens | Today /contacts is one page with 3 tabs (Employees, Customers, Suppliers). Founder ask 2026-08-13: 'separate the people section first because I want to create CRM for the supplier and customer.' Employees is HR/admin, Customers + Suppliers are RELATIONSHIPS — different mental model, different frequency of use, different workflow-engine integration. Move Employees to /team (owner + team_manage only). Redirect /contacts to /crm. | P1 | S | Done |  | Depends on the CRM shell (E2-02) landing at /crm first. [2026-08-13 SHIPPED] /contacts route now redirects to /crm; TeamPage default export at pages/Team.js gives /team its own route. Both verified live in preview browser as amit (owner). | Founder ask 2026-08-13
E2-02 | /crm — shell (list + filter chips) | 1 | New page | CRM shell at /crm — list + detail layout, read-only v1 | Two-column shell: left = filterable relationship list, right = selected relationship 360° detail. See CRM Ideation sheet for the full spec. v1 reads existing contacts data (customer/dealer + vendor); write actions come in E2-05/06/07. | P1 | M | Done | E2-01 | Route: /crm (perm='people'). Copy the ContactsPanel filter logic, throw away the tab shell. Reuse ContactProfile logic for the right pane so we don't rebuild the 360°. [2026-08-13 SHIPPED] New pages/CRM.js shipped with unified list (All / Customers / Suppliers / Mine filter chips, search bar, status dropdown), Add Customer + Add Supplier buttons in header, card grid with type / status / tag chips + view / edit / delete / log-complaint actions, click-through to /contacts/:id (existing 360°). Right-pane detail deferred to Sprint B (needs workflow-engine feed WE-06). | Founder ask 2026-08-13
E2-03 | /crm — lifecycle-stage chip (data) | 1 | Data model | Add relationship lifecycle_stage field | Add contacts.lifecycle_stage. Enum differs by type: Customer = {lead, active, loyal, dormant, churned}; Supplier = {trial, active, preferred, strategic, blocked}. Renders as a stage chip on both the CRM list and detail. Read-only migration: default to 'active' for existing rows with any transactions, 'lead' for empty vendors, 'trial' for empty customers. | P1 | S | Backlog | E2-02 | Migrate via services/migrations.py ledger. Extend PATCH /contacts/:id to accept lifecycle_stage. Enum validation in the router. | CRM Ideation
E2-04 | /crm — owner_id per relationship (data) | 1 | Data model | Add owner_id (team-member owner) on each contact | Today contacts have assigned_id (single field, used loosely). Rename semantics: owner_id = the person responsible for this relationship. Renders as an avatar chip on every CRM list row + detail header. Dropdown to reassign. Filters at top of CRM list ('My relationships' toggle uses this). | P2 | S | Backlog | E2-02 | Read-only for finance/sales, editable by role owner or team_manage. Cascade rename lives at server.py:update_contact (see FIX-003-C pattern). | CRM Ideation
E2-05 | /crm — tags chips (data + UI) | 1 | Data model + UI | Free-form tags on relationships (chips) | Add contacts.tags[] (already exists, currently unused in UI). Show tag chips on CRM list row + detail. Add-tag affordance inline. Tag filter at top of the CRM list (multi-select). Suggestions from top-8 tags in tenant. | P2 | S | Backlog | E2-02 | Tag string sanity: lowercase, max 24 chars, trim. Cap at 15 tags per contact. | CRM Ideation
E2-06 | /crm + /team (Sprint A exit) | 1 | Milestone | Sprint A exit gate — CRM v1 shipped, People retired | End-of-Sprint-A verification. Both roles walked through: founder can browse Customers + Suppliers under /crm with lifecycle stage, owner, tags; /contacts redirects; /team shows only Employees. No regressions on ContactProfile 360° (still works, now navigated to from /crm). | P1 | S | Backlog | E2-01..E2-05 | Verify test coverage adjusted (test_iteration27 TestRBACContacts still asserts 403 for prod). Screenshot the new /crm surface into the Page Redesign Log sheet. | Sprint A
E2-07 | /crm — right-pane workflow feed | 1 | Workflow-Engine integration | Live workflow feed on CRM detail | Right pane of CRM detail shows every workflow linked to this contact_id with the LIVE stage read from workflow_engine (not the stale workflows.stage column). One row per workflow: pipeline label, counterparty, amount, current stage chip, days-in-stage, next-stage button (owner-only, same gate as workflow board). Depends on WE-06 landing so the engine is authoritative. | P1 | M | Backlog | E2-02, WE-06 | Reuse the workflow board's advance() call. Show a stale-warning chip if last_transition_at > 5 days. Order rows by most-recent-transition desc. | Founder ask 'scoped under workflow engine'
E2-08 | /crm — right-pane activity timeline | 1 | New feature | CRM activity log — call, meeting, note, WhatsApp | New crm_activities collection: {tenant_id, contact_id, kind (call¦meeting¦note¦whatsapp_sent¦whatsapp_received¦email_sent¦email_received¦complaint_raised¦task_added), body, actor_user_id, at, meta}. Renders as a timeline on the CRM detail. 'Log activity' modal on the detail header with kind toggle + free-text body. WhatsApp/email/complaint/task kinds are written automatically by existing handlers (server.py already fires those events). | P1 | M | Backlog | E2-02 | Extend brain_context.record_context to also write a crm_activity row when kind='decision' and decision has a contact_id link. Kills two birds — timeline stays populated without a separate write pass. | CRM Ideation
E2-09 | /contacts/:id — AI Relationship Intelligence (supplier) | 1 | AI feature | AI Relationship Intelligence for Suppliers (already on Customers) | ContactProfile.js already has AI Relationship Intelligence for Customers (relationship + risk scores, signals, reasons, next best actions). Extend to Suppliers: use purchase-history, payment terms, delay pattern, quality complaints. Model: prompt Claude with the last 20 invoices + payments + complaints + workflow transitions for that supplier and ask for 3 signals + 3 risks + 1 recommendation. Same UI card, different data model. | P2 | M | Backlog | E2-07 | Reuse services/ai/relationship.py (already exists for customers). Add a supplier prompt template. Cache per-contact for 24h to control cost. | CRM Ideation
E2-10 | Layout — bottom-nav rebalance (Brain? / Team? etc) | 1 | Navigation | Replace PEOPLE bottom-nav with CRM; add Team under Settings | Bottom-nav becomes: DESK / BRIEF / WORK / CRM / BRAIN. The Employees tab that used to live at /contacts moves under Settings > Team (owner + team_manage only). Founder rarely opens Team weekly, so it doesn't earn a bottom-nav slot. Keeps the 5-tab bottom-nav pattern; no icon count changes. | P1 | S | Backlog | E2-01, E2-02 | Layout.js:47 and :60 both need updating. Keep the perm gate on the CRM tab as 'people' (post-FIX-FUP-51 opt-in). | Sprint A
E2-11 | /brief — remove Operating Score card | 3 | Page redesign | Remove Operating Score card from CEOBrief header | Founder ask 2026-08-13: 'remove the operating score from the brief to new page.' CEOBrief.js:215-232 owner-only row had two side-by-side buttons (Operating Score, CEO Journal); removed Operating Score, promoted CEO Journal to full-width (col-span-2). /operating-score page unchanged — still lives at that URL. | P2 | XS | Done |  | Shipped 2026-08-13 in the same session as this epic created. Also removed unused Gauge icon import. Verified live in browser as amit (owner): brief header now shows only CEO JOURNAL button. | Founder ask 2026-08-13
E2-12 | Layout — per-role bottom-nav audit | 3 | Navigation | Bottom-nav ownership audit — which tab per role? | Today all users see the same 5 tabs (subject to perm gates). Founder-vs-teammate flows are different: teammates almost never open BRIEF, founders rarely open MyWork task cards. Audit each of the 5 tabs and decide the target set for each role. Might land as a 'primary tab' per role config, or as simple reordering. | P3 | S | Backlog | E2-10 | Read-only audit first — no changes. Then propose.
E2-13 | Across screens — empty states with CTA | 3 | Polish | First-run empty states with clear next action | Every list surface (My Work, Inbox activity feed, Workflow board, CRM list, Ledger tables) currently renders 'Nothing here' with no next action for a fresh tenant. Write a per-surface empty state with a specific CTA button (e.g. 'Add your first customer', 'Record your first decision in the Desk'). | P2 | M | Backlog |  | Blocks the moment a founder finishes onboarding — they land on empty dashboards and don't know where to start. High retention-value fix.
E2-14 | Across screens — skeleton loaders | 3 | Polish | Skeleton loaders instead of blank/'Loading...' text | Every page currently shows 'Loading brief...' or empty space during initial fetch. Replace with brutalist skeleton bars (KPI card outlines, table row outlines) so the layout stops jumping when data lands. Keeps the brand and reduces perceived latency. | P3 | S | Backlog |  | Reuse the existing skeleton component pattern from the brief details drill-down.
E2-15 | Layout — Ops nav entry → /operating-score | 1 | Navigation | Ops menu entry — owner-only shortcut to /operating-score | Founder ask 2026-08-13 same session: 'add the button called operation score in main menu.. we will name it Ops.' Added Ops entry to the main sidebar NAV in Layout.js (Gauge icon, ownerOnly, position 4 between My Work and CRM). Points to /operating-score. Non-owners don't see the item at all (filtered out by useMemo(NAV.filter)). Matches the pattern E2-11 established when we removed the Operating Score card from the CEO Brief header — the page still lives at /operating-score, just moved from a Brief shortcut to a first-class nav entry. | P1 | XS | Done | E2-11 | SHIPPED 2026-08-13. Verified live: hamburger drawer shows Decision Desk > CEO Brief > My Work > Ops > CRM > Team > Company Brain > Finance > Capture > Meeting Notes > Settings. nav-ops testid resolves to href=/operating-score. Hindi label 'ऑप्स', Tamil label 'இயக்கம்' added to i18n. | Founder ask 2026-08-13
E2-16 | /inbox -- 4-chip shell + counter subline | 2 | Info architecture | Rebuild Decision Desk as a decision-only 4-chip surface | Replace the current mixed /inbox page with the founder's mock design: header 'Decision Desk' + counter subline ('6 decisions waiting on you / 8 on fire / 3 due today'), four mutually-exclusive chip tabs (Needs Your Decision, On Fire, Due Today, Important), card grid using the anatomy from the mocks (title + context line + amount + primary CTA). No task-list, no mixed feed, no capture UI. Chips are backed by client-side filtering on the /api/desk response; sort per chip: Needs Your Decision by waiting-days desc, On Fire by overdue days desc, Due Today by amount desc, Important by AI score desc. | P1 | M | Backlog |  | Founder mocks 2026-08-14 (3 annotated screenshots). Card CTA copy per chip: Review / Respond / Chase / Nudge. Preserves ownerOnly gate on the Decision Approvals content -- non-owners see an empty 'Needs Your Decision' and still get 'On Fire' when they have escalations / handoffs. | Founder mocks 2026-08-14
E2-17 | Backend -- /api/desk?chip=... aggregation endpoint | 2 | Backend | One /api/desk endpoint returns {counters, cards[]} per chip | New endpoint replaces the three fetches the Desk does today (/inbox + /decisions + /tasks?mine=true). Query param 'chip' in {needs_decision, on_fire, due_today, important}. Response: {counters:{needs_decision:N, on_fire:N, due_today:N, important:N}, cards:[{id, title, context_line, amount?, cta:'review¦respond¦chase¦nudge', target_id, target_kind}]}. counters always returned so header subline can render without a second call. Tenant-scoped, user-scoped. | P1 | M | Backlog | E2-16 | Backend logic: needs_decision = decisions.status=pending AND approver_id=me OR (owner_id=me AND approver_id=null). on_fire = task escalations/handoffs to me UNION overdue tasks I own. due_today = due_date=today in my column. important = AI-ranked (services/ai/priorities.py decision variant, E2-21). | Ideation 2026-08-14
E2-18 | /inbox -- 'On Fire' chip content | 2 | Migration | Merge 'Needs Your Attention' cards into the On Fire chip | Today the escalations + handoffs 'Needs Your Attention' cards render as a standalone section on /inbox with typed inline reply. Fold them into the On Fire chip alongside overdue-I-own cards. Reply composer preserved -- 'Respond' button on escalation/handoff cards opens the same POST /tasks/{id}/respond flow. Chase button on overdue cards is the new one, wired via E2-22. | P1 | S | Backlog | E2-16, E2-17 | Card 'Respond' vs 'Chase' distinction: Respond = I owe someone a reply (they escalated/handed off to me). Chase = someone owes me completion (I own an overdue task). Two different verbs, same chip. | Founder mocks 2026-08-14 (On Fire chip screenshot)
E2-19 | /inbox -- delete legacy sections | 2 | Deletion | Delete task feed + classification chips + capture UI from Desk | Once E2-16/17/18 are green, delete: (a) the 'Tasks & Activity' unified feed and its SwipeRow component, (b) the classification chips row (customer/supplier/invoice/payment/complaint/task/approval/reminder), (c) the mic/text/file capture UI. All three duplicate or dilute what MyWork + /ingest already do. Also delete the 'Structuring' sticky banner and the pre-submit AI clarify Q&A -- those move to /ingest with the capture UI (E2-20). | P1 | S | Backlog | E2-16, E2-17, E2-18, E2-20 | Deep-link safety: nothing in the codebase links '?task=' or '?focus=task:...' into the Desk. CEO Brief routes task notifications to /my-work?task=... (see CEOBrief.js:81, lib/notif.js:19). Zero deep-links break. | Founder ask 2026-08-14 'we will have the approval of decision option here alone'
E2-20 | /ingest -- capture UX consolidated | 2 | Migration | Move mic/text/file capture from Desk to /ingest | /ingest already has upload capabilities. Add the Desk's mic recorder (pause/resume/finalise/cancel, language auto-detect), text directive box (with pre-submit AI clarify Q&A), and file/photo drop as first-class Import tabs on the /ingest page. Preserves 'Analyse & structure' wording. Voice-notes POST endpoint stays the same. | P1 | M | Backlog |  | Can ship before E2-19; E2-19 depends on this landing so users don't lose the capture affordance. Nav 'Capture' item already points at /ingest -- no nav change needed. | Ideation 2026-08-14
E2-21 | /inbox -- 'Important' chip AI ranking | 2 | AI feature | Extend services/ai/priorities.py for decision-level ranking | The 'Important' chip is meaningless without an AI ranker. Extend the existing services/ai/priorities.py (already scores tasks for MyWork AI-Priority) with a decision-level model that surfaces 'not urgent yet but worth your attention'. Signals: high monetary amount, strategic keyword match, pattern from prior founder-approved decisions (via brain_context), days since raised without action. Cache per tenant per user for 15 minutes. | P2 | M | Backlog | E2-16, E2-17 | Uses the same LLM call pattern as MyWork AI-Priority. Fail-open: if the model call errors, Important chip returns empty (0) -- matches the founder mock where it shows 0. | Founder mocks 2026-08-14 ('Important 0' chip)
E2-22 | /inbox -- decision card Nudge/Chase actions | 2 | New feature | Nudge / Chase button -> WhatsApp (fallback email) counterparty | New POST /api/desk/nudge/{item_id} sends a WhatsApp template to the person we're waiting on (from the item's target owner / counterparty). Falls back to email if WhatsApp isn't configured. Two copy variants: 'Nudge' for Due Today items ('hi, this is due today, when can you get it done?'), 'Chase' for overdue items ('hi, this was due N days ago, please prioritise'). One-tap action; success toast with 'Sent via WhatsApp' or 'Sent via email'. Logs to crm_activities (E2-08 collection, once landed). | P1 | M | Backlog | E2-16, E2-17 | Wraps existing services/whatsapp.py send helper. For decisions, targets the person who raised it (from field). For overdue tasks, targets the current assignee. If neither has a phone number, button shows disabled tooltip 'No contact channel'. | Founder mocks 2026-08-14 (Nudge / Chase CTAs)

## CRM Ideation
CRM redesign — detailed spec, scoped under Workflow Engine
Founder ask 2026-08-13: 'not high-level — should be under scope, manage the details, and scope under our workflow engine.'
Why a dedicated CRM (not just 3 tabs on People)
• | Employees is HR/admin (add member, invite, mark absent, edit access). Weekly-cadence tool for owner + team_manage only.
• | Customers + Suppliers are relationships. Daily-cadence tool for sales, finance, and owner. Different data, different workflows, different mental model.
• | The current People page fights itself — the 'Add' button means invite-user vs add-contact depending on which tab you're on. Two mental models on one screen.
• | Splitting also unlocks role-specific perm defaults: 'sales' can see /crm without being able to see /team, and vice versa.
What lives at /crm — the shell
• | Two-column layout on desktop; single-column stack on mobile with a back button in the detail view.
• | Left column (280px on desktop): filter chips (All / Customers / Suppliers / My relationships), search bar (name, phone, GSTIN), lifecycle-stage filter chips, tag multi-select, sort menu (last activity / outstanding amount / name).
• | Left column rows: avatar (initial), name + company, type chip (Customer / Supplier), lifecycle-stage chip, owner avatar, outstanding-amount chip if > 0, days-since-last-activity if > 14.
• | Right column: selected relationship 360° detail. See section below.
• | Empty state (no contacts yet): 'Add your first customer' + 'Add your first supplier' CTAs — same buttons ContactsPanel has today.
Right-pane detail — the sections
• | 1. Header — name, company, avatar, type chip, lifecycle-stage chip (editable), owner avatar (editable), tags (editable), quick-actions row (Log activity / New workflow / Send WhatsApp / Add task).
• | 2. Financial summary — outstanding, total billed, total paid, credit limit, average days-to-pay (customer only) or average payment-punctuality (supplier only). Reuses ContactProfile.js summary tiles.
• | 3. LIVE workflow feed — every workflow keyed on contact_id. Rows show pipeline label + current stage chip (read from workflow_engine, not stale workflows.stage), amount, days-in-stage, and a next-stage advance button (owner or workflows-perm holder only). See E2-07.
• | 4. Activity timeline — merged chronological feed of: workflow transitions, tasks added/completed, payments received, invoices raised, complaints, communication logs (call/meeting/note/whatsapp/email). Colour-coded by kind. Filter chips at top. See E2-08.
• | 5. AI Relationship Intelligence — same card ContactProfile has for customers today. Extended to suppliers in E2-09. Score + top 3 signals + top 3 risks + 1 next-best-action.
• | 6. Documents — quotes, contracts, POs, delivery notes linked to this contact. Feeds Brain Documents. Uploadable inline.
• | 7. Tasks — open tasks with this contact in the title or referenced via contact_id. Reuses task card component.
• | 8. Complaints (customer only) — list of complaints with resolve-inline. Same widget as CEOBrief drill-down.
How this is 'scoped under the Workflow Engine'
• | Every workflow-linked object on the detail (feed rows, timeline entries) reads its stage from workflow_engine.get_stage(workflow_id), NEVER from a denormalised copy. Kills the FUP-48 class of bug at the source — no CRM row can show 'confirmed' while the engine says 'in_production'.
• | 'New workflow' from the CRM detail spawns via workflow_engine.create(pipeline_key, contact_id, amount). All stage advance calls from the CRM feed go through the same engine call. Same audit-trail, same idempotency, same side-effects framework (WE-08).
• | Activity timeline pulls workflow transitions from workflow_engine.transitions(contact_id) — no separate audit-log query. One source of truth.
• | Blocks E2-07 on WE-06 landing. Everything else in Sprint A ships without the engine dependency — v1 CRM shell is workflow-engine-agnostic; the engine hookup is Sprint B.
Data-model deltas (small)
• | contacts.lifecycle_stage — new enum field, migrated per E2-03.
• | contacts.owner_id — rename semantics on the existing assigned_id (see E2-04). No schema break; just a fresh alias with cleaner API/UI language.
• | contacts.tags[] — already exists on the model, currently unused in UI. Wire it up (E2-05).
• | crm_activities — new collection (E2-08). Fields: id, tenant_id, contact_id, kind, body, actor_user_id, at, meta.
• | Index: contacts.(tenant_id, type, lifecycle_stage). Index: crm_activities.(tenant_id, contact_id, at desc).
RBAC on /crm (post FIX-FUP-51)
• | Read (/crm list + detail): perm='people'. Founder grants sales + finance explicitly via Settings > Roles.
• | Write (add/edit/delete contact): role in {owner, sales} — unchanged from today.
• | AI Relationship Intelligence card (score-with-AI, rescore): perm='finance' — unchanged from today.
• | Log activity (call/meeting/note): any user with 'people' AND with an owner_id assignment on the contact — keeps the writes attributable.
• | Advance workflow from CRM feed: perm='workflows' OR role=owner.
• | Add to Team (Employees) surface: role=owner or perm='team_manage' only, and lives at /team (not on /crm).
What v1 is NOT
• | Not a general-purpose sales pipeline (kanban of leads through stages). Founders can build that later using workflows if they want; the CRM is a relationship-book not a deal-tracker.
• | Not a marketing tool. No campaigns, no bulk-email, no segments-with-triggers.
• | Not integrated with Zoho/Salesforce/HubSpot. If the founder wants Zoho sync it comes later as a distinct import feature.
• | Not multi-currency per contact. Currency is tenant-wide via Settings > Money & Approvals.
Success signals for the v1 shipped surface
• | Founder opens /crm daily instead of /contacts weekly.
• | Every relationship has a lifecycle_stage set within the first week of use.
• | Every high-value relationship (outstanding > threshold) has an owner_id set within the first week.
• | Activity timeline has 5+ non-auto entries per active relationship within a month.
• | AI Relationship Intelligence rescore triggered by founder at least once per relationship per quarter.

## Page Redesign Log
Date | Ticket | Page | What changed | Before | After | Screenshot | Commit
2026-08-13 | E2-11 | CEO Brief (/brief) | Removed the 'Operating Score' shortcut button from the owner-only controls row. Promoted 'CEO Journal' to full-width. Also removed the unused Gauge icon import. | Two side-by-side buttons in the header: Operating Score ¦ CEO Journal | Single full-width button in the header: CEO Journal. /operating-score URL unchanged. | verified live in preview browser as amit@kapoormills.co.in | (next commit)
2026-08-13 | E2-01/02/15 | People (retired) -> /crm + /team + Ops nav | Split the old 3-tab People page into a dedicated CRM (customers + suppliers only, at /crm) and a Team page (employees only, at /team). /contacts URL redirects to /crm. Bottom-nav PEOPLE slot renamed to CRM; sidebar drawer gains Team + Ops entries. Ops is owner-only and points at /operating-score. | One /contacts page with three tabs (Employees / Customers / Suppliers). Employees tab required team_manage; add-button meaning changed by tab. Operating Score reachable only from CEO Brief header shortcut (removed in E2-11). | /crm two-column-ready shell with filter chips (All / Customers / Suppliers / Mine), search, status filter, tag chips per card. /team is the pure Employees page with ADD MEMBER, access editor, invite links. Ops sits as its own owner-only sidebar item. | Verified live in preview browser as amit@kapoormills.co.in: CRM shows Delhi Retail Corp under Customers, Rajesh Cotton Traders under Suppliers, and clicking Ops takes you to /operating-score. Bottom-nav is DESK / BRIEF / WORK / CRM / BRAIN. | (next commit)