## Cover
DecisionOS
Epic 11 -- Requests (new feature)
Kickoff | 2026-10-21. Web first; the native app's own polish and Phase 3 come after.
Origin | The client's Requests plan (DecisionOS_Dossier/feature-plans/Requests_Feature_Plan.png) and its decisions of 2026-10-21: the requester picks who approves (reporting manager by default, or the owner) with no amount rule; approval creates the expense in Finance; seven types; many items per request. Founder 2026-10-21: a General request is not financial - approval closes it.
Epic 11 goal | A bottom-up ask that needs a yes and then fulfilment - not a task (work to do) and not a decision (a directive from above). Raised in seconds, decided where approvals already live, paid by Finance without typing the expense again.
Current state | Web build shipped to karma-redesign in 58ce262: backend rules + HTTP surface, expense on approval, paid closes it, stock in, notifications, and the screens (My Work +, New Request, card, /requests, Approvals tab, Desk card, phone More tile). Checked in the browser on a scratch database.
Working principles | 1. The server holds every rule - screens show what its can-flags allow. 2. Every state change is an atomic claim. 3. Built in the app's design system (components/neuglass). 4. Someone is told at every step. 5. docs/REQUESTS_PLAN.md is the build plan.
Note on backlog | Moved from Epic 6 Sprint 26 on 2026-10-21 at the founder's ask, IDs renumbered U7-26.x -> RQ-s.n (each row's Notes names its old ID; commit 58ce262 cites Epic 6 Sprint 26).
Sprint breakdown
Sprint 1 -- Backend: rules, money, notifications
Files | services/staff_requests.py, routers/staff_requests.py, models/staff_requests.py, routers/ledger.py, tests/test_staff_requests.py
Why | Seven types; the approver is the requester's choice (reporting manager by default, or the owner; no amount rule); approval books the expense in Finance in the company's own category words; Finance marks it paid and purchases go into stock; paying the expense in Finance closes the request; a General request is a yes, not money. Every state change an atomic claim. 34 tests.
Status | Done
Sprint 2 -- Web: the screens, in the design system
Files | components/requests/*, pages/Requests.js, pages/MyWork.js, pages/Tasks.js, pages/Desk.js, lib/requests.js
Why | My Work's + asks New task or New request; New Request form; request card with timeline and the actions the server allows; /requests (Mine / To approve / To pay / All); My requests in My Work; Approvals hub Requests tab; Desk card; phone More tile; notification links.
Status | Done
Sprint 3 -- Phase 3 (later)
Files | services/voice.py, services/ingestion.py, reports, services/whatsapp.py
Why | Raise by voice through Dex, reimbursement read from a bill photo, spend reports, WhatsApp. Not in the web build - per the client plan.
Status | Backlog

## Dashboard
DecisionOS - Epic 11 - Requests (new feature)
Employees ask for what they need - material, money or equipment - in one request with one or many items; their reporting manager (default) or the owner says yes; approval books the expense in Finance.
Epic 11 progress: 14 of 18 items Done (78%). Web build shipped 58ce262 (2026-10-21). Moved here from Epic 6 Sprint 26 the same day: a new feature gets its own epic. Open: Phase 3 only.
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 1 | Backend: rules, money, notifications | 8 | 8 | 100% | COMPLETE | Seven types; the approver is the requester's choice (reporting manager by default, or the owner; no amount rule); approval books the expense in Finance in the company's own category words; Finance marks it paid and purchases go into stock; paying the expense in Finance closes the request; a General request is a yes, not money. Every state change an atomic claim. 34 tests.
Sprint 2 | Web: the screens, in the design system | 6 | 6 | 100% | COMPLETE | My Work's + asks New task or New request; New Request form; request card with timeline and the actions the server allows; /requests (Mine / To approve / To pay / All); My requests in My Work; Approvals hub Requests tab; Desk card; phone More tile; notification links.
Sprint 3 | Phase 3 (later) | 0 | 4 | 0% | Backlog | Raise by voice through Dex, reimbursement read from a bill photo, spend reports, WhatsApp. Not in the web build - per the client plan.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
RQ-1.1 | services/staff_requests.py, models/staff_requests.py | 1 | Requests | The rules: seven types, approver choice, who may read / decide / fulfil | Types (Purchase & materials, Expense reimbursement, Advance, Travel, Equipment & assets, Repairs & services, General) with their expense-category hint; approver = the requester's choice, reporting manager by default or the owner, no amount rule; no manager falls to the owner and says so; an owner's own request is recorded approved. Access: requester, approver or delegate, owner, Finance once approved; everyone else 404. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.1 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.2 | routers/staff_requests.py | 1 | Requests | The HTTP surface, every state change an atomic claim | GET /api/requests?view=mine¦approvals¦fulfil¦all, GET approver-options, GET one; POST create, approve, reject (reason required), request-info, respond, withdraw, fulfil. Each update names the status it moves from, so two Approves make one approval and one expense; REQ-0001 numbering is one atomic increment per company with a unique index behind it. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.2 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.3 | routers/staff_requests.py _book_expense, routers/ledger.py create_expense | 1 | Requests / Finance | Approval books the expense in Finance | create_expense(source='request', request_id); the category is found in the company's own words (Raw Materials, Machine Maintenance) before the keyword guess; equipment books Asset Purchase so the asset register gets it; a reimbursement names the employee as payee. A failed booking keeps the approval and says so on the request. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.3 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.4 | routers/staff_requests.py fulfil, routers/ledger.py update_expense / delete_expense | 1 | Requests / Finance | Finance closes it: paid, and purchases into stock | Mark paid marks the booked expense paid and can put purchase items with a quantity into inventory (unit cost = line amount / quantity). Paying the expense in Finance closes the request on its own; deleting it unlinks the request and says why. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.4 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.5 | services/notifications.py, routers/staff_requests.py | 1 | Requests | Told at every step | Approver (and delegates) on a new request and an answer; requester on approve / reject / question / done; Finance and owners when something is approved to pay; approver when a request is withdrawn. Push titles: Request declined, Request withdrawn. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.5 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.6 | bootstrap/routing.py, bootstrap/lifecycle.py, services/tenant_wipe.py, routers/pulse.py, routers/files.py | 1 | Requests | Wired in on day one | Router registered; indexes (tenant+created, requester, approver+status, status, unique number); 'requests' in the tenant wipe list; pulse watches it; a bill attached to a request opens for whoever may open the request; read-gate inventory and API-parity baseline (+10 routes) updated. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.6 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.7 | tests/test_staff_requests.py, tests/fake_mongo.py | 1 | Requests | 31 tests: routing, access, money, ask-back, attachments | Manager default / owner choice / no-manager fallback, numbering per company, validation, owner auto-record; access 404s, no self-approval, owner and delegate decide; one expense under two simultaneous approvals, failed booking keeps the yes, company categories, equipment asset, reimbursement payee, fulfil -> paid + stock, expense paid -> request done, delete unlinks; reject needs a reason, question/answer, withdraw rules; own-files-only attachments. FakeDB gains $push and find_one_and_update. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.7 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-1.8 | services/staff_requests.py goes_to_finance, routers/staff_requests.py, components/requests/* | 1 | Requests | A General request is a yes, not money | Yokesh 2026-10-21: General is not financial. No amount on the form (any sent are dropped); approval closes it - no expense booked, Finance not told, never in To pay and cannot open it, Mark paid refused (409). The card reads 'Approved' and sits with the closed ones; the owner's own General request is recorded with no money. 3 tests. | P0 | S | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.18 (Epic 6 Sprint 26). | Founder 2026-10-21
RQ-2.1 | components/requests/NewWorkMenu.jsx, pages/MyWork.js, pages/Tasks.js | 2 | My Work | The + asks: New task or New request | My Work's + (phone circle and desktop '+ New') opens a glass menu with the two choices, the CRM add-menu pattern. NewTaskDialog gains a controlled mode (open / hideTrigger) so the menu can open it. | P0 | S | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.8 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-2.2 | components/requests/NewRequestDialog.jsx, lib/requests.js | 2 | Requests | New request form | Type chips; many items with quantity / unit / amount and a live total; needed-by date; bill or photo attached; why it is needed; Send to: reporting manager (default) or owner, with the no-manager and owner-records-it cases said up front. Words kept as a draft. Same sheet shape as New Task. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.9 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-2.3 | components/requests/RequestCard.jsx | 2 | Requests | The request card | Status and type chips, number, total, items, reason, files, question and answer together, reject reason, where the money is (in Finance / paid / in stock / why not), history timeline; Approve / Reject / Ask, Send answer, Withdraw and Mark paid shown from the server's can-flags. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.10 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-2.4 | pages/Requests.js, components/requests/RequestsPanel.jsx, pages/MyWork.js | 2 | Requests / My Work | Requests page and My requests in My Work | /requests: Mine, To approve, To pay, All (owner), summary, ?tab= and ?request= deep links. My Work gets a 'My requests' view (phone view picker and desktop segment) with its own + New. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.11 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-2.5 | pages/MyWork.js approvals hub, pages/Desk.js | 2 | Approvals / Desk | Approvals hub Requests tab and a Desk card | Approvals gets a Requests tab beside Tasks and Leave, counted in the number on the way in; the Desk's Watch column shows a Requests card when something waits on you. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.12 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-2.6 | components/mobile/AllAppsPanel.jsx, lib/notif.js, hooks/usePulse.js, App.js | 2 | Requests | Phone More tile, notification links, live refresh | More -> Requests; a request notification opens the approver's queue, Finance's list to pay or the requester's own list on the card; pulse refreshes requests, the Desk and expenses. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was U7-26.13 (Epic 6 Sprint 26). | Client plan 2026-10-21
RQ-3.1 | services/voice.py, Dex | 3 | Requests | Raise a request by voice through Dex | Phase 3. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.14. | Client plan 2026-10-21
RQ-3.2 | services/ingestion.py | 3 | Requests | Reimbursement read from a bill photo | Phase 3: fill the items and amount from the photographed bill. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.15. | Client plan 2026-10-21
RQ-3.3 | reports | 3 | Requests | Spend reports from requests | Phase 3: who asked for what, approved and paid, by type and month. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.16. | Client plan 2026-10-21
RQ-3.4 | services/whatsapp.py | 3 | Requests | Requests on WhatsApp | Phase 3: raise and approve from WhatsApp. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.17. | Client plan 2026-10-21