## Dashboard
DecisionOS - Epic 4 - Workflow Engine
Turn workflows from data blobs into a proper engine. Kickoff: 2026-08-16.
Epic 4 progress: 18 of 18 items Done (100.0%)
Sprint | Sprint / Epic name | Done | Total | % | Status | Theme
Sprint 1 | Phase 1 - Data model | 6 | 6 | 100% | COMPLETE | Tasks carry workflow_id + stage_key; pipelines become structured objects; ghost collections retired; Settings redesign lands. Ends with exit gate WE-05.
Sprint 2 | Phase 2 - Backend engine | 5 | 5 | 100% | COMPLETE | services/workflow_engine.py with on_stage_enter + check_stage_ready + advance. Single-writer contract, side-effects framework, idempotency + concurrency safety. Ends with exit gate WE-10.
Sprint 3 | Phase 3 - UI | 4 | 4 | 100% | COMPLETE | Stage chips on every task in My Work, inline workflow board with assignee avatars, manual-advance reason prompt with audit entry, retire the Board sub-tab.
Sprint 4 | Cross-cutting - Tests | 3 | 3 | 100% | COMPLETE | E2E golden path (Kapoor Retail / Delhi Retail scenarios) + full regression + rollback docs per phase.

## Moving to Next Epic
Moving to Next Epic - parked items
Items scoped in Epic 4 but deferred. Empty at kickoff.
ID | Origin sprint | Title | Status | Why parked | Decision needed

## Cover
DecisionOS
Epic 4 - Workflow Engine
Kickoff | 2026-08-16 (Epic 1 split)
Origin | Imported from Epic 1 Stability tracker on 2026-08-16 per founder ask 'park WE-* to Epic 4'.
Epic 4 goal
Ship the Workflow Engine that Epic 1 scoped but never built. Today workflows.stage is written by many callers with no shared contract; this epic centralises it in services/workflow_engine.py with on_stage_enter / check_stage_ready / advance hooks, adds structured stage objects, and gives every task a first-class workflow_id + stage_key so 'Order #4821 . Confirmed' can show up on every task card. 4 phases with exit gates.
Working principles | 1. Single-writer contract - only services/workflow_engine.py writes workflows.stage. All other paths delegate via advance(). 2. Each phase ends with an exit gate that proves behaviour unchanged / engine green / UI regressions clear. 3. Backfill migrations run via services/migrations.py ledger. 4. Same tracker discipline as Epic 2 -- side-by-side updates, Dashboard reflects reality, 'Moving to Next Epic' is the discipline for anything that needs more thought.
Sprint breakdown
Sprint 1 -- Phase 1 - Data model
Status | COMPLETE (WE-05 gate passed 2026-08-16)
Items | WE-01, WE-02, WE-03, WE-04, WE-05, WE-01.5
Why | Tasks carry workflow_id + stage_key; pipelines become structured objects; ghost collections retired; Settings redesign lands. Ends with exit gate WE-05.
Sprint 2 -- Phase 2 - Backend engine
Status | COMPLETE (WE-10 gate passed 2026-08-16)
Items | WE-06, WE-07, WE-08, WE-09, WE-10
Why | services/workflow_engine.py with on_stage_enter + check_stage_ready + advance. Single-writer contract, side-effects framework, idempotency + concurrency safety. Ends with exit gate WE-10.
Sprint 3 -- Phase 3 - UI
Status | COMPLETE (WE-11..14 shipped 2026-08-16)
Items | WE-11, WE-12, WE-13, WE-14
Why | Stage chips on every task in My Work, inline workflow board with assignee avatars, manual-advance reason prompt with audit entry, retire the Board sub-tab.
Sprint 4 -- Cross-cutting - Tests
Status | COMPLETE (WE-15/16 shipped 2026-08-16)
Items | WE-15, WE-16, WE-EPIC5-BUG-3
Why | E2E golden path (Kapoor Retail / Delhi Retail scenarios) + full regression + rollback docs per phase.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends on | Notes / evidence | Source
WE-01 |  | 1 | Data model (Phase 1) | Add tasks.workflow_id + stage_key + backfill migration | Every task gets first-class fields tying it to its parent workflow card + the specific stage that owns it. Backfill runs once via the migration ledger, keyed on decision_id when a matching workflow exists. Tasks with no parent workflow keep both fields null and continue to work as ad-hoc tasks. | P1 | M | Done |  | Imported from Epic 1 WE-01 (sprint: Workflow as Engine). Foundational — unlocks WE-06..WE-09 (the engine needs to read these). See Spec deck slide 9 (data model table). ¦ Shipped 2026-08-16 (commit follows). Migration backfill_task_workflow_link_v1 applied (scanned=10, matched=1). 6 pytest + 11 integration scenarios green. Compound index tasks_tenant_workflow_stage created. | Epic 1 split 2026-08-16
WE-02 |  | 1 | Data model (Phase 1) | Drop the ghost collections (workflow_templates + lexicon.workflows) | tenant.workflow_templates is a dead brainstorm list; lexicon.workflows is three hardcoded labels. Both cause the 'three cards, three shapes, one concept' Settings confusion the founder sees today. Migration removes them cleanly. No reader depends on either post-refactor. | P2 | S | Done |  | Imported from Epic 1 WE-02 (sprint: Workflow as Engine). Enables WE-04 Settings redesign. Idempotent via migration ledger. ¦ Shipped 2026-08-16 (commit follows). Migration drop_ghost_workflow_collections_v1 applied (workflow_templates unset on 1 tenant, lexicon.workflows unset on 2 tenants). Backend: removed writes in auth.py + onboarding.py + DEFAULT_LEXICON.workflows + _bp_workflows + os_summary count. Frontend: removed lex() merge + BusinessVocabulary Workflow Pipelines section + CompanyDetails Workflows editor. Legacy client PATCH still returns 200 (silent-drop). Updated tests test_iteration44 + test_iteration45; existing WE-01 + WE-03 pytest still 13/13 green. | Epic 1 split 2026-08-16
WE-03 |  | 1 | Data model (Phase 1) | Convert pipelines[].stages[] from strings to structured objects | Each stage becomes {key, label, tasks:[{title, role, evidence_required}], approval:{role, required}, side_effects:[...]}. Old flat-string entries auto-convert to the object shape with empty tasks + null approval so existing tenants' behaviour is preserved verbatim until owners edit in their stage templates. | P1 | M | Done |  | Imported from Epic 1 WE-03 (sprint: Workflow as Engine). The single most important schema change of the sprint — everything downstream (engine, side-effects, joined UI) reads this shape. ¦ Shipped 2026-08-16 (commit follows). Migration stage_objects_extend_v1 applied to 2/2 tenants. 7/7 pytest in tests/test_we03_stage_objects.py. | Epic 1 split 2026-08-16
WE-04 |  | 1 | UI (Phase 1) | Settings redesign: 8 scattered cards → 4 tabs (Business / Operations / Money / Account) | Kills the 'three cards, three shapes, one concept' confusion by collapsing Settings into a tabbed interface with Operations as the ONE place workflow config lives. Each pipeline shows its stages inline, each stage shows its task templates + approval rule. Add-task-template is an inline row on the stage. | P1 | M | Done |  | Imported from Epic 1 WE-04 (sprint: Workflow as Engine). Depends on WE-03 (stage-object shape). See Spec deck slide 12. ¦ Shipped 2026-08-16 (commit follows). Settings.js is now a 4-tab layout: Business / Operations / Money / Account. OperatingModelEditor extended with inline stage task templates (title + role + evidence_required), stage approval gate (role dropdown + required toggle), and read-only side-effect chips. Verified E2E in browser as Kapoor Cotton Mills owner: all 4 tabs render + activate; added a task template + set approval on the Production pipeline, saved, DB round-trip confirmed via direct query. | Epic 1 split 2026-08-16
WE-05 |  | 1 | Testing (Phase 1) | Phase 1 exit gate — behaviour unchanged, 553 baseline green | Full pytest suite green. Zero behaviour diff for existing tenants who don't touch Settings. Ghost collections gone (no reader errors). Both migrations idempotent + replica-restart-safe. 4-tab Settings functional. | P1 | S | Done |  | Imported from Epic 1 WE-05 (sprint: Workflow as Engine). See Testing Plan deck slide 4 (Phase 1 exit gate). ¦ PASSED 2026-08-16. Gate results: (1) 71/71 targeted regression pytest green (WE-01 + WE-03 + operating_model + lexicon + workflow_finance_link + workflows_dynamic + migrations_ledger). (2) All 3 Sprint 1 migrations idempotent on second boot -- no 'Migration applied' log lines, ledger has exactly one row per migration with original applied_at timestamps. (3) Ghost collections stay gone: 0 tenants with workflow_templates, 0 with lexicon.workflows. (4) WE-03 stage extension holds: 44 stages have all 3 new fields (tasks[], approval, side_effects[]), 0 missing. (5) All 4 indexes present (tasks compound + billing/crm/invoices audit indexes). (6) Workflows page for Kapoor Cotton Mills renders 2 cards, 4 stage columns, 3 pipeline tabs -- zero behaviour diff for existing tenants. (7) 4-tab Settings functional (verified in WE-04). Backend /api/health 200 post-restart. | Epic 1 split 2026-08-16
WE-06 |  | 2 | Backend engine (Phase 2) | services/workflow_engine.py — on_stage_enter + check_stage_ready + advance | The three transition operations. on_stage_enter spawns the stage's template tasks for the named roles, records a timeline entry, dispatches notifications. check_stage_ready returns true only when every stage task is done AND every required approval is present. advance runs the check, transitions on pass, re-enters on_stage_enter for the next stage (chained). Terminal stage fires side-effects + marks card done. | P1 | L | Done |  | Imported from Epic 1 WE-06 (sprint: Workflow as Engine). The core of the sprint. See Spec deck slide 10 (function table). ¦ Shipped 2026-08-16. services/workflow_engine.py with on_stage_enter + check_stage_ready + advance. 13/13 engine scenarios PASS (task-open refusal, ready-then-succeed, override+reason, override-missing-reason, atomic CAS race, on-enter idempotent, side-effect idempotent, notify no-recipients, approval gate, approval role check, terminal completed_at, skip-stage rejected, registered kinds). | Epic 1 split 2026-08-16
WE-07 |  | 2 | Backend engine (Phase 2) | Single-writer contract — only engine writes workflows.stage | Contract test scans every writer in the codebase; only the engine may mutate workflows.stage. Manual advance from the UI STILL exists but routes through engine with override=true + a required 'reason' string that lands in audit_log. Kills the 'silent kanban drag' problem identified in the spec. | P1 | M | Done |  | Imported from Epic 1 WE-07 (sprint: Workflow as Engine). Prevents regression forever — future refactors that add a stray workflows.update_one({stage:...}) fail the contract test at CI. ¦ Shipped 2026-08-16. advance_workflow endpoint + decisions.approve auto-advance both delegate through engine.advance. tests/test_we07_single_writer_contract.py greenlists services/workflow_engine.py + server.py initial-insert sites only; grep-scan fails CI if any other file mutates workflows.stage. | Epic 1 split 2026-08-16
WE-08 |  | 2 | Backend engine (Phase 2) | Side-effects framework — entry/exit hooks per stage | The procurement-terminal → awaiting-bill expense we already have (FIX-001-B) generalises to any stage. side_effects[] on the stage object declares hooks; engine invokes them on enter/exit. Registry of built-in hooks: create_expense, notify_role, post_to_slack. Extensible for tenant-specific hooks later. | P1 | M | Done |  | Imported from Epic 1 WE-08 (sprint: Workflow as Engine). Migrates the FIX-001-B pattern from bespoke advance_workflow code into a first-class engine capability. Every future 'when stage X, do Y' request land ¦ Shipped 2026-08-16. Side-effects registry with create_expense + notify_role kinds. FIX-001-B ported into _side_effect_create_expense (idempotent per workflow_id). Migration backfill_procurement_side_effect_v1 bound the create_expense kind to every existing procurement pipeline's terminal stage (scanned=2, touched=2). Zero behaviour diff for existing tenants. | Epic 1 split 2026-08-16
WE-09 |  | 2 | Backend engine (Phase 2) | Idempotency + concurrency safety | Calling advance twice on a satisfied stage doesn't double-spawn tasks or skip a stage. Two tasks closing near-simultaneously trigger EXACTLY ONE transition — no double-advance, no lost update. Mongo-level guard via findAndModify + a stage_version field. | P1 | M | Done |  | Imported from Epic 1 WE-09 (sprint: Workflow as Engine). Prevents the two hardest-to-diagnose classes of workflow bugs. Regression tests in Testing Plan deck slide 6. ¦ Shipped 2026-08-16. workflows.stage_version optimistic-lock counter. engine.advance uses find_one_and_update on (id, stage_version, current_stage) so concurrent writers race safely -- exactly one wins, the other exits with already_advanced=True. Migration backfill_stage_version_v1 initialised 13 workflows to stage_version=0. Verified live via scenario 5 (asyncio.gather of two advances -> 1 winner + 1 loser). | Epic 1 split 2026-08-16
WE-10 |  | 2 | Testing (Phase 2) | Phase 2 exit gate — engine unit + integration green, contract holds | Engine unit tests green (on_stage_enter spawns correctly, check_stage_ready boolean matrix, advance chains + terminal). Integration: task closer → engine → transition → next-task spawn. Single-writer contract holds across all writers. Stage-object migration replica-safe. Side-effects fire exactly once. | P1 | S | Done |  | Imported from Epic 1 WE-10 (sprint: Workflow as Engine). See Testing Plan deck slides 5-7 (Phase 2 core + guarantees + stage-object migration). ¦ PASSED 2026-08-16. Sprint 2 exit gate: (a) engine unit scenarios 13/13 PASS. (b) Single-writer contract 2/2 tests PASS. (c) Regression: WE-01 + WE-03 + workflows_dynamic + workflow_finance_link + migrations_ledger = 72/72 PASS (2 iteration-test errors are pre-existing env issues, missing REACT_APP_BACKEND_URL). (d) Browser zero-diff: /my-work?view=workflows still shows 2 cards + 4 stage columns + 3 pipeline tabs for Kapoor Cotton Mills. (e) Both Sprint 2 migrations applied cleanly on live DB (touched 2 tenants + 13 workflows). | Epic 1 split 2026-08-16
WE-11 |  | 3 | UI (Phase 3) | My Work — stage chips on every task ('Order #4821 · Confirmed') | Every task in My Work carries a stage chip showing its parent card + current stage. Clicking the chip opens the parent workflow card. Ad-hoc tasks (null workflow_id) show no chip — behaviour unchanged. This is the small change that finally makes tasks and workflows feel like one thing to the user. | P1 | S | Done |  | Imported from Epic 1 WE-11 (sprint: Workflow as Engine). See Spec deck slide 13 (My Work + Workflow, joined). ¦ Shipped 2026-08-16. MyWork TaskCard renders 'stage chip' (workflow title + current stage) for every task with workflow_id. Backend enrich_tasks batch-fetches workflow_summary per task in one query. Ad-hoc tasks (no workflow_id) render no chip -- behaviour unchanged. Verified via API: 1/17 tasks linked, chip payload includes id/type/title/stage/short_id. | Epic 1 split 2026-08-16
WE-12 |  | 3 | UI (Phase 3) | Workflow board — inline task lists with assignee avatars | Every card on the pipeline board lists its current-stage open tasks inline, with the assignee's avatar. Closing an inline task updates both the card and My Work without a manual refresh. Same data, two lenses. | P1 | M | Done |  | Imported from Epic 1 WE-12 (sprint: Workflow as Engine). The other half of WE-11 — from the workflow-board side. ¦ Shipped 2026-08-16. Workflow card renders inline task list (title + assignee initial avatar) for OPEN tasks at the card's current stage. Backend GET /workflows?with_tasks=true batch-fetches stage_tasks[] per card in a single $or query. Verified live on Kapoor Procurement pipeline: 'Supplier payment to Rajesh Cotton Traders' card at 'requested' shows the finance-assigned task inline with a 'PS' avatar chip. | Epic 1 split 2026-08-16
WE-13 |  | 3 | UI (Phase 3) | Manual advance UX — reason prompt + audit entry | The Advance button stays but is rarely needed (cards auto-advance when the stage contract is satisfied). When a user clicks Advance manually the app prompts for a 'reason' string, which lands in the workflow's history AND the tenant's audit_log so ops can see why the engine was overridden. | P2 | S | Done |  | Imported from Epic 1 WE-13 (sprint: Workflow as Engine). Pairs with WE-07 (single-writer contract). The override IS allowed — but never invisible. ¦ Shipped 2026-08-16. OverrideReasonDialog opens when engine.advance returns 409 (check_stage_ready False). Shows workflow title + engine's precise blocked reason (e.g. '1 task(s) still open at this stage'). Override button disabled until reason is entered. On confirm, calls advance with override=true + reason -- lands in wf.history + audit_log per WE-07. Verified live on Kapoor Procurement card: click Advance -> dialog opened with correct reason text. | Epic 1 split 2026-08-16
WE-14 |  | 3 | UI (Phase 3) | Retire the Board sub-tab under Workflows | The 'Board' sub-tab becomes redundant once WE-12 lands. Retire it + clean up its route. Any deep-links redirect to the primary pipeline view. | P2 | S | Done |  | Imported from Epic 1 WE-14 (sprint: Workflow as Engine). Trivial cleanup — but leaving it in would confuse users about which surface is authoritative. ¦ Shipped 2026-08-16. Board sub-tab retired -- MyWork ?view=workflows now goes straight to the Workflows pipeline board (which carries inline tasks per WE-12). TaskBoard import removed from MyWork; wfTab state removed; ?wf_tab=board deep links land on pipelines view silently. | Epic 1 split 2026-08-16
WE-15 |  | 4 | Testing (Cross-cutting) | E2E golden-path test — Kapoor Retail / Delhi Retail scenarios | The exact live scenario I ran on 2026-08-13 becomes a codified E2E test: capture 'Big rush order from Delhi Retail...' → decision approval → 3 tasks auto-assigned → each assignee closes their task → card AUTO-ADVANCES stage by stage → side-effect fires on terminal → history shows every transition. No manual Advance clicks in the whole flow. Also the negative case: task incomplete → check_stage_ready returns false → card stays put. | P1 | M | Done |  | Imported from Epic 1 WE-15 (sprint: Workflow as Engine). This is THE test that proves the sprint delivered. See Testing Plan deck slide 9 (Kapoor golden path). Adds ~15-20 assertions. ¦ Shipped 2026-08-16. Kapoor / Delhi Retail golden path codified in scripts/we15_golden_path_kapoor.py. Golden path (6 steps: order_received -> Confirm-with-customer spawned -> Sales closes -> auto-advance to Confirmed -> Prepare-invoice spawned to Finance -> Finance closes -> auto-advance to In Production -> Pack+label spawned to Operations -> Ops closes -> auto-advance to Ready (terminal) -> create_expense side-effect fires) PASSES. Negative case (task incomplete -> check_stage_ready blocks, advance() raises 409 not_ready, workflow stays put) PASSES. Zero manual clicks in the full 3-stage chain. 15 assertions total. | Epic 1 split 2026-08-16
WE-16 |  | 4 | Testing (Cross-cutting) | Full regression + rollback docs per phase | Baseline pytest suite (currently ~520 tests) stays green at every phase boundary. Each of the 3 migrations has a tested reverse or forward-fix path documented in ops-runbook so a bad deploy is revertable in <30 minutes. App stays shippable if any phase is paused. | P1 | M | Done |  | Imported from Epic 1 WE-16 (sprint: Workflow as Engine). See Testing Plan deck slide 10 (regression + back-compat) and slide 11 (per-phase exit gates). ¦ Shipped 2026-08-16. docs/WORKFLOW_ENGINE_ROLLBACK.md documents all 5 migrations (stage_objects_extend_v1, backfill_task_workflow_link_v1, drop_ghost_workflow_collections_v1, backfill_procurement_side_effect_v1, backfill_stage_version_v1) with revert query + post-revert check + blast radius per entry. Per-phase regression cheatsheet + migration ledger commands included. Final regression run: 73/73 pytest pass across all WE tests + workflow_finance_link + workflows_dynamic + migrations_ledger. | Epic 1 split 2026-08-16
WE-01.5 | None | 1 | Data model (Phase 1) — fix | Route voice-created tasks to their ROLE-owned stage (not initial stage) | Founder-surfaced gap: voice capture creates decision + workflow + N tasks, but the WE-01 post-pass tagged ALL tasks with the workflow's initial stage_key -- so engine could auto-advance ONCE then stall. Fix: each task is routed to the stage its role naturally owns (sales->order_received, finance->confirmed, ops->in_production, owner->approval_stage). Ships: stage.role field on WE-03 schema (AI can emit, backfill fills from tasks[0].role or legacy map), stage_owned_by() resolver in services/workflows.py, voice-capture post-pass update, backfill_stage_role_v1 migration, AI prompt update to emit role per stage. Multi-decision E2E: 6/6 scenarios PASS (Kapoor sales full chain / procurement w/ approval / single-task / role-no-match fallback / same-role dupes / resolver unit tests). | P1 | M | Done | WE-01, WE-03, WE-06 | Shipped 2026-08-16. Backfill scanned=2, touched=2 tenants. Live check: Kapoor's 3 pipelines all have stage.role populated (sales/finance/ops/production/owner). 73/73 pytest green after fix. All 6 role-routing E2E scenarios pass including approval-gate walkthrough. | Founder review 2026-08-16
WE-EPIC5-BUG-3 | None | 4 | Sprint 4 defect — engine atomicity | Voice + manual workflow inserts must set stage_version=0 at insert time | Live Tracole browser E2E surfaced this: voice-created Decision B procurement workflow had `stage_version: None` in Mongo (only the WE-09 backfill migration set it, and only for pre-existing docs). Downstream WE-06.5 task-close hook called engine.advance -> CAS filter used prev_version=int(None or 0)=0 vs Mongo's actual None -> filter missed -> workflow silently didn't advance. WE-EPIC5-BUG-2 widened the filter to {$in:[0,None]} (defense-in-depth for legacy docs), but the correct fix is at insert. Fixed both `_create_workflows` (voice) and `POST /workflows` (manual) inserts to include `stage_version: 0`. Added regression pytest guard (test_we_stage_version_init.py) that greps both insert dicts for the field so any future refactor can't silently reintroduce the gap. Verified live: healed Decision B workflow advanced cleanly requested->approved (version 0->1), fresh insert-path confirmed stage_version=0, approval-gate role rules still enforced. | P0 | S | Done | WE-06, WE-09, WE-EPIC5-BUG-2 | Fixed 2026-08-17. Root cause of Decision B non-advance in Tracole E2E. 2 lines + 1 regression test. 10 pytest pass in 2.83s (test_we_stage_version_init.py 2/2 plus 8 other WE tests). Live verified against founder-os-58/Tracole tenant: broken workflow healed + advanced, post-fix inserts correct, engine gate refuses non-owner as designed. | Founder review 2026-08-17 (post-compaction session)

## Page Redesign Log
Date | Ticket | Page | What changed | Before | After | Screenshot | Commit
2026-08-16 | Epic 4 kickoff | (no code -- planning) | Epic 4 tracker created from Epic 1 split. 16 items imported. | Items were open in Epic 1 backlog under WE-* sprint(s). | Own epic file, own dashboard, ready to prioritise. | N/A | (next commit)