## Dashboard
DecisionOS - Epic 5 - Enterprise RBAC
Multi-location + groups + SSO + API keys + client portal. DEFERRED to a future Enterprise Expansion phase -- DecisionOS is SME-first (phone/OTP, single-location, small teams) and the existing RBAC already exceeds SME needs. Revisit when enterprise/multi-location customers land.
Epic 5 DEFERRED -> Enterprise Expansion (future scope). 0 of 5 built; not on the SME-launch path.
Sprint | Sprint / Epic name | Done | Total | % | Status | Theme
Sprint 1 | Multi-location / multi-team data model | 0 | 2 | 0% | Deferred | Branches / departments scope on permissions (RBAC-18) + user groups (RBAC-19). Blocks multi-outlet SMEs from safely sharing a workspace.
Sprint 2 | Integrations | 0 | 2 | 0% | Deferred | SSO via Google + Microsoft OAuth (RBAC-28) + per-user API keys (RBAC-29). Enterprise-tier features for founders / integrators.
Sprint 3 | External sharing | 0 | 1 | 0% | Deferred | Client / customer read-only portal via signed link (RBAC-30). Whole new auth model + UX surface.

## Moving to Next Epic
Moving to Next Epic - parked items
Items scoped in Epic 5 but deferred. Empty at kickoff.
ID | Origin sprint | Title | Status | Why parked | Decision needed

## Cover
DecisionOS
Epic 5 - Enterprise RBAC
Kickoff | 2026-08-16 (Epic 1 split)
Origin | Imported from Epic 1 Stability tracker on 2026-08-16 per founder ask 'park RBAC-* to Epic 5'.
Epic 5 goal
Enterprise-tier RBAC features that don't block SaaS launch but unlock the next wave of tenants: multi-outlet retailers who need branch-scoped permissions, agencies that want SSO for their team, founders that want API keys for their zaps + scripts, and customer-facing surfaces for external comment / read-only sharing.
Working principles | 1. Every access change gets an audit trail entry (RBAC-20 log). 2. Time-bounded whenever possible - no permanent 'god mode' grants (leans on the RBAC-27 temp_grants pattern shipped in Epic 1). 3. Default DENY on any new surface; opt-in per tenant. 4. Same tracker discipline as Epic 2 - side-by-side updates.
Sprint breakdown
Sprint 1 -- Multi-location / multi-team data model
Status | Backlog (kickoff)
Items | RBAC-18, RBAC-19
Why | Branches / departments scope on permissions (RBAC-18) + user groups (RBAC-19). Blocks multi-outlet SMEs from safely sharing a workspace.
Sprint 2 -- Integrations
Status | Backlog (kickoff)
Items | RBAC-28, RBAC-29
Why | SSO via Google + Microsoft OAuth (RBAC-28) + per-user API keys (RBAC-29). Enterprise-tier features for founders / integrators.
Sprint 3 -- External sharing
Status | Backlog (kickoff)
Items | RBAC-30
Why | Client / customer read-only portal via signed link (RBAC-30). Whole new auth model + UX surface.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends on | Notes / evidence | Source
RBAC-18 |  | 1 | Data model | Department/branch scope on permissions | Add `branches` collection + membership.branch_id + permission modifier '[perm]:branch_X'. Blocks multi-location SMEs. Accept: Finance Manager in Store A sees zero Store B invoices. | P2 | L | Deferred |  | Imported from Epic 1 RBAC-18 (sprint: Sprint 4). Depends on RBAC-13 | Epic 1 split 2026-08-16
RBAC-19 |  | 1 | Data model | User groups | New `user_groups` collection: {tenant_id, name, member_ids, permissions[]}. user_perms merges (role) + (user override) + (union of groups). Accept: adding 'inventory' perm to 'Regional Managers' group instantly grants it to all group members. | P2 | M | Deferred |  | Imported from Epic 1 RBAC-19 (sprint: Sprint 4). Depends on RBAC-13 | Epic 1 split 2026-08-16
RBAC-28 |  | 2 | Auth | SSO (Google + Microsoft OAuth) | Add /auth/oauth/{provider}/start + callback. Map OAuth email to user via membership lookup. Handle first-time users (auto-provision if tenant allows). Accept: user with matching email can sign in with Google. | P2 | L | Deferred |  | Imported from Epic 1 RBAC-28 (sprint: Sprint 4). Depends on RBAC-12 | Epic 1 split 2026-08-16
RBAC-29 |  | 2 | Programmatic | Per-user API keys | New api_keys collection: {user_id, tenant_id, name, prefix, hash, scopes, created_at, last_used_at}. UI to create/revoke. Bearer-token auth reads api_key instead of JWT. Rate limits per key. Accept: script hits /tasks with key, works, revoke kills it. | P2 | M | Deferred |  | Imported from Epic 1 RBAC-29 (sprint: Sprint 4). | Epic 1 split 2026-08-16
RBAC-30 |  | 3 | UX | Client/customer read-only portal | Share a workflow (procurement order, complaint) with an external email via a signed link. Recipient sees status timeline + can add comments, no login. Accept: customer email link opens read-only page; commenting works without account. | P2 | L | Deferred |  | Imported from Epic 1 RBAC-30 (sprint: Sprint 5). | Epic 1 split 2026-08-16

## Page Redesign Log
Date | Ticket | Page | What changed | Before | After | Screenshot | Commit
2026-08-16 | Epic 5 kickoff | (no code -- planning) | Epic 5 tracker created from Epic 1 split. 5 items imported. | Items were open in Epic 1 backlog under RBAC-* sprint(s). | Own epic file, own dashboard, ready to prioritise. | N/A | (next commit)