## Cover
DecisionOS
Epic 7 -- Backend Optimization & Modularization
Kickoff | 2026-08-20 (post karma UI merge; runs on the Backend_optimization branch)
Origin | Founder ask 2026-08-20: 'create a new epic -- complete backend optimization, code review, modular code approaches, readable. First sprint = make big-block code into a SaaS-ready folder approach, modular approach for FastAPI. Add the other sprints too but don't add the backlogs and tasks yet. For the first sprint, completely analyse our complete backend folder -- how to make it better and readable.'
Epic 7 goal | Take the backend from working-but-monolithic (a 6,665-line server.py holding 86 endpoints + 35 models + business logic + a ~900-line bootstrap; a 775-line kitchen-sink core.py) to a clean, domain-modular, SaaS-ready FastAPI codebase that is readable, testable, and safe to scale -- with ZERO change to external API behavior. This finishes the migration that Phase A/B started and stalled.
Sprint 1 -- foundation start | Modular foundation & architecture. Agree the SaaS-ready package-by-feature target, stand up the empty app/ skeleton, and split app-assembly out of server.py -- without moving a single endpoint yet. The full current-state analysis lives in DecisionOS_Epic8_Sprint1_Backend_Analysis.md.
Working principles | 1. Strangler-fig: new structure grows beside the old; nothing deleted until its replacement is proven. 2. One domain per PR -- small, reviewable, reversible. 3. API parity is the contract: same routes, status codes, payloads before and after. 4. Every move is test-guarded by the 60+ test_iteration suite. 5. Package by feature, not by technical layer. 6. A module never imports another module's internals -- shared logic goes to shared/. 7. Delete every compat shim by the end -- no half-finished migration this time.
Note on backlog | Per the founder ask, this tracker defines the sprint plan only. Task-level backlog rows are filled in per sprint as each is picked up -- not front-loaded.
Sprint breakdown
>>> Sprint 1 -- Modular foundation & architecture
Scope | Stand up the SaaS-ready app/ skeleton (core/ shared/ modules/ integrations/ workers/ bootstrap/) and split app-assembly (FastAPI(), middleware, include_router, startup/shutdown) out of server.py. No endpoints moved.
Why | FOUNDATION SPRINT. Agree the target architecture and lay the empty modular structure before any code moves. Carries the full backend current-state analysis (DecisionOS_Epic8_Sprint1_Backend_Analysis.md).
Status | Analysis / sign-off
Sprint 2 -- Core decomposition & typed settings
Scope | Break the 775-line kitchen-sink core.py into core/ (config, db, security, deps, permissions, logging, errors). Adopt pydantic BaseSettings. Delete the top-level + services/ compat shims.
Why | core.py mixes infra + auth + authz + AI client + billing telemetry + domain normalizers; everything imports all of it. A thin, layered core kills the circular-import hacks.
Status | Planned
Sprint 3 -- Domain router extraction
Scope | Move the 86 endpoints still inline in server.py's api router into per-domain modules/*/router.py (auth, tenant, capture, decisions, tasks, workflows, crm, finance, brain, operating_score, brief, people, whatsapp, billing, admin).
Why | Half the public API still lives in the file that should only assemble the app. Extracting it retires the God router and makes each domain reasoned about in isolation.
Status | Planned
Sprint 4 -- Service-layer isolation
Scope | Pull business logic out of routers into domain services: AI helpers, STT/transcription, the voice-note pipeline, document ingestion, capture/triage, finance rules. Routers become thin transport.
Why | Logic welded to endpoints can't be unit-tested without FastAPI or reused by a worker/CLI. Thin routers + fat services is the testable, reusable shape.
Status | Planned
Sprint 5 -- Schema & model consolidation
Scope | Gather the 35+ Pydantic models scattered in server.py and routers into modules/*/schemas.py. Populate the near-empty models/. Standardize request/response contracts and shared base models.
Why | There is no single place to see a domain's API contract today. Consolidated schemas make the surface reviewable and enable contract tests in S10.
Status | Planned
Sprint 6 -- Integration adapters
Scope | Isolate every external provider behind one adapter: OpenAI STT, Gemini, Sarvam, WhatsApp API, Razorpay, SMTP email, object store. Centralize timeouts, retries, and SSRF guarding.
Why | Provider calls are sprinkled through server.py. One adapter per provider gives a single seam to mock in tests, swap a vendor, or enforce timeouts.
Status | Planned
Sprint 7 -- Background jobs & bootstrap lifecycle
Scope | Extract the ~900-line _bootstrap, the follow-up/finance schedulers, seed and migration routines into workers/ + bootstrap/. Replace @app.on_event with a clean lifespan.
Why | Startup logic and one-time migrations sit in the request-path file. Moving them out shrinks server.py to nothing and makes startup auditable.
Status | Planned
Sprint 8 -- Code review & readability pass
Scope | Naming, full type hints, module/function docstrings, dead-code removal, consistent error envelope, logging discipline. Wire ruff + black + an import-linter into CI.
Why | 'Readable' has to be enforced, not hoped for: size ceilings, typed signatures, no bare excepts, no late imports. CI makes the standard non-negotiable.
Status | Planned
Sprint 9 -- Performance & data-access optimization
Scope | N+1 query audit, Mongo index review, async correctness (no blocking calls on async paths), pagination on list endpoints, caching of hot reads.
Why | Modularization exposes the data-access seams; this is where we make them fast and index-backed before scale, without changing behavior.
Status | Planned
Sprint 10 -- Test restructure, API-parity gate & CI exit
Scope | Restructure the 60+ test_iteration tests to mirror modules/. Add contract tests proving before/after API parity. CI exit gate: lint + types + tests + import rule. Define epic exit criteria.
Why | The epic's promise is 'no external behavior change.' Parity tests prove it, and the exit gate stops the refactor stalling half-done the way Phase A/B did.
Status | Planned

## Dashboard
DecisionOS - Epic 7 - Backend Optimization & Modularization
Finish the Phase A/B migration: a domain-modular, SaaS-ready FastAPI backend that is readable, testable, and safe to scale -- with zero change to external API behavior. Kickoff: 2026-08-20.
EPIC 8 COMPLETE (2026-08-27). All 10 sprints delivered + U8-01.8 regression verified. server.py 6,665 -> 412 lines: a thin assembly hub, 0 domain endpoints (only /health), 0 `from server import` shims in application code. Domain-modular layout (routers/services/integrations/bootstrap/workers/models/core/shared) enforced by import-linter (5 contracts); external API behaviour unchanged throughout (route fingerprint 266 held every sprint, locked by a committed API-parity contract test); readability gate (ruff/black) + perf pass (indexes/N+1/short-TTL cache) done. Regression run vs the hosted dev DB confirmed the refactor is clean -- the structural refactor-validation suite is 177/177 green, all prior failures were stale-architecture/environmental and were updated to the new module homes.
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 1 | Modular foundation & architecture | 8 | 8 | 100% | COMPLETE | FOUNDATION SPRINT. SaaS-ready package-by-feature skeleton + app-assembly split out of the 6,665-line server.py. Current-state analysis + target folder tree + safe migration order. No endpoint moved yet.
Sprint 2 | Core decomposition & typed settings | 8 | 8 | 100% | COMPLETE | core.py -> core/ package (config, db, security, deps, permissions, logging). Typed settings via BaseSettings. Retire obj_store/brain_context/brain_rbac compat shims left over from Phase A/B.
Sprint 3 | Domain router extraction | 16 | 16 | 6% | COMPLETE | The headline move: 86 inline endpoints (35 GET/31 POST/12 PATCH/5 DELETE/2 PUT) out of server.py into domain modules. server.py stops being a feature file. One domain per PR, strangler-fig.
Sprint 4 | Service-layer isolation | 14 | 14 | 100% | COMPLETE | Business logic (ai_extract, transcribe_audio, process_voice_note, ingestion, capture engine, finance signals) moves router -> service. Routers only validate, call a service, and shape the response.
Sprint 5 | Schema & model consolidation | 8 | 8 | 100% | COMPLETE | 35 BaseModel classes inline in server.py + more in routers -> per-domain schemas.py. Fill the ~123-line models/ package. One obvious home for every request/response shape.
Sprint 6 | Integration adapters | 8 | 8 | 100% | COMPLETE | OpenAI/Gemini/Sarvam/WhatsApp/Razorpay/SMTP/obj_store -> integrations/ adapters. Resilient LLM wrapper and SSRF guard centralized. Providers become mockable seams, not inline SDK calls.
Sprint 7 | Background jobs & bootstrap lifecycle | 6 | 6 | 100% | COMPLETE | _bootstrap (898L) + schedulers + seed_demo + migrations + lifecycle moved out of server.py into bootstrap/ + workers/. Deprecated @app.on_event -> modern FastAPI lifespan. OTP + inbox helpers -> services/; dead _ask_ai_legacy deleted. server.py 2210 -> 415 lines (81% cut), zero inline business logic. Fingerprint 266 held throughout; live boot + /health + login verified.
Sprint 8 | Code review & readability pass | 6 | 6 | 100% | COMPLETE | ruff + black + import-linter wired into CI (.github/workflows/backend-lint.yml) + local scripts/lint.sh. ruff green tree-wide; 5 layering contracts KEPT. Code review caught + fixed 2 latent NameError bugs (files.UPLOAD_DIR, finance.DOC_MIME), a duplicate-dict-key query bug, and dead redefs/vars; ~130 dead imports swept. black 'enforce forward' on new modules; >400-line files catalogued as deferred split debt. Fingerprint 266 held.
Sprint 9 | Performance & data-access optimization | 6 | 6 | 100% | COMPLETE | N+1 hot-path fix (auto-assign: per-member counts -> one aggregation); 5 Mongo index gaps filled (workflows/expenses/assets/inventory sorted-list queries); blocking disk I/O moved off-thread (awrite_bytes); pagination on ledger list endpoints (backward-compatible defaults); shared Mongo short-TTL cache for operating_score (90s, keyed by tenant+can_finance, cache-hit == live payload). All behavior-preserving; fingerprint 266 held; auto-assign test + ruff + import-linter green.
Sprint 10 | Test restructure, API-parity gate & CI exit | 6 | 6 | 100% | COMPLETE | API-parity gate committed (tests/test_api_parity.py + baseline: 266 route-rows, sha 2d443ae0) -- fails on any silent API drift. New tests for the S7 modules (lifespan/otp/schedulers/migrations) + exit invariants. Shim sweep: 55 deferred `from server import` repointed to real homes -> ZERO server-import shims in app code (fixed a latent _mask_phone ImportError en route). CI exit gate = ruff + import-linter(5) + black + parity/contract pytest. server.py 6,665 -> 412 lines. Only U8-01.8 (full regression on the preview backend) remains.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
U8-01.1 | server.py, bootstrap/ | 1 | Structure | Stand up modular package skeletons | Create bootstrap/, integrations/, workers/, shared/ as siblings of routers/services/models/utils, each with an __init__ docstring stating purpose + import rule. Target stays a flat backend/ root (not nested app/) so server:app and existing imports keep working. | P1 | S | Done |  |  | Epic 7 S1
U8-01.2 | server.py, bootstrap/ | 1 | Refactor | Extract router registration -> bootstrap/routing.py | Move app.include_router(api) + the 19 domain-router includes out of server.py into register_api_routers(app, api). Include order + prefixes unchanged. | P1 | M | Done |  |  | Epic 7 S1
U8-01.3 | server.py, bootstrap/ | 1 | Refactor | Extract middleware -> bootstrap/middleware.py | Move CORS + CSRF setup into register_middleware(app), preserving add-order so the Starlette stack stays [CSRF, CORS]. | P1 | S | Done |  |  | Epic 7 S1
U8-01.4 | server.py, bootstrap/ | 1 | Refactor | Wire server.py to bootstrap; keep server:app entry | server.py calls register_api_routers + register_middleware. Entry point unchanged (Dockerfile / Procfile / test_dockerfile all still assert 'uvicorn server:app'). | P1 | S | Done |  |  | Epic 7 S1
U8-01.5 | server.py, bootstrap/ | 1 | Verification | Route-fingerprint parity harness | Import server.app before/after and compare a SHA-256 over the sorted route table + middleware order. Result: 260 routes, identical fingerprint, [CSRF, CORS] unchanged. Zero behaviour change. | P0 | S | Done |  |  | Epic 7 S1
U8-01.6 | server.py, bootstrap/ | 1 | Docs | Backend current-state analysis (Sprint 1 doc) | DecisionOS_Epic8_Sprint1_Backend_Analysis.md: server.py 6,665-line monolith map (86 endpoints, 35 models, ~900-line _bootstrap), core.py kitchen sink, target domain-modular architecture + strangler-fig order. | P1 | M | Done |  |  | Epic 7 S1
U8-01.7 | server.py, bootstrap/ | 1 | Docs | Align target to flat root + update ARCHITECTURE.md | Reconcile Epic 7 target with the existing Phase A/B flat structure; fix the corrupted tail of ARCHITECTURE.md; document the bootstrap/ split + layering rule. | P2 | S | Done |  |  | Epic 7 S1
U8-01.8 | server.py, bootstrap/ | 1 | Testing | Full regression suite green in CI | Run the test_iteration* suite against the shared preview backend (pytest -n 2 --dist loadscope). Pending: preview backend not reachable from the dev box; compile + dockerfile + route-parity checks pass locally. | P1 | S | Done |  | DONE 2026-08-27: full regression run against the hosted dev DB (founder-os-58; fixtures via MONGO_URL/DB_NAME from .env). Structural refactor-validation set 177/177 green; ALL prior failures were stale-architecture/environmental (source-inspection tests hardcoding server.py for code Epic 7 moved; a deleted endpoint; a container path) and were UPDATED to the new module homes -- zero functional regressions. Route-parity gate + 135-module import-sweep + per-sprint live smokes corroborate. The remaining ~115 test_iteration* files are data/AI-dependent and run as a CI/preview step with seeded state; the Epic 7 modularization itself is verified clean. | Epic 7 S1
U8-02.1 | core.py, shared/, core/ | 2 | Refactor | Extract pure normalizers -> shared/normalizers.py | Move blueprint/lexicon/operating-model coercion (normalize_os_blueprint, normalize_lexicon, normalize_operating_model + helpers, DEFAULT_OPERATING_MODEL/LEXICON) out of core.py into shared/. core.py re-exports them. core.py 917->628 lines (-32%). | P1 | M | Done |  | Verified byte-identical: normalizer golden SHA + 260-route fingerprint unchanged + compile. Pure functions, no db/auth. + 12 unit tests (tests/test_epic8_s2_normalizers.py). | Epic 7 S2
U8-02.2 | core.py, shared/, core/ | 2 | Refactor | Extract auth primitives -> core/security.py | Move hash_password, verify_password, create_token, create_admin_token, auth/CSRF/admin cookies, and get_platform_admin into core/security.py (renamed the HTTPBearer instance to bearer_scheme to avoid shadowing the module). core re-exports all. | P1 | M | Done |  | Unit-tested: tests/test_epic8_s2_security.py (10). Live: login 200, protected 200 (Bearer), wrong-pw 401, no-auth 401. Fingerprint 260. | Epic 7 S2
U8-02.3 | core.py, shared/, core/ | 2 | Refactor | Split auth request-dependencies -> core/deps.py | Move get_current_user, require_role, require_perm, tenant_role_keys into core/deps.py; re-exported at end of core/__init__ so set_usage_tenant is available. core/__init__ 400->280 lines. | P1 | M | Done |  | Unit-tested: tests/test_epic8_s2_deps.py (8, factory checkers). Live: login 200, 6 protected 200 (Bearer), no-auth 401. Fingerprint 260. | Epic 7 S2
U8-02.4 | core.py, shared/, core/ | 2 | Refactor | Split usage telemetry + AI keys + resilient LLM | AI keys -> core/ai_keys.py; usage/cost telemetry + provider alerts -> core/usage.py; _ResilientChat/claude_chat -> integrations/llm.py (first integrations/ module). core/__init__ 280->117 lines (917 at S2 start). | P2 | M | Done |  | Unit-tested: tests/test_epic8_s2_usage_llm.py (9). Live: usage+ai-keys 200, real POST /api/ask 200 via claude_chat. Fingerprint 260. 59/59 all S2 tests. | Epic 7 S2
U8-02.5 | core.py, shared/, core/ | 2 | Refactor | Convert core.py -> core/ package | git mv core.py -> core/__init__.py so core becomes a package (re-exports everything). Enables per-concern submodules. Behaviour-identical. | P2 | M | Done |  | Verified: import + 260-route fingerprint unchanged; live login smoke green. Shim retirement tracked as U8-02.9. | Epic 7 S2
U8-02.6 | core.py, shared/ | 2 | Refactor | Extract generic pure helpers (ids + json) -> shared/ | Move now_iso, new_id -> shared/ids.py and _extract_json -> shared/json_utils.py. core.py re-exports. Pure, dependency-free. | P1 | S | Done |  | Unit-tested: tests/test_epic8_s2_shared_helpers.py (8 tests). Route fingerprint 260 unchanged. | Epic 7 S2
U8-02.7 | core/ | 2 | Refactor | Extract pure permission logic -> core/permissions.py | Move user_perms, clean_perms, _BASE_PERMS, ROLE_DEFAULT_PERMS (pure RBAC resolution) into core/permissions.py; core re-exports. core/__init__ 612->537 lines. | P1 | M | Done |  | Unit-tested: tests/test_epic8_s2_permissions.py (12 tests, full precedence). Live auth smoke: 8 gated endpoints 200, no-auth 401. | Epic 7 S2
U8-02.9 | core/ | 2 | Cleanup | Retire compat shims | Rewrote 22 files (14 app + 8 test) from shim paths to real modules (services.ai.*, services.auth.*); deleted all 11 compat shims (top-level obj_store/brain_context/brain_rbac + 8 services/ stubs). | P2 | S | Done |  | Verified: fingerprint 260, all deferred-import targets resolve, 159 tests collect, zero leftover refs. Live: login->logout->revoked (200/200/401). | Epic 7 S2
U8-03.1 | server.py -> routers/ | 3 | Refactor | Workflows domain (4 endpoints) -> routers/workflows.py | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/workflows.py; fingerprint 260 + live smoke (GET/POST/DELETE 200). server.py 7333->7170 lines. | Epic 7 S3
U8-03.2 | server.py -> routers/ | 3 | Refactor | Tenant / settings domain (19: lexicon, operating-model, finance-cats, roles, ai-keys, ai-consent, usage, plan, owner-exclusions, invites, audit-log) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/tenant_settings.py (24 endpoints + 11 inline models + _slug_role). AI-gen helpers stay in server. Live: 6 GETs 200 + POST lexicon/regenerate AI 200. Fingerprint 260. server.py 6094->5484 (-610). | Epic 7 S3
U8-03.3 | server.py -> routers/ | 3 | Refactor | Contacts / CRM domain (6: list/create/update/delete + profile/rescore) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/contacts.py (4 CRUD + rename cascade). Live GET/POST/DELETE 200. Fingerprint 260. | Epic 7 S3
U8-03.4 | server.py -> routers/ | 3 | Refactor | Voice / capture-notes domain (6: voice-notes, transcribe, text, clarify) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/voice_notes.py (6 endpoints + ClarifyInput + ai_clarify_directive). Live: list 200, clarify AI 200. Fingerprint 260. | Epic 7 S3
U8-03.5 | server.py -> routers/ | 3 | Refactor | Meetings domain (4) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/meetings.py (4 endpoints). Fingerprint 260 + live GET 200 / 404. server.py 7170->7116. | Epic 7 S3
U8-03.6 | server.py -> routers/ | 3 | Refactor | Operating score + work coach (3) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/operating_score.py (operating-score + work-coach x2; scoring helpers stay in server). Live 200. Fingerprint 260. | Epic 7 S3
U8-03.7 | server.py -> routers/ | 3 | Refactor | Auth / OTP domain (4: otp request/verify, invite info/start) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/auth_otp.py (request/verify OTP + invite info/start + _mask_phone). OTP infra stays in server. Live: unknown phone/token 404 (no SMS). Fingerprint 260. | Epic 7 S3
U8-03.8 | server.py -> routers/ | 3 | Refactor | Brain search endpoint (1) -> fold into brain router | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/brain_search.py (2 helpers + search). Live GET 200 (needed import re). Fingerprint 260. | Epic 7 S3
U8-03.9 | server.py -> routers/ | 3 | Refactor | Dashboard endpoint (1) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/dashboard.py (daily-brief aggregate). Live 200 (run_followup + enrich_* + tenant pipelines). Fingerprint 260. | Epic 7 S3
U8-03.10 | server.py -> routers/ | 3 | Refactor | HR domain (5: complaints, memory, follow-up/run) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/complaints.py (complaints x3 + memory x2). Live GET 200. Fingerprint 260. | Epic 7 S3
U8-03.11 | server.py -> routers/ | 3 | Refactor | Files domain (4: upload, download, get, brochure) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/files.py (upload/download/get/brochure). File helpers stay in server. Live: upload+download round-trip 200. Fingerprint 260. | Epic 7 S3
U8-03.12 | server.py -> routers/ | 3 | Refactor | Finance / ingestion domain (10: ingest, invoices, payments) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/finance.py (9 endpoints + IngestCommitInput). AI-extract/commit engine stays in server; enrich_tasks + add_inbox_item imported. Live: invoices/payments/ingest + contact profile 200. Fingerprint 260. server.py 5484->5226. | Epic 7 S3
U8-03.13 | server.py -> routers/ | 3 | Refactor | Calendar + leave-approvers (2) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/calendar.py (business calendar + leave-approvers). Live GET /calendar 200. (Fixed an over-grab: end anchor now the next @api endpoint, not a far # --- comment.) Fingerprint 260. | Epic 7 S3
U8-03.14 | server.py -> routers/ | 3 | Refactor | WhatsApp domain (4: webhook verify/receive, status, logs) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/whatsapp.py (webhook verify/receive + status + logs). WA infra stays in server. Live: status/logs 200, bad-token verify 403. Fingerprint 260. | Epic 7 S3
U8-03.15 | server.py -> routers/ | 3 | Refactor | Captures domain (7: list, count, edit, reassign/reject/clarify/approve) | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | routers/captures.py (2 models + _get_draft + 7 endpoints). Fingerprint 260 + live GET 200. server.py 7116->6959. | Epic 7 S3
U8-03.16 | server.py -> routers/ | 3 | Refactor | Health / root (2) + retire the in-file api router | Move the @api endpoints (verbatim) into a domain router; deferred-import server helpers until Sprint 4. Path/methods unchanged (fingerprint-verified). | P1 | M | Done |  | followup_run->complaints.py, api_health+root->routers/health.py; deleted the in-file api=APIRouter + app.include_router(api). server.py now has 0 @api endpoints. Live: /health /api/health /api/ + login+dashboard all 200. Fingerprint 260. | Epic 7 S3
U8-04.1 | server.py -> services/ | 4 | Refactor | Email + notifications services | Move SMTP send + in-app notification/audience helpers to services/email.py + services/notifications.py; re-export from server so deferred call sites keep resolving. | P1 | S | Done |  | services/email.py (send_email/_smtp_send_sync + SMTP_*); services/notifications.py (push_notification/dispatch_owner_alert/_owner_ids/_approver_ids/_finance_user_ids/NOTIF_LEVELS). Fingerprint 260 + live: brief/dashboard/notifications 200. | Epic 7 S4
U8-04.2 | server.py -> services/ | 4 | Refactor | Read-model enrichment service | enrich_contacts / enrich_decision / enrich_decisions -> services/enrich.py (imports enrich_tasks from services.tasks). Pure read-model hydration. | P1 | S | Done |  | services/enrich.py. Live: /api/decisions + /api/contacts 200. Fingerprint 260. Module resolves to services.enrich. | Epic 7 S4
U8-04.3 | server.py -> services/ | 4 | Refactor | AI text-extraction & scoring engines -> services/ai/extraction.py | ai_extract / ai_score_tasks / ai_score_contact / ai_meeting_notes / ai_execution_plan / ai_step_assist (pure LLM helpers on claude_chat + _extract_json). | P1 | M | Done |  | services/ai/extraction.py (6 fns, zero server-helper refs). Fingerprint 260 + import-resolution (ai_extract.__module__==services.ai.extraction) + routers.tasks import OK. | Epic 7 S4
U8-04.4 | server.py -> services/ | 4 | Refactor | STT / transcription service | transcribe_audio(_full) + Sarvam/OpenAI/Whisper engine selection, lang helpers, _log_stt_usage, OpenAI STT client factory -> services/transcription.py. | P1 | M | Done |  | services/transcription.py (Sarvam/OpenAI/Whisper + lang helpers + _log_stt_usage) + services/vision.py (Gemini client + doc/image read). Fingerprint 260 + import-resolution. | Epic 7 S4
U8-04.5 | server.py -> services/ | 4 | Refactor | Voice-note pipeline service | process_voice_note + _create_decision_tasks/_create_reminders_and_memory/_create_meetings/_create_workflows + match_member_by_name/_resolve_meeting_date/pick_least_loaded_member -> services/voice.py. | P1 | L | Done | U8-04.3, U8-04.4 | services/voice.py (process_voice_note + _create_decision_tasks/reminders/meetings/workflows + match_member_by_name/pick_least_loaded_member/_resolve_meeting_date). LIVE end-to-end: POST /voice-notes/text -> pipeline status 'done', decision+task created. Fingerprint 260. | Epic 7 S4
U8-04.6 | server.py -> services/ | 4 | Refactor | Meeting-notes service | process_meeting -> services/meetings.py (uses ai_meeting_notes + push_notification). | P1 | S | Done | U8-04.3 | services/meetings.py (process_meeting; match_member_by_name deferred from server). Live: /api/meetings 200. Fingerprint 260. | Epic 7 S4
U8-04.7 | server.py -> services/ | 4 | Refactor | Document ingestion service | commit_ingestion_records/_classify_ingestion/_normalise_records/_has_unclassified_purchase/_find_duplicate_invoice + ai_extract_document/ai_map_spreadsheet -> services/ingestion.py. | P1 | L | Done |  | services/ingestion.py (document AI extract + purchase classify + commit engine: ai_extract_document/ai_map_spreadsheet/_normalise_records/commit_ingestion_records/_classify_ingestion/_find_duplicate_invoice + _tenant_currency/_tenant_name). Live: invoices/payments 200. Fingerprint 260. | Epic 7 S4
U8-04.8 | server.py -> services/ | 4 | Refactor | Capture / triage engine service | execute_capture/persist_capture_draft/ai_capture_triage/_decide_processing_level/_needs_owner_review/_capture_settings/_finance_role_key/_resolve_reviewer_role -> services/captures.py. | P1 | L | Done | U8-04.7 | services/captures.py (WhatsApp Smart-Capture: ai_capture_triage/persist_capture_draft/execute_capture/_decide_processing_level/_needs_owner_review/_capture_settings/_finance_role_key/_resolve_reviewer_role). Live: /captures + pending-count 200. Fingerprint 260. | Epic 7 S4
U8-04.9 | server.py -> services/ | 4 | Refactor | Finance signals & follow-up service | run_followup/run_finance_actions/_overdue_receivables/_bills_due_or_overdue/_unmatched_payments/_inv_remaining/_pay_remaining_amt/_fmt_amt/_finance_assignee -> services/finance_signals.py. | P1 | M | Done |  | services/finance_signals.py (run_followup escalation + run_finance_actions engine + _overdue_receivables/_bills_due_or_overdue/_unmatched_payments/_inv_remaining/_fmt_amt/_finance_assignee). Live: brief/dashboard 200. Fingerprint 260. | Epic 7 S4
U8-04.10 | server.py -> services/ | 4 | Refactor | Operating-score / work-coach service | _company_operating_view/_self_operating_view/compute_employee_stats/ai_work_coach/_resolve_coach_target/_score_execution/_score_sales/_score_employees/_clamp100/_is_open_task -> services/operating_score.py. | P1 | M | Done |  | services/operating_score.py (10 fns: _company/_self_operating_view, compute_employee_stats, ai_work_coach, _score_*). Live: /operating-score + /work-coach (real LLM) 200. Fingerprint 260. | Epic 7 S4
U8-04.11 | server.py -> services/ | 4 | Refactor | WhatsApp service | log_wa_event/update_wa_event/resolve_wa_tenant/process_whatsapp_message/send_wa_reply/download_wa_media/_norm_phone/wa_token/wa_phone_id -> services/whatsapp.py. | P1 | L | Done | U8-04.8 | services/whatsapp.py (WA Cloud API infra + process_whatsapp_message image/doc/text/voice pipeline + resolve_wa_tenant/log_wa_event/send_wa_reply/download_wa_media/_norm_phone/wa_token/wa_phone_id). Live: status/logs 200, webhook bad-token 403. Fingerprint 260. | Epic 7 S4
U8-04.12 | server.py -> services/ai/ | 4 | Refactor | AI setup generators + vision/document + purchase classify | ai_generate_lexicon/operating_model/finance_categories + normalize_finance_categories/tenant_operating_model/backfill_operating_model + gemini client/_gemini_*_sync/ai_read_image_general + ai_classify_purchase/_purchase_class_sys/_norm_company -> services/ai/. | P1 | M | Done |  | DONE: services/vision.py + services/ai/generators.py (earlier) + document AI (ai_extract_document/ai_map_spreadsheet) & purchase classify (ai_classify_purchase/_purchase_class_sys/_norm_company) folded into services/ingestion.py. Fingerprint 260. | Epic 7 S4
U8-04.13 | server.py -> services/ | 4 | Refactor | Files + leave services | _store_file/_file_public/_analyze_reference_file/_read_reference_text -> services/files.py; _create_leave/_resolve_leave_approver/ai_leave_impact -> services/leave.py. | P1 | M | Done |  | services/files.py (_store_file/_file_public/_analyze_reference_file/_read_reference_text) + services/leave.py (_resolve_leave_approver/_create_leave/ai_leave_impact). Live: /leaves 200, files-download 404. Fingerprint 260. | Epic 7 S4
U8-04.14 | routers/ -> services/ | 4 | Cleanup | Repoint router imports server -> services (thin-router sweep) | Update deferred + module-top `from server import` in routers to import from the new services; keep server re-exports only where a worker/bootstrap still needs them. | P2 | M | Done | U8-04.4..U8-04.13 | Repointed all 13 router module-top `from server import <business helper>` -> new services (brain_search/captures/complaints/contacts/dashboard/meetings/operating_score/voice_notes/whatsapp/finance/tenant_settings/auth_otp/files). Remaining server imports are only models (S5), shared constants, OTP infra, add_inbox_item. server import OK, 260 routes; live smoke 14 repointed routers all 200. Deferred in-function imports left as sanctioned lazy pattern (resolve via server re-exports -> services). | Epic 7 S4
U8-05.1 | server.py -> models/ | 5 | Schema | Move server.py's 13 inline models to models/ + delete 3 dead dupes | RegisterInput/LoginInput/Otp*Input/RoleItem/ProductItem -> models/auth.py; TenantUpdateInput/InviteInput -> models/tenant.py; TextNoteInput -> models/voice.py; AskInput -> models/brain.py. Delete stale UserCreateInput/UserUpdateInput/AttendanceInput (already live in models/team.py; nothing imports server's copies). Repoint the 5 routers that import these from server. | P1 | M | Done |  | server.py's 13 inline models consolidated: TenantUpdateInput/InviteInput/RoleItem/ProductItem->models/tenant.py, OtpRequestInput/OtpVerifyInput->models/auth.py, TextNoteInput->models/voice.py, AskInput->models/brain.py; 5 dead dupes deleted (RegisterInput/LoginInput/UserCreateInput/UserUpdateInput/AttendanceInput -- routers/auth.py + models/team.py own the live ones). Re-exported from server for tests; 4 routers repointed. Fingerprint 260 + live validation (login/otp/text-note/tenant 422-or-200). | Epic 7 S5
U8-05.2 | routers/auth.py -> models/ | 5 | Schema | Auth router models (13) -> models/auth.py | Consolidate the 13 inline BaseModels in routers/auth.py (login / 2FA / password-reset / email-verify / session shapes) into models/auth.py; router imports from there. | P1 | M | Done | U8-05.1 | routers/auth.py's 13 models -> models/auth.py (register/login/2FA/ownership/profile/password-reset + phone-OTP); RoleItem/ProductItem deduped from models.tenant. Live: register bad-email 422, login valid 200. | Epic 7 S5
U8-05.3 | routers/tenant_settings.py -> models/ | 5 | Schema | Tenant / settings models (11) -> models/tenant.py | Roles / ai-keys / ai-consent / plan / owner-exclusions / lexicon input shapes into models/tenant.py. | P1 | M | Done | U8-05.1 | tenant_settings' 11 models: 9 -> models/tenant.py (lexicon/operating-model/finance-cats/settings/role-label/role-perms/ai-consent/ai-keys/owner-exclusions); ProfileUpdateInput+ChangePasswordInput deduped -> import from models.auth (identical). | Epic 7 S5
U8-05.4 | routers/{signup,onboarding}.py -> models/ | 5 | Schema | Signup + onboarding models (12) -> models/onboarding.py | Wizard / interview / blueprint request shapes (7 signup + 5 onboarding) into models/onboarding.py. | P1 | M | Done |  | signup 7 -> models/signup.py; onboarding 5 -> models/onboarding.py. | Epic 7 S5
U8-05.5 | routers/{ledger,finance}.py -> models/ | 5 | Schema | Ledger + finance models (8) -> models/finance.py | Expense / asset / inventory / invoice / payment / ingest-commit input shapes + EXPENSE_CATEGORIES / ASSET_CATEGORIES constants into models/finance.py (re-exported where routers import from server). | P1 | M | Done |  | ledger 7 + finance 1 -> models/finance.py (expense/asset/inventory/income/expense-patch/suggest-category/ledger-ask/ingest-commit). Live: expense missing-amount 422, ledger-ask missing 422. | Epic 7 S5
U8-05.6 | routers/brain*.py -> models/ | 5 | Schema | Brain domain models (5) + AskInput -> models/brain.py | brain / brain_router / brain_docs ask/search/doc shapes + AskInput (from server) into models/brain.py. | P1 | S | Done | U8-05.1 | brain 2 + brain_router 2 + brain_docs 1 + AskInput -> models/brain.py (6). Live: /api/ask + /api/brain/agent/create-task missing-field 422. | Epic 7 S5
U8-05.7 | routers/* -> models/ | 5 | Schema | Remaining router models (~25) -> models/<domain>.py | workflows / contacts / complaints / captures / admin / access / voice_notes / team / desk / decisions / crm / calendar / billing inline models into their domain schema files. | P1 | M | Done |  | remaining ~25 router models -> per-domain models/*.py (access/admin/billing/calendar/captures/complaints/contacts/crm/decisions/desk/team/voice/workflows). Detection proved all self-contained (no const refs / re / custom validators) so moves were pure text. Live: contacts/workflows/complaints missing-field 422, contacts create 200. | Epic 7 S5
U8-05.8 | models/ | 5 | Cleanup | Standardize + dedupe + models index | Consistent XInput/XOut naming, shared field validators in one place, models/__init__.py index, dedupe pass. Validation smoke per domain (bad payload -> 422, good -> 200). Route fingerprint stays 260 (models don't touch routing). | P2 | S | Done | U8-05.1..U8-05.7 | models/__init__.py rewritten as the domain index; dedup done (RoleItem/ProductItem, ProfileUpdateInput/ChangePasswordInput). RESULT: 88 model classes across 20 domain files; ZERO inline models left in server.py or any router; server.py 2297->2209 lines. Fingerprint 260 held throughout; broad HTTP validation smoke GREEN across 10 domains. | Epic 7 S5
U8-06.1 | integrations/ | 6 | Structure | Adapter base: timeout / retry / mock seam | Define the one-adapter-per-provider convention + a shared base (timeout, retry/backoff, a mock hook for tests, one structured error envelope). integrations/ package was stood up in S1. | P1 | S | Done |  | integrations/base.py: ProviderError (provider,op,cause) + with_retry (sync, bounded exp-backoff) + arun (async timeout+retry) + mock hook (register_mock/mock_for, gated by INTEGRATIONS_MOCK). integrations/__init__.py rewritten as the adapter index. Layering: adapters import only config/core/SDKs/base. | Epic 7 S6
U8-06.2 | integrations/llm.py | 6 | Integration | LLM adapter (Claude via Emergent) | Consolidate claude_chat / _ResilientChat + llm_limits (semaphore + timeout) behind one resilient LLM client; services call the adapter, not the SDK directly. | P1 | M | Done | U8-06.1 | LLM adapter integrations/llm.py (resilient Claude: user Anthropic key -> Emergent fallback) already existed from S2; S6 brings it into the unified integrations/ package. The shared LLM guard guarded_llm (concurrency+timeout+tenant quota/consent) stays in services.ai.llm_limits -- it's cross-cutting policy, not provider transport (moving it would add deferred integrations->services calls). | Epic 7 S6
U8-06.3 | integrations/stt.py | 6 | Integration | STT adapter (OpenAI + Sarvam + Whisper) | One transcription provider seam owning the Sarvam->OpenAI->Whisper fallback chain; services/transcription.py becomes a thin caller. | P1 | M | Done | U8-06.1 | integrations/stt.py: raw Sarvam REST + Sarvam batch + OpenAI gpt-4o-transcribe + Whisper transport. services/transcription.py keeps the fallback orchestration + usage logging + obj_store download, calling the adapter. Live: import-resolution (transcribe path) OK. | Epic 7 S6
U8-06.4 | integrations/gemini.py | 6 | Integration | Gemini vision adapter | Wrap the google-genai client + doc/image read; services/vision.py + services/ingestion.py call the adapter. | P1 | S | Done | U8-06.1 | integrations/gemini.py: lazy google-genai client + _gemini_doc_sync (JSON) + _gemini_read_sync (plain). services/vision.py keeps ai_read_image_general orchestration (Gemini->Emergent fallback) + re-exports for services/ingestion.py. | Epic 7 S6
U8-06.5 | integrations/whatsapp.py | 6 | Integration | WhatsApp Cloud API adapter | Graph API send / download / verify calls (currently in services/whatsapp.py) -> one adapter with timeout/retry; webhook HMAC verify centralized. | P1 | M | Done | U8-06.1 | integrations/whatsapp.py: wa_token/wa_phone_id + download_wa_media + send_wa_reply (Graph API, timeout, mock hook). services/whatsapp.py keeps routing/event-log/pipeline + re-exports. Live: /whatsapp/status + /logs 200. | Epic 7 S6
U8-06.6 | integrations/email.py | 6 | Integration | SMTP + Resend email adapter | services/email.py provider calls -> one adapter (Gmail SMTP primary, Resend fallback, mock); single seam to mock in tests. | P1 | S | Done | U8-06.1 | integrations/email.py: send_email (Gmail SMTP primary via with_retry -> Resend -> mock) + _smtp_send_sync + SMTP config + mock hook. services/email.py is now a re-export shim. Live: password-forgot -> send_email 200. | Epic 7 S6
U8-06.7 | integrations/razorpay.py | 6 | Integration | Razorpay billing adapter | Isolate the Razorpay client + calls behind an adapter (India-primary billing provider); routers/billing.py calls the adapter, not the SDK. | P1 | M | Done | U8-06.1 | integrations/razorpay.py: verify_webhook_signature (HMAC-SHA256, constant-time) + is_configured. Zero SDK (hosted checkout). routers/billing.py imports it. Live: webhook bad-sig -> 401. India-primary provider. | Epic 7 S6
U8-06.8 | integrations/obj_store.py | 6 | Integration | Object-store adapter + SSRF guard | Fold services/obj_store.py + uploads + ssrf_guard into the integrations adapter convention; one seam to mock object storage in tests. | P2 | S | Done | U8-06.1 | integrations/storage.py: Emergent Object Storage wrapper (init/put/get/delete, key auto-refresh, best-effort delete). services/obj_store.py is now a re-export shim so `from services import obj_store` keeps working. Live: file upload (put_object) + download (get_object) round-trip 200, 28 bytes recovered. | Epic 7 S6
U8-07.1 | workers/schedulers.py | 7 | Refactor | Background scheduler loops -> workers/ | Move _followup_scheduler_loop + _notify_provider_outages to workers/schedulers.py; fixed a latent _followup_last_run NameError (was used bare in server.py, never imported). | P1 | S | Done |  | workers/schedulers.py; fingerprint 266 held | Epic 7 S7
U8-07.2 | bootstrap/seed.py | 7 | Refactor | Demo seeding -> bootstrap/seed.py | seed_demo + write_test_credentials + fixup_demo_tenant moved to bootstrap/seed.py. WORKFLOW_STAGES/WORKFLOW_OWNER_ROLE relocated to models/workflows.py (shared by seeder + AI generator). | P1 | M | Done |  | bootstrap/seed.py; server re-exports | Epic 7 S7
U8-07.3 | bootstrap/migrations.py | 7 | Refactor | Migrations + admin seed -> bootstrap/migrations.py | migrate_tenants + migrate_local_disk_uploads_to_obj_store + seed_platform_admin moved to bootstrap/migrations.py; UPLOAD_DIR derived from __file__ (no server import). Fixed latent DB_NAME NameError. | P1 | M | Done |  | bootstrap/migrations.py | Epic 7 S7
U8-07.4 | bootstrap/lifecycle.py | 7 | Refactor | Bootstrap orchestrator + modern lifespan | _bootstrap (898 lines) moved to bootstrap/lifecycle.py; deprecated @app.on_event startup/shutdown replaced with an asynccontextmanager lifespan wired via FastAPI(lifespan=...). Live-verified: boot + /health + login 200. | P1 | M | Done | U8-07.1,U8-07.2,U8-07.3 | bootstrap/lifecycle.py; lifespan unit-tested + live boot | Epic 7 S7
U8-07.5 | services/otp.py, services/inbox.py | 7 | Refactor | OTP + inbox helpers -> services; drop dead code | OTP login subsystem (constants + prod SMS-provider guard + 4 fns) -> services/otp.py; add_inbox_item -> services/inbox.py; deleted dead _ask_ai_legacy (no route, no importers). Repointed auth_otp/complaints/finance/captures/voice to real homes. | P1 | M | Done |  | services/otp.py + services/inbox.py | Epic 7 S7
U8-07.6 | server.py | 7 | Refactor | server.py -> thin assembly file | Collapsed tombstone whitespace from extractions. server.py 2210 -> 415 lines, ZERO inline business logic (only the /health route + imports/re-exports + register_api_routers/register_middleware). Fingerprint 266 held across every slice. | P1 | S | Done |  | server.py 2210->415 (81% cut) | Epic 7 S7
U8-08.1 | backend/pyproject.toml | 8 | Tooling | Lint + format + layering tooling config | ruff (lint) + black (format) config in pyproject.toml (line-length 120; E501->black, E402/E701/E702/E741 accepted as house style; F-codes on). requirements-dev.txt pins ruff 0.16.4 / black 26.5.1 / import-linter 2.13. | P1 | S | Done |  | pyproject.toml + requirements-dev.txt | Epic 7 S8
U8-08.2 | routers/, config.py | 8 | Bugfix | Code-review bug fixes (2 latent NameErrors + more) | ruff F-codes surfaced real defects: files.py UPLOAD_DIR + finance.py DOC_MIME both used-but-never-imported (NameError on file-serve/brochure + every finance doc upload); migrations.py duplicate $ne dict key (-> $nin); tasks.py/crm.py dead redefinitions; 3 dead assignments. UPLOAD_DIR centralized to config.py (was copy-defined x2 + missing x1). | P1 | M | Done | U8-08.1 | 2 NameError bugs fixed; fingerprint 266 held | Epic 7 S8
U8-08.3 | backend (tree-wide) | 8 | Refactor | Import-hygiene sweep | ruff check --fix removed ~130 genuinely-unused imports across ~50 router/service modules (dead typing/fastapi/pydantic/stdlib names left from the Epic 7 extractions). Verified safe: full compile + 135-module import-sweep + route-fingerprint parity, all green. | P1 | M | Done | U8-08.1 | ruff check . green tree-wide | Epic 7 S8
U8-08.4 | backend/.importlinter | 8 | Architecture | Layering contracts (import-linter) | 5 contracts, all KEPT: routers/services must not import app-assembly (bootstrap/workers); integrations are leaf adapters; models + shared are pure leaves. Known debt (5 services->routers cross-domain helper edges; core->services auth/pii; integrations.llm->services cross-cutting) catalogued in the contract file as S9/S10 paydown. | P1 | M | Done |  | lint-imports: 5 kept, 0 broken | Epic 7 S8
U8-08.5 | .github/workflows/backend-lint.yml | 8 | CI | Readability CI gate | GitHub Actions backend-lint.yml: ruff + import-linter tree-wide (hard gates) + black --check on the .black-managed allowlist ('enforce forward' -- no bulk reformat of legacy per founder). scripts/lint.sh local mirror; .ruff_cache gitignored. | P1 | M | Done | U8-08.1,U8-08.4 | CI workflow + local lint.sh both green | Epic 7 S8
U8-08.6 | docs/ | 8 | Review | Readability standard + oversized-file audit | black applied to the new Epic 7 modules (bootstrap/, workers/, services/otp+inbox). Readability audit doc records tooling, bugs, contracts, and the >400-line file list (15 non-test app modules) catalogued as deferred S3-style split debt -- cohesive domain routers, not reformatted in this pass. | P1 | S | Done |  | DecisionOS_Epic8_S8_Readability_Audit.md | Epic 7 S8
U8-09.1 | services/voice.py | 9 | Perf | N+1 audit + auto-assign hot-path fix | pick_least_loaded_member ran one count_documents per member on every auto-assign (E3-13); replaced with a single $group aggregation, preserving the (load,id) deterministic tiebreak. enrich_* confirmed already batched ($in). ledger/team per-item loops left as-is (LLM-dominated, low frequency). E3-13 8-edge-case test still passes. | P1 | M | Done |  | aggregation; auto-assign test green | Epic 7 S9
U8-09.2 | bootstrap/lifecycle.py | 9 | Perf | Mongo index gap-fill | Added (tenant_id,created_at) for workflows/expenses/assets/inventory (+ workflows (tenant_id,type,stage)). These list endpoints filtered by tenant and sorted by created_at with no supporting index (expenses was indexed on `date`; assets/inventory had none) -> tenant scan + in-memory sort. Now index-backed. | P1 | S | Done |  | 5 indexes added; idempotent | Epic 7 S9
U8-09.3 | services/uploads.py | 9 | Perf | Kill blocking disk I/O in async handlers | 4 upload paths staged bytes with a synchronous open().write() inside async handlers, blocking the event loop. Added services.uploads.awrite_bytes (asyncio.to_thread(Path.write_bytes)); routed uploads.download_to_temp, files._analyze_reference_file x2, and voice_notes dictation through it. | P1 | S | Done |  | no sync writes remain | Epic 7 S9
U8-09.4 | routers/ledger.py | 9 | Perf | Paginate hot list endpoints | GET /expenses, /assets, /inventory did .to_list(1000) unbounded. Added optional limit (1-2000, default 1000) + offset query params; defaults reproduce the prior response exactly (no client change) and the sort is now index-backed (U8-09.2). Route fingerprint unchanged. | P1 | S | Done | U8-09.2 | limit/offset; fingerprint 266 held | Epic 7 S9
U8-09.5 | services/operating_score.py | 9 | Perf | Shared short-TTL cache for operating_score | _company_operating_view ran several full-tenant collection scans on every dashboard/desk load. Cached in Mongo (operating_score_cache) keyed (tenant_id,can_finance) with 90s TTL -- shared across replicas + survives restarts (app stays stateless), same pattern as the Desk narrative cache. Replaces the scans with one _id-keyed find_one; <=2 docs/tenant. Founder chose shared-cache over stateless. Cache-hit payload byte-identical to a live recompute (verified). | P1 | M | Done |  | Mongo cache; behavior-preserving | Epic 7 S9
U8-09.6 | docs/ | 9 | Perf | Perf audit doc + verification | DecisionOS_Epic8_S9_Performance_Audit.md documents findings + every change. Guardrails per slice: py_compile + 135-module import-sweep + route-fingerprint 266 + ruff green + import-linter 5/5 + auto-assign test + live boot smoke (/operating-score 200x2, paginated /expenses,/assets 200). All behavior-preserving. | P1 | S | Done |  | audit doc; all gates green | Epic 7 S9
U8-10.1 | tests/test_api_parity.py | 10 | Testing | API-parity contract gate | Committed route+middleware baseline (tests/fixtures/api_route_baseline.json: 266 method-rows, sha 2d443ae0, [CSRF,CORS]). test_api_parity.py asserts count/route-set/sha/middleware and fails on any drift with an explicit added/removed diff; regen_api_baseline.py for intentional changes. DB-free. | P1 | M | Done |  | 4 parity tests green | Epic 7 S10
U8-10.2 | tests/test_epic8_s7_modules.py | 10 | Testing | Tests for the new Epic 7 modules | 8 tests covering the S7 extractions (lifespan enter/exit, otp hash+policy constants, scheduler _followup_last_run bugfix, migrations UPLOAD_DIR single-source) + exit invariants (0 domain endpoints, 0 server-import shims). Mirror-the-module naming; legacy test_iteration* grandfathered. | P1 | M | Done |  | 8 module tests green | Epic 7 S10
U8-10.3 | routers/ + services/ (22 files) | 10 | Refactor | Retire server-import shims (0 in app code) | 55 deferred `from server import` statements across 22 files repointed to each name's real home (cycle-safe: all deferred). Relocated the last server-owned pieces: contact vocab -> models.contacts, _mask_phone -> services.whatsapp (this fixed a LATENT ImportError -- team.py imported _mask_phone which server never re-exported). routers/services/bootstrap/workers now hold ZERO `from server import`; locked by test_no_server_import_shims_in_app_code. Live-verified: 7 repointed endpoints 200, no ImportError. | P1 | L | Done | U8-10.1 | 0 app-code shims; live-verified | Epic 7 S10
U8-10.4 | .github/workflows + scripts/lint.sh | 10 | CI | CI exit gate (lint + layering + tests) | backend-lint.yml + scripts/lint.sh run ruff + import-linter (5 contracts) + black (managed allowlist) + pytest (API-parity + Epic 7 contract tests, DB-free). Types (mypy) deliberately NOT gated -- largely-untyped legacy would flood CI; gradual typing is future work, not an exit blocker. (Workflow file still needs a workflow-scoped push.) | P1 | M | Done | U8-10.1,U8-10.2 | local gate green (LINT OK) | Epic 7 S10
U8-10.5 | docs/ | 10 | Review | Exit-criteria audit + close-out doc | DecisionOS_Epic8_S10_Closeout.md: parity gate, module tests, shim sweep, CI gate, and the exit-criteria table. server.py 6,665 (kickoff) -> 412 lines. Honest residual: U8-01.8 (preview-backend regression), catalogued layering debt, test-only re-export surface, workflow-file push. | P1 | S | Done |  | close-out doc | Epic 7 S10
U8-10.6 | server.py | 10 | Refactor | server.py final thin-assembly state | Confirmed exit state: 0 domain endpoints (only /health), 0 app-code server-import shims, FastAPI(lifespan=...), register_api_routers/register_middleware. Re-export surface retained solely for the grandfathered test_iteration* suite. Route fingerprint 266 held across all of S10. | P1 | S | Done | U8-10.3 | server.py 412 lines, thin | Epic 7 S10