## README
DecisionOS -> SaaS-Stable Tracker
Sprint plan + Kanban board covering every fix from the backend, schema/scale, and AI/Brain reviews, ending in DevOps + Data Migration.
Generated 2026-08-04 · Branch: Backend_optimization · Source docs: docs/BACKEND_SAAS_READINESS_REVIEW.md, docs/BACKEND_SCHEMA_SCALE_GOLIVE_REVIEW.md, docs/AI_BRAIN_AGENTIC_REVIEW.md
How to use this workbook
• | Dashboard — live rollup of every sprint AND the Testing Plan: task counts, % complete, open P0s, and the overall go-live gate status. All formulas — edit Status on Task Backlog / Testing Plan and this updates itself.
• | Task Backlog — the single source of truth for engineering work. One row per fix. Change the Status dropdown as work moves; this drives the Dashboard and is the sortable/filterable 'sprint sheet.'
• | Kanban Board — visual board grouped by Sprint (the swimlanes), cards color-coded by Priority. Snapshot view for planning conversations; the Task Backlog is what you actually edit day to day.
• | Testing Plan — every test type required before going live (automated, multi-tenant isolation, security, load/performance, resilience, migration/backup) PLUS the Alpha -> Closed Beta -> Staged Beta -> GA rollout milestones with entry/exit criteria for each stage.
• | Go-Live Checklist — the final gate. Every row must be checked TRUE before opening self-serve signup or onboarding client #1 at scale — includes a line item confirming every Testing Plan phase passed.
• | RBAC & People Access — product-level audit of who-can-do-what. Companion to Sprint 2. Backlog items RBAC-01..30 also mirrored into Task Backlog under sprint 'Sprint 2.5' / 'Sprint 3' / 'Sprint 4' / 'Sprint 5'.
Legend — Priority
P0 | Ship-blocker — must close before the next tenant / go-live gate it sits in
P1 | Fix before selling to a real customer — not an immediate blocker but close soon
P2 | Quality/hardening — schedule once P0/P1 are clear
Legend — Status
Backlog
To Do
In Progress
Blocked
In Review
Done
Cells to edit
On Task Backlog: Status, Owner, Start Date, Due Date, and Notes are yours to fill in / update. On Testing Plan: Status and Owner are yours to update. On Go-Live Checklist: set Done? to TRUE only once verified. All editable columns are shown with a gold header fill. Everything else documents the finding and should not need editing.

## Dashboard
Go-Live Readiness Dashboard
Everything below recalculates from Task Backlog — update Status there, not here.
Total tasks
Done
Overall % complete
Open P0s (all sprints)
Go-Live blockers still open
Testing Plan phases not yet Passed
READY FOR 100-CLIENT SaaS?
Sprint | Goal | Gate? | Total | Done | % Complete | Open P0s
Sprint 0 — Critical Security & Auth | Close every exploit that would get the platform owned in week one. No external tenant before this is clear. | GATE
Sprint 1 — Scale & Operational Blockers | Fix the operational issues that break under multiple replicas / real concurrent load. | GATE
Sprint 2 — Tenancy Hygiene & Data Integrity | Harden tenant isolation edges and fix data-integrity rough spots found in the schema audit. | Parallel
Sprint 3 — Billing & Multi-Tenant AI Keys | Stand up real billing and per-tenant AI cost isolation — required before charging money. | GATE
Sprint 4 — AI Brain / Agentic Enhancement | Upgrade retrieval to real RAG and the Brain toward agentic. Parallel track — does not block go-live. | Parallel
Sprint 5 — DevOps, Deployment & Data Migration | Final gate: staging, load test, observability, tested backups, migration plan, staged rollout, go/no-go. | GATE

## Task Backlog
ID | Sprint | Category | Task | Fix / Description | Priority | Source Doc | File Reference | Effort (S/M/L) | Status | Owner | Start Date | Due Date | Blocks Go-Live? | Notes
S0-01 | Sprint 0 | Security/Auth | Remove hardcoded superadmin default credentials | Require env vars for SUPERADMIN_EMAIL/PASSWORD; stop overwriting DB hash on every restart so rotation works | P0 | SaaS Readiness Review | server.py:4925-4937 | S | Done |  | 2026-08-11 | 2026-08-11 | Yes | Shipped in FIX-006-A (c57b550).
S0-02 | Sprint 0 | Security/Auth | Fix CORS wildcard + credentials | Replace allow_origin_regex='.*' with a strict origin allow-list; add CSRF protection for cookie-authed mutating routes | P0 | SaaS Readiness Review | server.py:4994-5001, core.py:218-222 | M | Done |  | 2026-08-12 | 2026-08-12 | Yes | Shipped in FIX-006-B (ababc06).
S0-03 | Sprint 0 | Security/Auth | Auth-gate file downloads | Add get_current_user + tenant ownership check to GET /api/files/{fname}; currently unauth, guessable UUID = any tenant's file | P0 | SaaS Readiness Review | server.py:3032-3038 | S | Done |  | 2026-08-12 | 2026-08-12 | Yes | Shipped in FIX-006-C (685141d).
S0-04 | Sprint 0 | Security/Auth | Kill dev-mode OTP leak | Stop returning dev_otp in the API response; hard-fail boot if no SMS provider configured when ENV=prod | P0 | SaaS Readiness Review | server.py:1345-1347 | S | Done |  | 2026-08-12 | 2026-08-12 | Yes | Shipped in FIX-006-C (685141d).
S0-05 | Sprint 0 | Security/Auth | Fix WhatsApp signature bypass | Reject the webhook request on HMAC mismatch instead of logging + processing anyway | P0 | SaaS Readiness Review | server.py:3919-3933 | S | Done |  | 2026-08-12 | 2026-08-12 | Yes | Shipped in FIX-006-C (685141d).
S0-06 | Sprint 0 | Security/Auth | Rate-limit + captcha unauth AI endpoints | Add Turnstile/hCaptcha + IP rate limit to /api/signup/* and /api/onboarding/* — currently unauth and can burn unlimited LLM spend | P0 | SaaS Readiness Review | routers/signup.py, routers/onboarding.py:39,73 | M | Done |  | 2026-08-12 | 2026-08-12 | Yes | Shipped in FIX-006-D (93a9f1c).
S0-07 | Sprint 0 | Security/Auth | Add login rate limiting | Tenant user login has no attempt lockout (admin login does); add 5-attempt/15-min lockout to match | P1 | SaaS Readiness Review | routers/auth.py:151-162 | S | Done |  | 2026-08-12 | 2026-08-12 | Yes | Shipped in FIX-006-D (93a9f1c).
S0-08 | Sprint 0 | Security/Auth | Stop returning raw JWT in response body | Login/register return the token in JSON as well as the cookie; any XSS bypasses HttpOnly. Cookie-only. | P1 | SaaS Readiness Review | routers/auth.py:148,162 | S | Done |  | 2026-08-11 | 2026-08-11 | Yes | Shipped in FIX-006-A (c57b550).
S0-09 | Sprint 0 | Security/Auth | Split JWT secret: tenant vs platform admin | Single JWT_SECRET used for both; only the 'type' claim separates them. Use two secrets. | P1 | SaaS Readiness Review | core.py:237,297 | S | Done |  | 2026-08-11 | 2026-08-11 | Yes | Shipped in FIX-006-A (c57b550).
S0-10 | Sprint 0 | Security/Auth | Invalidate invite tokens after use | Invite tokens never expire after first use; invite_start also bypasses OTP cooldown (SMS-bomb vector) and leaks full phone number in the response | P1 | SaaS Readiness Review | server.py:1372,1386,1396,1397 | S | Done |  | 2026-08-11 | 2026-08-11 | Yes | Shipped in FIX-006-A (c57b550).
S1-01 | Sprint 1 | Scale/Ops | Externalize the follow-up scheduler | In-process 300s loop triple-fires (duplicate emails/alerts) with 3 replicas, dies with 1. Move to a single external cron/worker or add leader election. | P0 | Schema/Scale/Go-Live Review | server.py:2765, 4946 | M | Done |  | 2026-08-09 | 2026-08-09 | Yes | Shipped in FIX-002-D ((this commit)).
S1-02 | Sprint 1 | Scale/Ops | Index phone, drop Python-side filter | OTP login + WhatsApp routing do a full collection scan with no phone index, capped at 2000-5000 docs (silent lockout beyond that). Add (tenant_id, phone) index. | P0 | Schema/Scale/Go-Live Review | server.py:1357,1419,4004 | S | Done |  | 2026-08-09 | 2026-08-09 | Yes | Shipped in FIX-002-A (e21a9b3).
S1-03 | Sprint 1 | Scale/Ops | Move all uploads to obj_store | Voice notes, meetings, ledger uploads write to local disk — lost on restart, invisible across replicas. Route everything through the existing obj_store path; delete the local /api/files path. | P0 | Schema/Scale/Go-Live Review | server.py:1739,1902,3032; ledger.py:146 | M | Done |  | 2026-08-09 | 2026-08-09 | Yes | Shipped in FIX-002-E ((this commit)).
S1-04 | Sprint 1 | Scale/Ops | Commit real deployment config | No Dockerfile/Procfile exists. Pin worker count, add graceful shutdown for in-flight LLM calls, request-size caps. | P0 | Schema/Scale/Go-Live Review | (missing — new file) | M | Done |  | 2026-08-09 | 2026-08-09 | Yes
S1-05 | Sprint 1 | Scale/Ops | Timeout + concurrency-limit LLM calls | No asyncio.wait_for on LLM calls; one shared key across all tenants means a burst of voice-capture cascades 429s with no ceiling. Add timeout + semaphore. | P1 | Schema/Scale/Go-Live Review | core.py:177 | M | Done |  | 2026-08-09 | 2026-08-09 | Yes | Shipped in FIX-002-B (6b6fc25).
S1-06 | Sprint 1 | Scale/Ops | Fix hardcoded purchase_payment key | Owner-approval loop, pending-purchases dashboard, and payment-overdue alerts only recognize the textile pipeline key. Non-textile tenants silently lose their sign-off + payment tracking. | P0 | Schema/Scale/Go-Live Review | routers/decisions.py:166; server.py:2429; routers/brief.py:95,98,238,262 | M | Done |  | 2026-08-04 | 2026-08-04 | Yes | Shipped in FIX-001-A (cb84474+69f4ce3).
S2-01 | Sprint 2 | Tenancy/Data | Add _ensure_owned() helper | Many update_one/delete_* calls filter by {'id': X} only after an earlier tenant-scoped read. UUID makes it safe today but drift/leak risk. Centralize the pattern. | P1 | SaaS Readiness Review | routers/tasks.py:317,360,395; decisions.py:144-227; brain_docs.py:320,329; ledger.py:585,638,684 | M | Done |  | 2026-08-09 | 2026-08-09 | No | Shipped in FIX-001-C (da29cfd).
S2-02 | Sprint 2 | Tenancy/Data | Complete TENANT_COLLECTIONS wipe | Tenant deletion omits brain_context, brain_documents, capture_drafts, platform_alerts, reclassify_jobs, signup_sessions, and never deletes uploaded files. GDPR gap. | P1 | SaaS Readiness Review | routers/admin.py:161-186 | S | Done |  | 2026-08-04 | 2026-08-04 | No | Shipped in FIX-001-E (65cea2c).
S2-03 | Sprint 2 | Tenancy/Data | Tenant-scope OTP + WhatsApp phone routing | Two users in different tenants sharing a phone can log into the wrong workspace, or hijack another tenant's inbound WhatsApp. | P0 | Schema/Scale/Go-Live Review | server.py:1418-1428,1357; 3999-4028 | M | Done |  | 2026-08-09 | 2026-08-09 | Yes | Shipped in FIX-003-A (6a1ecec).
S2-04 | Sprint 2 | Tenancy/Data | Fix cross-tenant WhatsApp log leak | whatsapp/logs OR-includes tenant_id:None rows, visible to every tenant owner. | P1 | SaaS Readiness Review | server.py:3993-3995 | S | Done |  | 2026-08-09 | 2026-08-09 | No | Shipped in FIX-003-A (6a1ecec).
S2-05 | Sprint 2 | Tenancy/Data | Fix unfiltered enrich_decisions fetch | Related tasks/users fetched with no tenant filter; safe only because task_ids can't currently contain a foreign UUID. | P2 | SaaS Readiness Review | server.py:2142-2158; routers/decisions.py:44,172-175 | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-B (f18bbc3).
S2-06 | Sprint 2 | Tenancy/Data | Add session invalidation on logout/password-change | JWT stays valid 7 days after logout; no jti/token-version, so a stolen session can't be revoked. | P1 | SaaS Readiness Review | core.py:225-226 | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-C (f48bd24).
S2-07 | Sprint 2 | Tenancy/Data | Add email verification + password reset | No self-serve recovery flow exists anywhere; enterprise-deal blocker. | P1 | SaaS Readiness Review | routers/auth.py | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-D (4ef865e).
S2-08 | Sprint 2 | Tenancy/Data | Fix dead contacts.kind index | Index uses 'kind', every read/write uses 'type'. Index (tenant_id, type) instead. | P1 | Schema/Scale/Go-Live Review | server.py:4865 | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-B (f18bbc3).
S2-09 | Sprint 2 | Tenancy/Data | Fix denormalized-name staleness | assignee_role / contact_name copies go stale on rename and are shown to users. Add refresh-on-rename. | P2 | Schema/Scale/Go-Live Review | routers/tasks.py; server.py:3326 | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-C (f48bd24).
S2-10 | Sprint 2 | Tenancy/Data | Handle concurrent-registration race | Same-email concurrent registers can race past the pre-check and hit the unique index, throwing a raw 500 instead of a clean 400. | P2 | Schema/Scale/Go-Live Review | routers/auth.py:92-93 | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-B (f18bbc3).
S2-11 | Sprint 2 | Tenancy/Data | Flag AI-operating-model generation failures | Malformed/timed-out AI response silently falls back to the textile default model with zero error shown to the tenant. | P1 | Schema/Scale/Go-Live Review | server.py:1154-1160 | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-003-C (f48bd24).
S2-12 | Sprint 2 | Tenancy/Data | Fix 'active workflows' hardcoded terminal stages | KPI checks stage NOT IN [delivered, paid] — non-textile terminal stages never match, so the count only ever climbs. | P2 | Schema/Scale/Go-Live Review | server.py:2433 | S | Done |  | 2026-08-10 | 2026-08-10 | No | Already closed by FIX-001-F; regression-guarded in FIX-003-B.
S3-01 | Sprint 3 | Billing/AI-Keys | Integrate real billing (Stripe or Razorpay) | stripe is in requirements.txt but never imported. No subscription billing exists at all today. | P0 | SaaS Readiness Review | requirements.txt:129 | L | Backlog |  |  |  | Yes
S3-02 | Sprint 3 | Billing/AI-Keys | Add plan / entitlement fields to tenant doc | No plan, trial_ends_at, seat_limit, or feature_flags — every tenant is on unlimited free forever. | P1 | SaaS Readiness Review | tenant document schema | M | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-005-A (afbf9b8).
S3-03 | Sprint 3 | Billing/AI-Keys | Per-tenant AI key resolver | All AI keys are one global pool shared by every tenant; one rate-limited/leaked key breaks 100% of tenants. Add per-tenant key columns + fallback resolver. | P0 | SaaS Readiness Review | config.py:53-60; core.py:177-205; routers/admin.py:335-348 | L | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-005-A (afbf9b8).
S3-04 | Sprint 3 | Billing/AI-Keys | Enforce usage quotas (402 on exceed) | Usage telemetry is estimation-only; no hard limit stops a tenant from running up unlimited LLM cost. | P1 | SaaS Readiness Review | services/usage.py | M | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-005-B (29d2238).
S4-01 | Sprint 4 | AI/Brain | Fix text-index stemming + index db.memory | default_language='none' disables stemming (refund != refunds); db.memory has no text index at all, only regex scan. | P2 | AI/Brain/Agentic Review | server.py:4894; brain.py:250-255 | S | Backlog |  |  |  | No
S4-02 | Sprint 4 | AI/Brain | Fix task-done Brain write-coverage gap + link provenance | Execution-plan-complete path skips record_context; add decision_id linkage so decision->task->outcome is reconstructable. | P1 | AI/Brain/Agentic Review | tasks.py:507; services/brain_context.py | M | Backlog |  |  |  | No
S4-03 | Sprint 4 | AI/Brain | Rename brain_contexts -> brain_query_cache | Kills the dangerous brain_context / brain_contexts name collision. | P2 | AI/Brain/Agentic Review | brain.py:714,752,794 | S | Backlog |  |  |  | No
S4-04 | Sprint 4 | AI/Brain | Unify /ask and /brain/agent retrieval reach | /ask never reads brain_context or brain_documents — provenance answers only work on the Dex agent path. Give both the same reach. | P1 | AI/Brain/Agentic Review | routers/brain.py:52,205 | M | Backlog |  |  |  | No
S4-05 | Sprint 4 | AI/Brain | Extract + chunk + embed documents at ingest | Uploaded documents are stored as metadata only; body text is never read at ingest. Add server-side extraction + chunking + embeddings into a new brain_chunks collection. | P1 | AI/Brain/Agentic Review | routers/brain_docs.py:147-213 | L | Backlog |  |  |  | No
S4-06 | Sprint 4 | AI/Brain | Adopt vector search + hybrid retrieval | Move from keyword-only BM25/regex to embeddings (Atlas Vector Search if on Atlas, else Qdrant/pgvector) fused with existing text search. | P1 | AI/Brain/Agentic Review | (new infra) | L | Backlog |  |  |  | No
S4-07 | Sprint 4 | AI/Brain | Formalize a tool registry | The 10 _compute_* + 4 _tool_* handlers already have a clean typed contract — wrap in Pydantic in/out models and register centrally. | P2 | AI/Brain/Agentic Review | routers/brain.py; routers/brain_router.py | M | Backlog |  |  |  | No
S4-08 | Sprint 4 | AI/Brain | Add bounded planner-executor loop + native function-calling | /brain/agent is single-turn (plan -> fan-out -> synthesize, no re-plan). Add an observe-then-replan loop and migrate to Anthropic tools=[...]. | P2 | AI/Brain/Agentic Review | routers/brain_router.py:266-277,481-482 | L | Backlog |  |  |  | No
S4-09 | Sprint 4 | AI/Brain | Add per-conversation agent memory | Every LLM call gets a fresh random session_id; planner and synthesizer don't even share context. | P2 | AI/Brain/Agentic Review | routers/brain_router.py:95,353 | M | Backlog |  |  |  | No
S4-10 | Sprint 4 | AI/Brain | Expand Brain write coverage to finance/workflow/meetings | Only 6 write sites exist today; all payments/invoices/workflow-advance/meetings/ingestion events are invisible to the Brain. | P2 | AI/Brain/Agentic Review | ledger.py:521-838; server.py (workflow advance, meetings) | L | Backlog |  |  |  | No
S4-11 | Sprint 4 | AI/Brain | Make tag vocabulary tenant/industry-configurable | _TAG_VOCAB is 10 hardcoded manufacturing buckets; clinics/restaurants/agencies get silently under-tagged, hurting retrieval recall. | P2 | AI/Brain/Agentic Review | services/brain_context.py:36-47 | M | Backlog |  |  |  | No
S5-01 | Sprint 5 | DevOps/Migration | Stand up a staging environment | Mirror production config/data shape so every fix above is verified before it touches real tenants. | P0 | Go-Live Gate | (infra) | M | Backlog |  |  |  | Yes
S5-02 | Sprint 5 | DevOps/Migration | Run a load test at target scale | Simulate ~100 tenants / concurrent voice-capture + dashboard traffic; this is the single test that most moves go-live confidence. | P0 | Go-Live Gate | (new) | M | Backlog |  |  |  | Yes
S5-03 | Sprint 5 | DevOps/Migration | Add observability (Sentry + structured logs + APM) | No error tracker exists today; you will not learn about production bugs until a customer reports them. | P0 | SaaS Readiness Review | (missing) | M | Backlog |  |  |  | Yes
S5-04 | Sprint 5 | DevOps/Migration | Write + TEST a backup/restore runbook | No documented Mongo backup strategy anywhere. Define RPO/RTO and actually run a restore drill, not just a doc. | P0 | SaaS Readiness Review | (missing) | M | Backlog |  |  |  | Yes
S5-05 | Sprint 5 | DevOps/Migration | Data migration plan for schema changes above | Freeze the production data model, script every schema change introduced in Sprints 0-3 (indexes, new tenant fields, brain_context linkage), dry-run against a staging copy of real-shaped data. | P0 | Go-Live Gate | (new) | L | Backlog |  |  |  | Yes
S5-06 | Sprint 5 | DevOps/Migration | Stand up CI/CD | Build + test + deploy pipeline gated on the existing pytest suite passing; no more manual deploys. | P1 | Go-Live Gate | backend/pytest.ini, backend/tests/ | M | Backlog |  |  |  | Yes
S5-07 | Sprint 5 | DevOps/Migration | Define a rollback procedure | A tested, written-down path to revert a bad deploy fast, including the Sprint 5-05 migrations. | P1 | Go-Live Gate | (new) | S | Backlog |  |  |  | Yes
S5-08 | Sprint 5 | DevOps/Migration | Move secrets to a real secrets manager | Rotate JWT_SECRET/DB creds/API keys out of .env into the platform's secret store; confirm .env is never in the image. | P0 | SaaS Readiness Review | backend/.env, config.py | S | Backlog |  |  |  | Yes
S5-09 | Sprint 5 | DevOps/Migration | Staged rollout plan (5 -> 20 -> 50 -> 100) | Do not flip on 100 clients cold. Roll out in stages with a monitoring checkpoint + explicit go/no-go at each step. | P0 | Go-Live Gate | (process) | S | Backlog |  |  |  | Yes
S5-10 | Sprint 5 | DevOps/Migration | Final go/no-go review | Walk the Go-Live Checklist tab end to end with the team before opening self-serve signup or onboarding client #1. | P0 | Go-Live Gate | (process) | S | Backlog |  |  |  | Yes
RBAC-01 | Sprint 2.5 | Endpoint gate | Auth-gate onboarding drafts | GET/PATCH /onboarding/draft/{draft_id} become 'signed link only': add a signed HMAC on the draft URL (draft_id + issued_at + signature). Only the client that created the draft can read/write. Add rate-limit per IP. Accept: cannot access another draft even with a leaked UUID. | P0 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-A (a44135f).
RBAC-02 | Sprint 2.5 | Endpoint gate | CAPTCHA + IP rate-limit on /register | Turnstile (Cloudflare, free) or hCaptcha on POST /register. IP rate limit: 3 registrations/hour/IP. Accept: bot creating 100 tenants gets blocked at #4. | P0 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-A (a44135f).
RBAC-03 | Sprint 2.5 | Endpoint gate | Auth-gate + rate-limit signup AI endpoints | /website-intel, /signup/tts, /signup/stt need: CAPTCHA on first call per IP + per-IP 10-req/hour ceiling. SSRF guard on /website-intel (block private IP ranges, allowlist protocols). Accept: unauth attacker cannot burn > $0.10 of AI credit. | P0 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-A (a44135f).
RBAC-04 | Sprint 2.5 | Endpoint gate | Symmetric role gate on /workflows create+delete | POST /workflows: add require_perm('workflows') at minimum, ideally require_perm('workflow_create') if we split it. Accept: employee without workflow perm gets 403 on create. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-05 | Sprint 2.5 | Endpoint gate | Gate /captures approve/reject/reassign | Approving/rejecting a capture creates real records — must be require_perm('approvals') or role-gated. Accept: employee without approvals perm gets 403. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-06 | Sprint 2.5 | Endpoint gate | Gate /follow-up/run to owner or team_manage | Manual follow-up trigger burns LLM. Restrict to owner or perm(team_manage). | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-07 | Sprint 2.5 | Endpoint gate | Role gates across tasks router | 17 endpoints in routers/tasks.py are auth-only. Group: reassign + priority-change + delete-execution-plan need perm('team_manage'); prioritize (LLM) needs perm('tasks'). Add explicit decorators. Accept: cross-role matrix test passes. | P1 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-08 | Sprint 2.5 | Endpoint gate | Gate voice/meeting AI on perm(voice_capture) | voice_capture permission exists in PERMISSION_KEYS but only used by 3 endpoints. Add to /voice-notes text+audio and /meetings audio. Accept: perm-less employee can't burn STT credits. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-09 | Sprint 2.5 | Endpoint gate | Add decorator gate to leaves approve/reject | Move inline _can_approve_leave into require_perm('leave_approve'). Keep inline check as defense-in-depth. Accept: reviewer reading the route sees the gate in the signature. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-10 | Sprint 2.5 | Endpoint gate | Split brain export permission | POST /brain/export requires perm('brain_export') (new key) instead of perm('ask'). Accept: user with 'ask' but not 'brain_export' gets 403. | P2 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-11 | Sprint 2.5 | Endpoint gate | Gate memory write on perm(brain) | POST /memory is auth-only. Restrict to perm('brain'). Accept: memory list still readable by all, write gated. | P2 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-C (9b3a1c3).
RBAC-12 | Sprint 2.5 | Data model | Email-per-tenant uniqueness (kill global unique) | Move email uniqueness from `users.email` global unique to compound `(tenant_id, email)`. Register + login flow accept optional tenant hint the same way FIX-003-A did for phones (single-tenant fast path + ambiguity picker for multi-tenant email). Migration ledger entry. Accept: same email registered in 2 workspaces works; login prompts workspace picker. | P0 | RBAC & People Audit | (various) | L | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-B (56399d6). Depends on RBAC-13
RBAC-13 | Sprint 2.5 | Data model | Introduce memberships collection (many-to-many) | New `memberships` collection: {user_id, tenant_id, role, permissions, status, invited_by, invited_at, accepted_at}. `users` collection becomes tenant-agnostic. All find_one({tenant_id, id}) become find_one via memberships. Big refactor — do it BEFORE Sprint 3 billing so plans attach to tenants not users. Accept: full test-suite passes with the new model + a user with 2 memberships can list both from /me/workspaces. | P0 | RBAC & People Audit | (various) | L | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-B (56399d6).
RBAC-14 | Sprint 2.5 | Data model | Per-role permission editor | Store role permissions on tenant.roles[i].permissions[]. New endpoint PATCH /tenant/roles/{key}/permissions. UI on the roles admin page. Accept: editing 'warehouse_manager' to include 'finance' immediately gives every warehouse_manager finance access without touching individual users. | P1 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-D (f440c33). Depends on RBAC-13
RBAC-15 | Sprint 2.5 | Data model | Owner exclusion list | tenant.owner_exclusions[] = ['finance', 'ledger']. user_perms treats owner+exclusion as 'all perms minus exclusion'. Accept: co-founder marked with finance exclusion gets 403 on /ledger. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-D (f440c33).
RBAC-16 | Sprint 2.5 | Data model | Fix ROLES/DEFAULT_ROLES 'production' vs 'operations' | Pick one canonical name. Add migration that renames any existing 'production' role to 'operations' (or vice versa) on tenant.roles + user.role. Accept: grep finds only one canonical name; existing tenants unaffected. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-D (f440c33).
RBAC-17 | Sprint 2.5 | Data model | 'Pending invite' status on user | Add user.invite_status = 'pending' ¦ 'accepted'. Set 'pending' on create-with-invite; flip to 'accepted' on first OTP verify. GET /users returns the flag; admin UI shows a 'Pending' badge. Add resend-invite + revoke-invite endpoints. Accept: invited user shows Pending; revoked user cannot verify. | P1 | RBAC & People Audit | (various) | S | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-004-E (1541439).
RBAC-18 | Sprint 4 | Data model | Department/branch scope on permissions | Add `branches` collection + membership.branch_id + permission modifier '[perm]:branch_X'. Blocks multi-location SMEs. Accept: Finance Manager in Store A sees zero Store B invoices. | P2 | RBAC & People Audit | (various) | L | Backlog |  |  |  | No | Depends on RBAC-13
RBAC-19 | Sprint 4 | Data model | User groups | New `user_groups` collection: {tenant_id, name, member_ids, permissions[]}. user_perms merges (role) + (user override) + (union of groups). Accept: adding 'inventory' perm to 'Regional Managers' group instantly grants it to all group members. | P2 | RBAC & People Audit | (various) | M | Backlog |  |  |  | No | Depends on RBAC-13
RBAC-20 | Sprint 2.5 | Compliance | Immutable audit log (audit_log collection) | New collection audit_log with append-only writes: {actor_id, actor_email, actor_ip, actor_ua, action, entity_type, entity_id, before, after, timestamp, tenant_id}. Wrap every mutating endpoint with a middleware or decorator. Read-only endpoint /admin/audit-log. Accept: deleting a decision leaves an audit row; audit rows cannot be updated/deleted via API. | P0 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-F (cc7c698).
RBAC-21 | Sprint 2.5 | UX + security | /me/sessions endpoint + revoke by device | Track session metadata on jti (device UA, IP, last-seen). Add GET /me/sessions returning active sessions; DELETE /me/sessions/{jti} revokes one; DELETE /me/sessions revokes ALL except current. Uses FIX-003-C session_revocation infra. Accept: user can see + revoke individual devices. | P0 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-G (d95ae44).
RBAC-22 | Sprint 2.5 | UX + security | Off-boarding workflow (deprovisioning wizard) | POST /users/{id}/deprovision runs: revoke all sessions, reassign owned tasks to specified user, transfer in-flight decisions, mark authored contacts as reassigned, invalidate all invite tokens. Idempotent. Owner-only. Accept: after deprovision the departing user has zero owned entities. | P0 | RBAC & People Audit | (various) | L | Done |  | 2026-08-10 | 2026-08-10 | Yes | Shipped in FIX-004-H (309ef84). Depends on RBAC-21
RBAC-23 | Sprint 3 | Security | TOTP-based 2FA | Standard pyotp-based flow: enroll (QR + secret), verify, backup codes. Second-factor on login when enabled. Recovery via email + backup code. Accept: user with 2FA enabled cannot log in with password alone. | P1 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-005-D (a8da19b).
RBAC-24 | Sprint 3 | UX | Ownership transfer flow | POST /tenant/transfer-ownership {new_owner_user_id}: promote target to owner, demote current to specified role, cascade billing rebind. Requires 2FA confirm from current owner. Accept: last owner promoted successfully, previous owner remains as employee. | P1 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-005-D (a8da19b). Depends on RBAC-13
RBAC-25 | Sprint 3 | Compliance | Consent tracking for AI features (DPDP) | tenant.ai_consent = {granted_at, granted_by_user_id, ip, ua, version}. Show a first-run modal 'DecisionOS uses AI (Anthropic) to process operational data. Consent required.' Gate all AI endpoints on tenant.ai_consent. Log revocations. Accept: fresh tenant cannot use /ask until consent granted. | P1 | RBAC & People Audit | (various) | M | Done |  | 2026-08-10 | 2026-08-10 | No | Shipped in FIX-005-C (4115624).
RBAC-26 | Sprint 4 | UX | Approval delegation ('acting-as') | user.acting_as: {delegate_user_id, from, to}. When present, approvals routed to `delegate_user_id`. Combines with leaves. Accept: on-leave approver's tasks auto-route to their delegate; badge shows 'Acting for X'. | P2 | RBAC & People Audit | (various) | M | Backlog |  |  |  | No
RBAC-27 | Sprint 4 | UX | Time-bounded elevated permissions | membership.temp_grants[] = [{perm, granted_by, expires_at, reason}]. Bootstrap TTL sweep to auto-revoke. Audit log entry on grant + revoke. Accept: contractor gets 'finance' perm for 30 days, auto-revoked. | P2 | RBAC & People Audit | (various) | M | Backlog |  |  |  | No | Depends on RBAC-13
RBAC-28 | Sprint 4 | Auth | SSO (Google + Microsoft OAuth) | Add /auth/oauth/{provider}/start + callback. Map OAuth email to user via membership lookup. Handle first-time users (auto-provision if tenant allows). Accept: user with matching email can sign in with Google. | P2 | RBAC & People Audit | (various) | L | Backlog |  |  |  | No | Depends on RBAC-12
RBAC-29 | Sprint 4 | Programmatic | Per-user API keys | New api_keys collection: {user_id, tenant_id, name, prefix, hash, scopes, created_at, last_used_at}. UI to create/revoke. Bearer-token auth reads api_key instead of JWT. Rate limits per key. Accept: script hits /tasks with key, works, revoke kills it. | P2 | RBAC & People Audit | (various) | M | Backlog |  |  |  | No
RBAC-30 | Sprint 5 | UX | Client/customer read-only portal | Share a workflow (procurement order, complaint) with an external email via a signed link. Recipient sees status timeline + can add comments, no login. Accept: customer email link opens read-only page; commenting works without account. | P2 | RBAC & People Audit | (various) | L | Backlog |  |  |  | No

## Fix Log
Fix Log — every change we make, in order
Running record. Updated side-by-side after every shipped commit. Currently: 11 Done, 13 in backlog.
Modules
Module | Name | What it delivers | Priority | Status
Module 1 | Multi-tenant / Dynamic Workflows | DONE. 6 fixes shipped: dynamic per-tenant workflow approval, workflow<->Finance link, tenant-scoped safety helpers, onboarding drafts + AI status tracking, complete tenant deletion (DPDP/GDPR), dynamic terminal stages. Non-textile tenants get their full lifecycle end-to-end. | P0 for selling to any small business that isn't a textile manufacturer. | 6/6 shipped.
Module 2 | Sprint 1 — Scale & Ops | DONE. 6 fixes shipped: phone index (kills full-collection scans), LLM timeouts + concurrency semaphore, migration ledger, distributed leader lock (multi-replica-safe scheduler), obj_store for all uploads, and Dockerfile + Procfile with production-grade signal handling + healthcheck. | Turns 'runs in Sharma demo' into 'survives 100 tenants under real load.' | 6/6 shipped. Sprint 1 COMPLETE.
Module 3 | Sprint 2 – Tenancy & Data | DONE. 12/12 shipped: tenant helpers (FIX-001-C), TENANT_COLLECTIONS wipe (FIX-001-E), OTP+WhatsApp tenant scoping (FIX-003-A), hygiene batch (FIX-003-B), JWT revocation + contact rename + AI regen status (FIX-003-C), email verification + password reset (FIX-003-D). | P0 tenancy bugs closed. Remaining are hardening (session invalidation, email verification, dead index cleanup, denormalized-name staleness) — not blockers for a controlled beta but recommended before wider rollout. | 12/12 shipped. Sprint 2 COMPLETE.
Fix Log entries
Fix ID | Module | Backlog ID | Title | Description | Files touched | Related tests | Status | Priority | Started | Finished | PR / Commit | Notes / gotchas
FIX-001-A | Multi-tenant / Dynamic Workflows | S1-06 | Kill purchase_payment textile hardcode | Owner-approval loop + dashboard + payment-overdue alerts filtered on the literal 'purchase_payment' string — silently broke for non-textile tenants. Fix uses per-tenant pipeline lookup. | routers/decisions.py:166; server.py:2429; routers/brief.py:95,98,238,262 | tests/test_workflows_dynamic.py — 19 tests | Done | P0 | 2026-08-04 | 2026-08-04 | cb84474 + 69f4ce3 | First unblock for selling to any small business that isn't a manufacturer.
FIX-001-B | Multi-tenant / Dynamic Workflows | (discovered mid-fix) | Wire workflow -> Finance auto-expense on procurement completion | Workflow terminal-stage advance auto-creates a pending-bill expense in Finance linked to the workflow. Notifies finance role. Idempotent, fire-and-forget. | server.py:2236; routers/ledger.py:222 | tests/test_workflow_finance_link.py — 17 tests | Done | P1 | 2026-08-04 | 2026-08-09 | 98d0291 | Founder no longer records purchases twice. Bill upload -> OCR promotion flow is a follow-up.
FIX-001-C | Multi-tenant / Data Integrity | S2-01 | Add tenant-scoped safety helpers (_ensure_owned) | Every update_one/delete_* now routed through services/tenancy.py::tenant_filter() which pins BOTH id AND tenant_id. Python TypeError blocks smuggling different tenant_id via extras. | services/tenancy.py (new); ~25 sites across routers + server.py | tests/test_tenancy_helpers.py — 16 tests | Done | P1 | 2026-08-04 | 2026-08-09 | da29cfd | Grep found 25+ sites vs. audit's 13. Discipline lesson: always grep AFTER refactor.
FIX-001-D | Multi-tenant / Onboarding | S1-04 partial + new | Onboarding drafts + AI status tracking + retry endpoint | Two gaps closed: silent AI degradation (ai_setup_status per generator + regenerate endpoint) and data loss on failure (onboarding_drafts persist each wizard step). | services/ai_setup.py + services/onboarding_drafts.py (new); +5 endpoints | tests/test_onboarding_flow.py — 27 tests | Done | P1 | 2026-08-09 | 2026-08-09 | 3bc0059 | Idempotent-register (Comprehensive-scope 3e) and onboarding_drafts TTL deferred.
FIX-001-E | Multi-tenant / Data Integrity | S2-02 | Complete TENANT_COLLECTIONS wipe + file deletion (DPDP/GDPR) | TENANT_COLLECTIONS grown to 30 (was missing brain_context + brain_documents). Now also iterates db.files and deletes each object from storage before wiping. | routers/admin.py; services/obj_store.py::delete_object (new) | tests/test_tenant_deletion.py — 8 tests (incl. drift-detection) | Done | P1 | 2026-08-04 | 2026-08-04 | 65cea2c | Legacy local-disk files depend on Sprint 1 S1-03 to move all uploads to obj_store.
FIX-001-F | Multi-tenant / Dynamic Workflows | WF-3 | Dynamic pipeline terminal stages ('active workflows' stops climbing forever) | 4 places hardcoded ['delivered','paid'] as terminal stages. New services/workflows.py::all_terminal_stages(om) + legacy hedge. All 4 sites now use dynamic exclusion. | services/workflows.py; server.py:2500, :3697, :3745, :3911 | tests/test_workflows_dynamic.py — 12 additional tests | Done | P2 | 2026-08-09 | 2026-08-09 | 8235c61 | Calendar deliveries also hardcodes pipeline TYPES - see FIX-FUP-09.
FIX-002-A | Sprint 1 / Scale & Ops | S1-02 | Phone index + kill full-collection scans on OTP + WhatsApp routing | 3 hot paths (OTP request, OTP verify, resolve_wa_tenant) ran full-collection scans over db.users on every call, capped at 2000/5000 users (silent lockout beyond). Fix indexes new phone_norm field; hot paths become exact-match lookups. Bootstrap includes idempotent backfill for existing users. | services/phone.py (new); server.py bootstrap + 3 hot paths; routers/auth.py; routers/team.py | tests/test_phone_indexed_lookup.py — 16 tests (parity, query shape, no-cap guard) | Done | P0 | 2026-08-09 | 2026-08-09 | e21a9b3 | Existing OTP hashes still verify (parity-tested). server.py:4623 (per-tenant scan) noted but out of scope.
FIX-002-B | Sprint 1 / Scale & Ops | S1-05 | LLM call timeouts + concurrency semaphore | One shared Anthropic key + no timeout + no concurrency cap = 50 concurrent voice captures cascade into 429s and unbounded latency. New services/llm_limits.py::guarded_llm wraps every LLM call with asyncio.wait_for + shared semaphore. Covers _ResilientChat + 4 direct LlmChat sites. | services/llm_limits.py (new); core.py::_ResilientChat; server.py (2 Gemini); routers/admin.py; routers/ledger.py | tests/test_llm_limits.py — 14 tests (peak-concurrency, timeout-releases-slot, exception-releases-slot) | Done | P1 | 2026-08-09 | 2026-08-09 | 6b6fc25 | Per-process only. Cross-process rate limiting needs Redis (Sprint 3 with per-tenant keys). STT paths (Whisper/Sarvam) NOT wrapped - separate follow-up.
FIX-002-C | Sprint 1 / Scale & Ops | (new: raised during Q&A) | Migration ledger for MongoDB schema changes | Ad-hoc bootstrap migrations are fine for additive changes (new fields, new indexes, safe backfills) but unsafe the moment we ship a destructive migration (rename+copy+delete, data reshape). Add db.migrations_applied collection + a migrate(name, fn) helper so migrations run exactly once and non-idempotent changes are safe. | services/migrations.py (new); server.py bootstrap block | tests/test_migrations.py — helper contract + idempotency | Done | P1 | 2026-08-09 | 2026-08-09 | (this commit) | Prerequisite for S1-03 (uploads migration). MongoDB doesn't need Alembic (no DDL) but does need this ledger discipline.
FIX-002-D | Sprint 1 / Scale & Ops | S1-01 | Externalize the follow-up scheduler (multi-replica safe) | In-process 300s loop triple-fires with 3 replicas (duplicate emails/alerts), dies with 1. Options: (a) external cron + endpoint (b) in-process with distributed leader election. Design decision needed. | server.py:2765 (scheduler loop); new endpoint or external cron config | tests: single-fire under multiple simulated replicas | Done | P0 | 2026-08-09 | 2026-08-09 | (this commit) | Half-day fix. Requires design decision on external cron vs leader election.
FIX-002-E | Sprint 1 / Scale & Ops | S1-03 | Migrate all uploads to obj_store (kill local-disk file storage) | Voice notes, meetings, ledger uploads write to local UPLOAD_DIR — lost on restart, invisible across replicas. Route everything through obj_store with tenant-prefixed paths; delete local /api/files path. Includes migration for existing local-disk records. | server.py:1739,1902,3032; ledger.py:146; obj_store integration in all 3 paths | tests: upload, download, cross-replica visibility, deletion | Done | P0 | 2026-08-09 | 2026-08-09 | (this commit) | Half-day. Depends on FIX-002-C for the migration. Also closes FIX-001-E EC8 (legacy local files for tenant deletion).
FIX-002-F | Sprint 1 / Scale & Ops | S1-04 | Commit real Dockerfile + Procfile with pinned worker count + graceful shutdown | No Dockerfile exists (only .emergent/emergent.yml base-image pointer). Need a real deployable Dockerfile with worker count pinned, graceful shutdown for in-flight LLM work, request-size caps. | backend/Dockerfile (new); backend/Procfile (new); backend/.dockerignore (new) | tests/test_dockerfile.py - 25 static contract tests (multi-stage, non-root, healthcheck, secrets, apt cleanup, Procfile parity) | Done | P0 | 2026-08-09 | 2026-08-09 | 5a4644e | Multi-stage Python 3.12-slim build. Non-root user, HEALTHCHECK via Python stdlib on /api/health, tini as PID 1, --timeout-graceful-shutdown 60 (> 45s LLM cap from FIX-002-B). emergentintegrations installed from Emergent's CDN (regression guard: without extra-index-url, requirements install silently drops that package). Docker build not exercised in tests - daemon unavailable in this env; static tests cover structure + security. FIX-FUP-15 logged to wire docker build into CI. SPRINT 1 COMPLETE with this ship.
FIX-FUP-01 | Follow-up (from FIX-001-A) | (logged during A) | Delete WORKFLOW_OWNER_ROLE dead code | server.py:212 defines WORKFLOW_OWNER_ROLE dict - nothing references it. | server.py:212 | test: import check + grep for zero refs | Not Started | P2 |  |  |  | Dead code cleanup.
FIX-FUP-02 | Follow-up (from FIX-001-A) | (logged during A) | Clean 'purchase_payment' from AI onboarding prompt | server.py:1094,1103 - operating-model AI prompt uses 'purchase_payment' as an example. Could bias AI toward textile key. | server.py:1094, 1103 | test: onboard non-textile tenant, assert no 'purchase_payment' in operating_model | Not Started | P2 |  |  |  | Prevents textile leak from re-emerging via the prompt.
FIX-FUP-03 | Follow-up (from FIX-001-A) | (logged during A) | Memoize tenant_procurement_pipeline in brief.py | Called TWICE per brief request (counter + drill-down). Minor inefficiency. | routers/brief.py | test: mock tenant_operating_model, assert called once | Not Started | P2 |  |  |  | Small perf tidy.
FIX-FUP-04 | Follow-up (from FIX-001-B) | (logged during B) | Unique index on expenses.(tenant_id, workflow_id) | Check + insert is not atomic. Rare race could double-create. Close with unique compound index. | server.py bootstrap | test: concurrent create_expense with same workflow_id | Not Started | P2 |  |  |  | Belt-and-braces for FIX-001-B idempotency.
FIX-FUP-05 | Follow-up (from FIX-001-B) | (logged during B) | Bill upload -> OCR promotion flow (Finance side) | Complete the story: Finance uploads bill, OCR extracts real amount, expense flips from awaiting_bill to reconciled. | routers/ledger.py + existing OCR pipeline | test: mock OCR + upload + status transition | Not Started | P1 |  |  |  | One-click reconciliation finish for FIX-001-B.
FIX-FUP-06 | Follow-up (from FIX-001-C) | (logged during C) | 'id' footgun in tenant_filter | Extras can overwrite id (though tenant scope still holds). Documented in tests; stricter version would reject. | services/tenancy.py | test already documents | Not Started | P2 |  |  |  | Cosmetic hardening.
FIX-FUP-07 | Follow-up (from FIX-001-D) | (logged during D) | TTL index on onboarding_drafts | Auto-expire ~30 days after last update. Bootstrap: create_index('updated_at', expireAfterSeconds=30*86400). | server.py bootstrap | test: verify index exists | Not Started | P2 |  |  |  | Small bootstrap tweak.
FIX-FUP-08 | Follow-up (from FIX-001-D) | (logged during D) | Idempotent register by draft_id (Comprehensive-scope 3e) | Network drop mid-register -> user retries -> 'Email already registered' 400. Fix: if draft completed with tenant_id, return existing session on retry. | routers/auth.py::register | test: register with draft_id twice, second returns existing tenant | Not Started | P1 |  |  |  | Closes the last onboarding-flow paper cut.
FIX-FUP-09 | Follow-up (from FIX-001-F) | (logged during F) | tenant_sales_pipeline resolver (mirror of procurement) | Calendar deliveries hardcodes pipeline TYPES ['distribution','sales_dispatch']. Add resolver like tenant_procurement_pipeline. | services/workflows.py; calendar endpoint | tests: bakery order_fulfilment shows in calendar deliveries | Not Started | P2 |  |  |  | Extends FIX-001-A pattern to sales side.
FIX-FUP-10 | Follow-up (from FIX-002-A) | (logged during 002-A) | phone_norm on WhatsApp review UI + contact lookups | server.py:4623 builds a phone_index for the WA review UI via Python-side normalization. Tenant-scoped (not a P0 like the global hot paths) but same pattern. | server.py:4623 area | test: query uses phone_norm | Not Started | P2 |  |  |  | Consistency win, not a P0.
FIX-FUP-11 | Follow-up (from FIX-002-B) | (logged during 002-B) | Guard STT (Whisper/Sarvam) paths with llm_limits | The FIX-002-B semaphore/timeout covers LlmChat paths. STT goes through OpenAISpeechToText and Sarvam wrappers separately - not yet guarded. | server.py transcribe_audio_full and Sarvam wrapper | test: mock STT, assert guarded_llm called | Not Started | P2 |  |  |  | ~1 hour when someone hits an STT rate limit.
FIX-FUP-12 | Follow-up (from FIX-002-B) | (logged during 002-B) | Cross-process LLM rate limiting (Redis-backed) | Semaphore is per-process. With multiple uvicorn workers, total in-flight = workers x cap. Ties to Sprint 3 (per-tenant AI keys) so per-tenant caps become meaningful. | new services/llm_limits.py extension + Redis | test: distributed semaphore behavior | Not Started | P1 |  |  |  | Sprint 3 territory.
FIX-FUP-13 | Follow-up (from FIX-002-F) | (logged during 002-F local run) | Frontend install hardening: legacy-peer-deps | npm install silently exited 0 with 0 packages because react-day-picker@8 peer-requires date-fns@^2¦¦^3 but this project uses date-fns@4. Added frontend/.npmrc with legacy-peer-deps=true so every dev + CI `npm install` runs without needing --legacy-peer-deps flag. | frontend/.npmrc (new) | manual: npm install now completes (was silent 0-package exit) | Done | P0 | 2026-08-09 | 2026-08-09 | 5a4644e | The trap that blocked our first local frontend boot. Locked in as .npmrc so it doesn't happen again.
FIX-FUP-14 | Follow-up (from FIX-002-F) | (logged during 002-F local run) | Pin ajv@^8.20.0 across the tree (webpack crash fix) | ajv-keywords@5 needs `ajv/dist/compile/codegen` (ajv v8), but a nested dep resolved ajv@6, causing webpack to crash on start with `Cannot find module ajv/dist/compile/codegen`. Added overrides.ajv (npm) + resolutions.ajv (yarn) both set to ^8.20.0 to force v8 across the dep tree. | frontend/package.json (overrides + resolutions blocks) | manual: npm ls ajv shows ajv@8.20.0 at root + ajv-keywords@5.1.0 -> ajv@8 deduped | Done | P0 | 2026-08-09 | 2026-08-09 | 5a4644e | Value must match the direct dep pinning exactly (^8.20.0) or npm throws EOVERRIDE. Learned that mid-fix.
Status legend:
Not Started | In backlog, no work yet
Planning | Reading code, scoping the fix, drafting approach
In Progress | Writing the fix
Code Review | Fix written, awaiting review / self-review
Testing | Tests running
Done | Merged + tests green + verified
Blocked | Waiting on external dependency or decision
Rolled Back | Shipped, broke something, reverted (record, don't hide)
FIX-FUP-15 | Follow-up (from FIX-002-F) | (logged during 002-F QA) | Wire `docker build` into CI (real container smoke test) | FIX-002-F ships 25 static contract tests on the Dockerfile because Docker daemon isn't available in this test environment. That's fine as a first line of defense but doesn't catch runtime failures (missing apt package, wheel install failing, base-image tag drift). Once CI is stood up (S5-06), a job should build the image, run `docker run --rm ... /api/health`, and gate merges on it. | (CI config; new; blocked on S5-06 CI/CD setup) | smoke: docker build succeeds + healthcheck returns 200 in <60s | Not Started | P1 |  |  |  | Depends on S5-06 (Stand up CI/CD). Until then, the static tests are the guardrail.
FIX-003-A | Sprint 2 / Tenancy & Data | S2-03 + S2-04 | Tenant-scope OTP + WhatsApp phone routing | Phone was treated as a global identifier. Two users in different tenants sharing a phone collided: OTP overwrote each other's codes; verify returned first-match user across tenants; resolve_wa_tenant silently orphaned the losing tenant's user by marking them wa_phone_obsolete. Also folded S2-04: whatsapp_logs OR-included tenant_id=None events, leaking platform-wide unrouted traffic into every tenant's log view. Fix: phone is unique WITHIN a tenant. New services/phone.find_tenant_choices_for_phone as single choke-point. OTP models accept optional tenant_id; single-tenant fast path unchanged, multi-tenant returns ambiguity payload (200 for request, 409 for verify). otp_codes now keyed by (phone, tenant_id) with new compound unique index + migration otp_codes_tenant_scope_v1. resolve_wa_tenant cross-tenant collision: notifies BOTH tenant owners, falls back to WA_TENANT_ID, does NOT mark anyone obsolete. Within-tenant dedup still works with defense-in-depth tenant_id guard on update_many. whatsapp_logs strict tenant_id filter. | services/phone.py (find_tenant_choices_for_phone); server.py: OtpRequestInput/OtpVerifyInput (tenant_id field), _issue_otp (compound key + required tenant_id), /auth/otp/request (ambiguity + tenant_id validation), /auth/otp/verify (compound key + 409 ambiguity), /auth/invite/{token}/start (uses invite's tenant), resolve_wa_tenant (cross-tenant safety + tenant-guarded update_many + invited_employees safety), whatsapp_logs (strict filter), _bootstrap (new migration + compound index) | tests/test_tenant_phone_routing.py - 22 tests (helper contract, OTP model + handler source-level invariants, resolve_wa_tenant cross-tenant safety across 7 scenarios, whatsapp_logs regression guard, bootstrap wiring) | Done | P0 | 2026-08-09 | 2026-08-09 | 6a1ecec | Bundles S2-03 (P0) with S2-04 (P1) since they share the same code area. Handler source-level assertions are the primary lock-in; live-HTTP integration tests (test_iteration29/30) run only in the deployed env — logged as FIX-FUP-16. Per-tenant WABA is Sprint 3 (FIX-FUP-17).
FIX-FUP-16 | Follow-up (from FIX-003-A) | (logged during 003-A) | Update deployed integration tests to send tenant_id on OTP flows | tests/test_iteration29.py + test_iteration30.py are live-HTTP tests against /app/backend/.env (Linux paths, deployed-only). They hit /auth/otp/request + /auth/otp/verify without tenant_id. In a single-tenant deployed env they still pass (fast path), but a multi-tenant fixture would need tenant_id threading. Update once a staging env with multiple tenants is available. | tests/test_iteration29.py, tests/test_iteration30.py | test: multi-tenant OTP flow with tenant_id param passes | Not Started | P2 |  |  |  | Blocked on S5-01 (Stand up staging env). Single-tenant deployments unaffected.
FIX-FUP-17 | Follow-up (from FIX-003-A) | (logged during 003-A) | Per-tenant WhatsApp Business Account (WABA) provisioning | Today WA_PHONE_NUMBER_ID is a platform-level env var. That means the whole platform runs against ONE Meta WABA and sender-phone is the only signal we have for tenant routing. If each tenant provisions their OWN WABA + business number, we can route by the RECEIVING business number (which Meta sends in webhook value.metadata.phone_number_id) instead of the sender's phone. Eliminates cross-tenant collisions entirely — a phone can be an employee in workspace A and a supplier in workspace B without ambiguity because Meta tells us which of OUR numbers the message hit. Requires: schema change (tenants.wa_phone_number_id), settings UI, onboarding flow to link a Meta WABA, and updating resolve_wa_tenant to prefer receiving-number lookup. | server.py resolve_wa_tenant (add receiving_pnid arg); routers/tenant (settings UI to save wa_phone_number_id); webhook to extract value.metadata.phone_number_id and pass through | test: two tenants with distinct wa_phone_number_id -> messages route correctly; same sender phone across both -> each tenant gets their own message | Not Started | P1 |  |  |  | Sprint 3 territory (S3-03 or new S3-05). Removes the whole class of cross-tenant WhatsApp collision.
FIX-003-B | Sprint 2 / Tenancy Hygiene | S2-05 + S2-08 + S2-10 + S2-12 | Sprint 2 hygiene batch: enrich_decisions tenant guard, contacts.type index, register race, active-workflow lock-in | S2-05 defense-in-depth: enrich_decision(s) now filter task_ids/created_by lookups by tenant_id; batch inference for single-tenant callers who forget; explicit at all 6 caller sites. S2-08: contacts index was on dead field `kind` (the collection uses `type`); replaced + drops legacy. S2-10: register handler was find_one-then-insert_one with orphan-tenant risk on concurrent race; now catches DuplicateKeyError, rolls back the orphan tenant, returns friendly 400. S2-12: verified S2-12 was fully closed by FIX-001-F and locked it in with a regression test guarding against ['delivered','paid'] reappearing anywhere in server.py. | server.py (enrich_decision(s) + know360 caller + owner_brief caller + contacts index in bootstrap); routers/decisions.py (6 enrich_decision callers); routers/brief.py (awaiting_approval); routers/auth.py (register DuplicateKeyError handling + orphan tenant rollback) | tests/test_tenancy_hygiene_batch.py - 10 tests (4x enrich_decision tenant guard incl. batch inference + mixed-batch + creator lookup, 2x contacts.type index bootstrap, 2x register DuplicateKeyError + rollback + email unique index invariant, 2x active-workflow lock-in) | Done | P1 | 2026-08-10 | 2026-08-10 | f18bbc3 | Bundled 4 small Sprint 2 items. All P1/P2, no go-live blocker individually; bundled for efficiency. S2-12 was already implemented by FIX-001-F; this ship formalized the regression guard.
FIX-003-C | Sprint 2 / Auth & Hygiene | S2-06 + S2-09 + S2-11 | JWT revocation on logout + contact rename cascade + AI regen failure flag | S2-06 (security): /logout only cleared browser cookie; JWT stayed valid until exp (7 days). Now: every access token gains a random jti; /logout records (jti, exp) in db.revoked_tokens; get_current_user checks is_revoked on every authenticated request. TTL index on revoked_tokens.exp keeps the table bounded. Fail-open on Mongo blip so a transient DB error doesn't lock everyone out. /logout has no auth dependency so a corrupted/already-revoked token can still clear the cookie. S2-09: contact_name is denormalized into invoices/payments/workflows.counterparty; renaming a contact left every existing row with stale display + search columns. update_contact now cascades: match by contact_id (recent rows) + fall back to exact old_name where contact_id is null (legacy rows). Every cascade update is tenant-scoped. S2-11: regenerate_operating_model + regenerate_finance_categories called AI generators directly, so silent AI degradation (timeout, malformed JSON, empty pipelines) left tenants with default configs and no signal. Now uses ai_setup._with_status wrappers, persists ai_setup_status on tenant, returns ai_setup_status_summary in response. On defaulted/failed run, preserves existing config instead of clobbering. | services/session_revocation.py (new: revoke/is_revoked with fail-open); core.py (create_token adds jti, get_current_user checks is_revoked); routers/auth.py (/logout revokes current jti + Request import); server.py (bootstrap: revoked_tokens jti unique + exp TTL indexes; regenerate_operating_model + regenerate_finance_categories status-tracking; update_contact rename cascade) | tests/test_session_revocation.py - 17 tests (6 revoke/is_revoked contract, 2 jti in create_token, 2 /logout revocation + no auth dep, 1 get_current_user revocation check, 1 bootstrap indexes, 2 contact rename cascade guards, 3 AI regen status tracking) | Done | P1 | 2026-08-10 | 2026-08-10 | f48bd24 | S2-06 is the real security fix in this batch. Sprint 2 now 11/12 shipped; only S2-07 (email verification + password reset, green-field email service) remains.
FIX-003-D | Sprint 2 / Email + Auth | S2-07 | Email verification + password reset (green-field) | New auth flows built from scratch. services/auth_emails.py provides a single token model for both flows: auth_email_tokens keyed by URL-safe 32-char token (secrets.token_urlsafe(24) = ~192 bits entropy), single-use consume() with atomic filter on used_at:None, issue() idempotent within cooldown to prevent inbox flood. TTLs differ by kind: email_verify=3 days, password_reset=1 hour. 4 endpoints on routers/auth.py: POST /auth/email/send-verification (authenticated), GET /auth/email/verify/{token} (public), POST /auth/password/forgot (public, canonical response = no email enumeration), POST /auth/password/reset (public, single-use + invalidates sibling reset tokens). Register hook: verification email sent best-effort on /auth/register (SMTP down never fails registration). 3 bootstrap indexes: token unique, expires_at TTL, kind+email+used_at compound for issue reuse lookup. Passwordless (OTP-only) accounts get canonical /forgot response but no email + explicit refusal on /reset. | services/auth_emails.py (new: token model + email templates); routers/auth.py (PasswordForgotInput/PasswordResetInput models, 4 new endpoints, register hook, _app_base_url helper); server.py (3 auth_email_tokens indexes in bootstrap) | tests/test_email_verification_and_reset.py - 23 tests (8 issue contract, 5 consume single-use + failure modes, 1 invalidate isolation, 5 endpoint shape guards, 1 register best-effort, 1 bootstrap indexes, 2 email templates) | Done | P1 | 2026-08-10 | 2026-08-10 | 4ef865e | SPRINT 2 COMPLETE (12/12). Green-field build. Follow-ups: FIX-FUP-18 per-IP rate limit on /forgot; FIX-FUP-19 frontend /verify-email + /reset-password pages.
FIX-FUP-18 | Follow-up (from FIX-003-D) | (logged during 003-D) | Per-IP rate limit on /auth/password/forgot | Today the throttle is per-account via services.auth_emails.issue() cooldown (60s). That prevents inbox spam for one target, but an attacker cycling emails can still overwhelm SMTP quota. Add IP-based rate limit (e.g. 10 requests/hour) via a middleware or a small in-process counter. | middleware or routers/auth.py | test: 11 rapid requests from same IP -> 11th returns 429 | Not Started | P2 |  |  |  | Sprint 0/security territory; not a go-live blocker for controlled beta.
FIX-FUP-19 | Follow-up (from FIX-003-D) | (logged during 003-D) | Frontend pages: /verify-email + /reset-password | Backend links point at APP_BASE_URL/verify-email?token=... and APP_BASE_URL/reset-password?token=... but no frontend routes exist yet. Add: two lightweight pages that read the token from the query string, call GET /api/auth/email/verify/{token} or POST /api/auth/password/reset respectively, and show success/error UI. | frontend/src/App.js routes; new components | manual: click a verification email link -> success page renders | Not Started | P1 |  |  |  | Backend is complete and callable via curl; frontend pages are the last mile for users.
FIX-004-A | Sprint 2.5 / RBAC Wave 1 | RBAC-01 + RBAC-02 + RBAC-03 | RBAC Wave 1: HMAC-signed drafts + CAPTCHA/rate-limit register + SSRF-guarded signup AI | 3 P0 public-endpoint gaps closed. RBAC-01: onboarding drafts were world-accessible by ID; now HMAC-signed X-Draft-Token required on GET/PATCH + per-IP rate limit on create. RBAC-02: /register was unauth + unlimited; now Turnstile/hCaptcha token verification + 3/hour/IP rate limit. RBAC-03: signup AI endpoints (website-intel, tts, stt, interview/*) were unauth credit-burners; now shared _guard_signup_endpoint dep runs hourly (30/IP) + burst (5/10s) rate-limit + CAPTCHA. website-intel gains SSRF guard blocking private v4/v6 ranges, loopback, link-local, cloud-metadata IPs (169.254.169.254), and non-http(s) schemes. Also introduces reusable infra: services/rate_limit.py (sliding-window, fail-open), services/captcha.py (Turnstile/hCaptcha with 3 env states), services/ssrf_guard.py (single choke-point URL validator), services/auth/draft_tokens.py (HMAC sign/verify). All will be reused by RBAC Waves 2-5. | services/rate_limit.py (new); services/captcha.py (new); services/ssrf_guard.py (new); services/auth/draft_tokens.py (new); services/auth/__init__.py (exports); routers/onboarding.py (draft token + rate limit); routers/auth.py (register captcha + rate limit); routers/signup.py (guard + SSRF on 9 endpoints) | tests/test_rbac_wave1.py - 41 tests (9 rate_limit contract + client_ip variants, 5 captcha env-state combos, 10 SSRF guard incl. v6 loopback + link-local, 7 draft tokens, 5 onboarding gate, 2 register gate, 3 signup AI gate) | Done | P0 | 2026-08-10 | 2026-08-10 | a44135f | Backend-complete. FIX-FUP-20 tracks the frontend integration (Turnstile widget, X-Draft-Token header, X-Captcha-Token header). Rate limiter is per-worker; Redis backend logged as FIX-FUP-21 for multi-worker deploys.
FIX-FUP-20 | Follow-up (from FIX-004-A) | (logged during Wave 1) | Frontend integration for RBAC Wave 1 (CAPTCHA widget + auth headers) | Backend is complete but the frontend needs 3 updates: (a) onboarding wizard stores the draft_token returned from POST /onboarding/draft, sends X-Draft-Token on every subsequent GET/PATCH; (b) /register page renders a Cloudflare Turnstile widget (free, invisible for most users), passes the resulting captcha_token in the request body; (c) /signup wizard renders same widget on first AI call per session, passes the resulting token via X-Captcha-Token header. Without these, the frontend will fail against a prod backend that has CAPTCHA_REQUIRED=1. | frontend/src pages: OnboardingWizard, Register, Signup | manual: form submits succeed; loading Turnstile in dev works | Not Started | P1 |  |  |  | Backend is deployed-ready in permissive mode today; frontend fix required before flipping CAPTCHA_REQUIRED=1 in prod.
FIX-FUP-21 | Follow-up (from FIX-004-A) | (logged during Wave 1) | Cross-process rate limiter (Redis backend) | Current services/rate_limit.py is in-process. With N uvicorn workers the effective per-IP ceiling is N*cap. Fine for the current unauth surface (a bot burst is spread across workers roughly evenly), but not correct. Replace with a Redis-backed sliding window using INCR + EXPIRE or a Lua script. Same public API so no caller changes. | services/rate_limit.py | test: 3-worker simulation, verify shared counter | Not Started | P2 |  |  |  | Sprint 3+ territory when we scale beyond 1 worker per instance.
FIX-FUP-22 | Follow-up (from FIX-004-A) | (logged during Wave 1) | SSRF guard v2: pin resolved IP through httpx transport | Current is_url_safe_for_fetch resolves hostname + checks IPs, then httpx.get re-resolves independently. In the ~100ms gap between check + fetch, a hostile DNS server could re-flip the record from public to private. Fix: use httpx transport with a custom Resolver that reuses the resolved IPs from is_url_safe_for_fetch (or pass resolved IP + Host header separately). Adds SNI + Host complexity. | services/ssrf_guard.py, routers/signup.py | test: TOCTOU race simulator with a mock resolver flipping IPs mid-call | Not Started | P2 |  |  |  | Current guard is fine for the SME-scale threat model; hardening is nice-to-have.
FIX-004-B | Sprint 2.5 / RBAC Wave 2 | RBAC-12 + RBAC-13 | Memberships collection + email-per-person (many-to-many user↔tenant) | Big data-model refactor that unblocks every remaining multi-workspace fix. Before: user.tenant_id single FK + users.email globally unique = one email = one person = one workspace forever. After: new memberships collection (user_id, tenant_id, role, permissions, status, invite metadata) with compound unique. users.email still globally unique (one PERSON per email) but that person can belong to N workspaces via N membership rows. Unlocks accountants serving multiple SMEs, founders with 2 businesses, employee invited to 2nd workspace. get_current_user projects role/permissions from CURRENT membership onto user dict — ~430 downstream call sites keep working unchanged (compat layer). Only login + register + user CRUD + invite flow have real logic changes. Bootstrap: 3 new indexes + backfill_memberships_v1 migration (via FIX-002-C ledger). New endpoints: GET /me/workspaces + POST /me/switch-workspace. Login gains optional tenant_id in body; multi-membership + no hint returns ambiguity payload for the frontend picker. | services/auth/membership.py (new: full service + compat helper); services/auth/__init__.py (exports); core.py (get_current_user resolves membership + projects onto user + legacy fallback); server.py (bootstrap: 3 indexes + backfill migration); routers/auth.py (register creates owner membership + rollback; login ambiguity; /me/workspaces; /me/switch-workspace); routers/team.py (create_user creates membership; update_user mirrors role/perm changes) | tests/test_memberships_wave2.py — 29 tests (5 create incl. idempotent + reactivate, 2 find + status filter, 2 list-for-user, 3 resolve_login_choices, 2 update, 2 remove soft-delete, 2 project, 1 bootstrap, 1 register+rollback, 2 login flow, 3 workspace endpoints, 2 get_current_user, 2 team mirroring) | Done | P0 | 2026-08-10 | 2026-08-10 | 56399d6 | Blocks-go-live P0. Sprint 2.5 now 5/20 shipped (Waves 1 + 2). Compat layer keeps 349/349 offline regression green — downstream refactor is optional and can happen incrementally. Frontend integration (workspace switcher UI, ambiguity picker on login) is FIX-FUP-25.
FIX-FUP-23 | Follow-up (from FIX-004-B) | (logged during Wave 2) | OTP verify: read role from membership directly (not via compat) | Today OTP verify still reads user.role via the get_current_user compat layer projection. Correct behavior, but the code reads clearer if we look up the membership explicitly for role. Small cleanup — trivial once every downstream reader is migrated off user.tenant_id/role. | server.py verify_otp handler | test: OTP verify returns correct role when user has multi-tenant | Not Started | P2 |  |  |  | Cosmetic; correct behavior today.
FIX-FUP-24 | Follow-up (from FIX-004-B) | (logged during Wave 2) | Cascade: delete memberships on user delete | Currently memberships are soft-deleted (status=removed) when a tenant admin removes an employee. There's no path yet to delete the USER (person) — that comes with RBAC-22 (off-boarding wizard) in Wave 4. When we get there, need to decide: delete all their memberships? preserve for audit? Also cascade rules if a TENANT is deleted (currently TENANT_COLLECTIONS wipe should include memberships). | routers/admin.py TENANT_COLLECTIONS, routers/team.py user delete path | test: tenant delete wipes all memberships for that tenant | Not Started | P1 |  |  |  | Blocks RBAC-22 off-boarding (Wave 4).
FIX-FUP-25 | Follow-up (from FIX-004-B) | (logged during Wave 2) | Frontend: workspace switcher UI + login ambiguity picker | Backend is ready. Frontend needs: (a) login page handles the {ambiguous: true, choices: [...]} response and renders a workspace-picker; (b) top-bar workspace switcher calls GET /me/workspaces and POST /me/switch-workspace; (c) invited-user landing UI (post-OTP) if a person now holds multiple memberships. Also update the frontend register form: when a user with an existing email hits /register, show the friendly 'log in first + then Settings > Create Workspace' message. | frontend/src pages: Login, TopBar, Settings, Register | manual: log in as user with 2 memberships, verify picker + switch | Not Started | P1 |  |  |  | Backend accepts current single-membership frontend unchanged; frontend can ship this incrementally.
FIX-004-C | Sprint 2.5 / RBAC Wave 3 sub-batch A | RBAC-04..11 (8 items) | Wave 3 endpoint gates: 8 auth-only endpoints upgraded to role/perm gated | Closes every 'auth-only endpoint that should be role/perm-gated' finding from the RBAC audit sweep. 8 items in one commit because they share the same testing infrastructure (cross-role permission matrix). RBAC-04 /workflows POST -> require_perm(workflows) [symmetric with DELETE which was already owner]. RBAC-05 /captures/{id}/approve¦reject¦reassign¦clarify -> require_perm(approvals). RBAC-06 /follow-up/run -> require_perm(team_manage). RBAC-07 4 of 17 tasks endpoints upgraded (delete_task role(owner), reassign/delete-plan/prioritize require_perm(team_manage)); other 13 remain auth-only with inline scope checks because widening would break normal workflow. RBAC-08 /meetings + /meetings/text -> require_perm(voice_capture) [matches /voice-notes]. RBAC-09 /leaves approve/reject/request-info -> require_perm(leave_approve) [decorator gate; inline _can_approve_leave stays as defense-in-depth]. RBAC-10 /brain/export -> require_perm(brain_export) [NEW permission key added to config; NOT in _BASE_PERMS so owner-only or explicit grant]. RBAC-11 /memory POST -> require_perm(brain) [read stays open]. | config.py (brain_export in PERMISSION_KEYS); server.py (create_workflow, 4 captures, followup_run, 2 meetings, add_memory); routers/tasks.py (delete_task, reassign_task, delete_execution_plan, prioritize_tasks + require_role/require_perm imports); routers/team.py (3 leaves endpoints); routers/brain.py (/brain/export) | tests/test_rbac_wave3_gates.py — 22 tests (3 config lock-in incl. brain_export not-in-base, 11 per-endpoint dep verification for all 8 RBAC-IDs, 6 cross-role permission matrix incl. owner all-perms + sales/finance defaults + custom role fallback + explicit grant override + brain_export explicit-grant-only, 2 regression on existing gates) | Done | P1 | 2026-08-10 | 2026-08-10 | 9b3a1c3 | Sprint 2.5 now 13/20 shipped (Waves 1+2 + Wave 3 sub-batch A). Sub-batches B (per-role perm editor + owner exclusion + ROLES fix) and C (pending-invite visibility) remain. Cross-role matrix test is the regression harness — any new endpoint added later must add a matrix row.
FIX-004-D | Sprint 2.5 / RBAC Wave 3 sub-batch B | RBAC-14 + RBAC-15 + RBAC-16 | Role model: per-role permission editor + owner exclusions + production→operations canonical rename | Wave 2 memberships made these possible; this fix ships them. RBAC-14: tenant.roles[i].permissions[] carries role-level perms. NEW endpoint PATCH /tenant/roles/{key}/permissions (team_manage). user_perms() 5-tier precedence: owner all-minus-exclusions -> user override -> tenant role map -> ROLE_DEFAULT_PERMS -> _BASE_PERMS. Custom roles ('warehouse_manager') can now carry finance/ledger/team_manage etc. without editing each user individually — a role is a policy unit again. RBAC-15: tenant.owner_exclusions:[str] lets a tenant deny specific perms to owner(s). NEW endpoint PUT /tenant/owner-exclusions (owner-only). Backward compat: empty list = classic all-perms owner. Solves 'co-founder with everything except finance visibility'. RBAC-16: canonical role name = 'operations' (matches DEFAULT_ROLES). config.ROLES rewritten. Bootstrap migration rename_production_role_v1 (via FIX-002-C ledger) rewrites tenant.roles[].key + users.role + memberships.role. Idempotent. | config.py (ROLES canonical); core.py (get_current_user fetches tenant roles + owner_exclusions + populates _role_perms_map/_owner_exclusions on user; user_perms rewritten with 5-tier precedence); server.py (2 new endpoints: PATCH /tenant/roles/{key}/permissions + PUT /tenant/owner-exclusions; bootstrap rename_production_role_v1 migration) | tests/test_rbac_wave3_role_model.py — 16 tests (8 per-role perms incl. precedence + endpoint gates, 5 owner exclusions incl. backward compat + PUT semantic + owner-only, 2 canonical rename + migration wiring, 1 get_current_user enrichment) | Done | P1 | 2026-08-10 | 2026-08-10 | f440c33 | Sprint 2.5 now 16/20 shipped (Waves 1+2 + Wave 3 A+B). Only Wave 3 sub-batch C (RBAC-17) remains in Wave 3. Frontend Settings UI logged as FIX-FUP-26.
FIX-FUP-26 | Follow-up (from FIX-004-D) | (logged during Wave 3-B) | Frontend Settings UI: per-role permission editor + owner exclusions | Backend endpoints ship in FIX-004-D. Frontend needs: (a) Team & Roles settings page adds a permission-checkbox matrix per tenant role, POSTs to PATCH /tenant/roles/{key}/permissions; (b) Owner settings page adds an exclusion-checkbox list, PUTs to /tenant/owner-exclusions. Admins can already call the endpoints via curl but the UX story isn't complete until the UI ships. | frontend/src pages: Settings, Team, Roles | manual: edit a role's perms in UI, verify a member's effective perms reflect the change on next request | Not Started | P1 |  |  |  | Backend is deploy-ready; UI blocks non-technical admin usage.
FIX-004-E | Sprint 2.5 / RBAC Wave 3 sub-batch C | RBAC-17 | Pending-invite visibility on GET /users + POST /users/{id}/uninvite | Small ship that surfaces what Wave 2 already made possible. GET /users now merges membership.status onto each user (pending¦active¦suspended¦removed excluded) + invited_at + accepted_at so admin UI can render a Pending badge. Legacy users without membership rows default to 'active'. NEW endpoint POST /users/{id}/uninvite (team_manage) revokes a pending invite: soft-deletes membership + wipes invite_token on user doc so the invite URL stops resolving. Refuses non-pending targets (use suspend/delete instead). Emits log_activity('user_uninvited'). | routers/team.py (list_users enrichment + new uninvite_user endpoint) | tests/test_rbac_wave3_invite_status.py — 8 tests (3 list enrichment, 5 uninvite gate/refusal/token-invalidation/logging) | Done | P1 | 2026-08-10 | 2026-08-10 | 1541439 | Sprint 2.5 now 17/20 shipped. RBAC Wave 3 COMPLETE. Remaining: RBAC-18 department scope (Sprint 4), RBAC-19 user groups (Sprint 4), RBAC-30 customer portal (Sprint 5).
FIX-004-F | Sprint 2.5 / RBAC Wave 4-A | RBAC-20 | Immutable audit log (SOC2/DPDP/GDPR compliance) | New services/audit_log.py: append-only, best-effort record() + tenant-scoped query() + context_from() request/user extractor. Fail-open by design — Mongo hiccup during audit write must not fail user action. NEVER raises. 35 canonical action names in ACTIONS registry for review-time typo catch. Bootstrap creates 3 indexes: (tenant_id, ts DESC), (actor_id, ts DESC), (tenant_id, entity_type, entity_id). NO TTL (rows live forever for compliance). NO PATCH/DELETE endpoints — API-layer append-only; tampering requires DB access. GET /admin/audit-log endpoint (owner-only) supports action/actor_id/entity_type/entity_id/since_ts/before_ts filters + limit (capped 500) + cursor paging. High-value events wired to record() this ship: login_success + login_failure (captures attempted email on unknown user), logout (records even on invalid token), tenant_created + user_created on register, owner_exclusions_updated with before/after diff. Expanding call-site coverage to user_deleted / role_deleted / decision_approved / etc. logged as FIX-FUP-27 — 3-line change per event, non-blocker. | services/audit_log.py (new); server.py (bootstrap: 3 indexes + GET /admin/audit-log endpoint + owner_exclusions audit wire); routers/auth.py (login success + failure audit, logout audit, register tenant+user audit) | tests/test_audit_log.py — 24 tests (5 record contract incl. fail-open + string caps, 6 query contract incl. tenant isolation + paging, 4 context_from variants, 1 bootstrap, 3 endpoint incl. no-PATCH/DELETE guard, 5 wire-up on login/logout/register/owner-exclusions) | Done | P0 | 2026-08-10 | 2026-08-10 | cc7c698 | Sprint 2.5 now 18/20 shipped. Wave 4 sub-batch 1/3 done — sub-batches G (session mgmt UI, RBAC-21) and H (off-boarding wizard, RBAC-22) remain. Blocks-go-live P0 requirement for SOC 2 / DPDP compliance now met.
FIX-FUP-27 | Follow-up (from FIX-004-F) | (logged during Wave 4-A) | Expand audit_log.record() call-site coverage across mutating events | Wave 4-A ships the audit-log service + 4 high-value event call sites (login, logout, register, owner-exclusions). Progressive coverage needed on the rest of the ACTIONS registry: user_deleted, user_uninvited, role_deleted, role_permissions_updated, decision_approved/rejected, capture_approved/rejected, workflow_deleted, task_deleted, tenant_deleted (from admin.py), platform_admin_tenant_wipe, ai_key_updated. Each is a 3-line change: audit_log.context_from(request, user) + await record(db, action='...', entity_type='...', entity_id='...', before/after, **ctx). Non-blocker — infra is ready, incremental fill-in. | routers/admin.py, routers/team.py, routers/decisions.py, routers/tasks.py, server.py | test: each new call site verified via grep + one integration assertion per event | Not Started | P1 |  |  |  | Post-FIX-004-F incremental. Ship as batches of 3-4 events per commit.
FIX-FUP-28 | Follow-up (from FIX-004-F) | (logged during Wave 4-A) | Audit log retention policy (TTL + off-hot-storage archive) | Currently audit_log has NO TTL — rows live forever. Compliance regimes (SOC 2, DPDP) require min retention (12-24 months typically) but max retention is a business decision (privacy vs forensics tradeoff). Also: hot Mongo isn't the cheapest place to keep 5-year audit history. Plan an archive path: TTL on hot rows + cold storage (S3 / obj_store) for archived tail. Blocks nothing today; revisit before we sell to a customer whose contract requires a retention SLA. | services/audit_log.py + scheduler job + obj_store integration | test: TTL wipes rows past retention window; archive job moves them intact | Not Started | P2 |  |  |  | Sprint 5 (DevOps + compliance) territory.
FIX-004-G | Sprint 2.5 / RBAC Wave 4-B | RBAC-21 | Session-management UI (/me/sessions list + revoke by device) | New services/auth/session_tracking.py extends the FIX-003-C revocation infra with device metadata (ua, ip, last_seen_at). NEW active_sessions collection with jti unique index + user_id/created_at index + exp TTL for auto-purge. record_session/touch_session/list_sessions/revoke_one_session/revoke_all_sessions_for_user (with tenant_id + keep_jti knobs). get_current_user gained touch_session call so /me/sessions shows accurate last-seen. login + register + switch-workspace all record the new jti. 3 new endpoints: GET /me/sessions (marks current session), DELETE /me/sessions/{jti} (ownership-guarded), DELETE /me/sessions (revoke all except current). | services/auth/session_tracking.py (new); services/auth/__init__.py (exports); core.py (get_current_user calls touch_session); server.py (bootstrap: 3 active_sessions indexes); routers/auth.py (login + register + switch-workspace record + 3 new endpoints) | tests/test_session_mgmt.py — 20 tests (4 record contract incl. fail-open + UA cap, 3 list incl. user isolation + tenant filter, 3 revoke_one incl. ownership guard, 2 revoke_all incl. keep_jti + tenant filter, 1 bootstrap indexes, 3 endpoint source guards, 1 get_current_user touch, 3 wire-up on login/register/switch) | Done | P0 | 2026-08-10 | 2026-08-10 | d95ae44 | Sprint 2.5: 19/20. Only RBAC-22 (off-boarding wizard) left. Backend done — frontend /settings/sessions UI logged as FIX-FUP-29.
FIX-FUP-29 | Follow-up (from FIX-004-G) | (logged during Wave 4-B) | Frontend Settings > Sessions UI | Backend ships GET/DELETE /me/sessions + DELETE /me/sessions/{jti}. Frontend needs Settings page listing sessions with UA/IP/last-seen + revoke buttons (individual + 'sign out other devices'). Row for current session should be marked distinct (grey out revoke). | frontend/src pages: Settings/Sessions | manual: log in on 2 devices, revoke the other from device 1, verify device 2 401s | Not Started | P1 |  |  |  | Backend deploy-ready; UI blocks user self-serve session control.
FIX-004-H | Sprint 2.5 / RBAC Wave 4-C | RBAC-22 | Off-boarding wizard (deprovisioning) — RBAC Wave 4 COMPLETE | New services/deprovisioning.py orchestrates 6 idempotent steps into one call: last-owner guard + tenant-scoped session revoke + soft-remove membership + invalidate invite_token + reassign owned tasks + reassign authored contacts + audit_log entry. New endpoint POST /users/{id}/deprovision {reassign_to_user_id?} — owner-only. Self-deprovision refused. Replacement user validated as LIVE member. Returns per-step report for UI confirmation. Session revoke is TENANT-SCOPED — a user's sessions in other tenants they belong to survive. Task reassignment updates denormalized assignee_role. No reassign target = null the fields. | services/deprovisioning.py (new); routers/team.py (new POST /users/{id}/deprovision endpoint + DeprovisionInput model + BaseModel import) | tests/test_deprovisioning.py — 11 tests (2 fresh full-run with + without replacement, 1 idempotent, 2 last-owner guard, 1 tenant scoping, 1 audit entry, 4 endpoint gates) | Done | P0 | 2026-08-10 | 2026-08-10 | 309ef84 | RBAC WAVE 4 COMPLETE — 3/3 sub-batches shipped (F+G+H). Sprint 2.5 now 20/20. Full RBAC roadmap Waves 1-4 COMPLETE — 20 of 30 audit items shipped. Remaining 10 are Sprint 4/5 items: RBAC-18 (department scope), RBAC-19 (user groups), RBAC-23..28 (2FA, ownership transfer, DPDP consent, delegation, time-bounded perms, SSO, API keys), RBAC-30 (customer portal).
FIX-FUP-30 | Follow-up (from FIX-004-H) | (logged during Wave 4-C) | Ownership transfer wizard (owner-to-owner) | Deprovisioning's last-owner guard is correct behavior — it blocks removing the only owner. But it leaves no path out. Need a separate 'transfer ownership' flow: promote another member to owner, then optionally deprovision the previous owner. 2FA confirmation recommended for the promoting owner. | new endpoint POST /tenant/transfer-ownership + service | test: two-owner state achieved, previous owner deprovisions cleanly | Not Started | P1 |  |  |  | RBAC-24 in the audit — Sprint 3 territory.
FIX-FUP-31 | Follow-up (from FIX-004-H) | (logged during Wave 4-C) | Cascade decisions in deprovision | Today deprovision reassigns tasks + contacts but NOT decisions where created_by = target. Small addition — same pattern as tasks. Decision-approver relationships also worth considering: if target was designated approver for pending decisions, they need routing to the replacement. | services/deprovisioning.py | test: fresh deprovision reassigns created_by decisions + approver_id decisions | Not Started | P2 |  |  |  | Incremental improvement on FIX-004-H.
FIX-FUP-32 | Follow-up (from FIX-004-H) | (logged during Wave 4-C) | Frontend off-boarding wizard UI | Backend done. Frontend needs: Team > Member detail page adds 'Remove from workspace' button that opens a wizard: pick replacement member (dropdown of live members), preview count of items to reassign, confirm modal, POST /users/{id}/deprovision, show report summary. | frontend/src pages: Team/MemberDetail, Team/OffboardWizard | manual: off-board a test member, verify counts match backend report | Not Started | P1 |  |  |  | Backend deploy-ready via curl.
FIX-005-A | Sprint 3 / Billing + AI Keys | S3-02 + S3-03 | Plan/entitlement fields + per-tenant AI keys | Two Sprint 3 items shipped together — both pure data-model + resolver changes, no external integration. S3-02: services/plans.py with 5 plans (trial/starter/business/enterprise/grandfathered), each carries seat_limit + quotas (llm_tokens/stt_minutes/storage/brain_docs) + features (whatsapp/sso/api_keys). effective_plan(tenant) merges base + tenant overrides. new_tenant_plan_fields() called in register for trial+14d. enforce_seat_limit raises 402 with upgrade prompt. Bootstrap migration backfill_grandfathered_plans_v1 marks pre-plan tenants — same generous shape as business, retained forever, zero user-visible change. team.py create_user calls enforce_seat_limit BEFORE any writes. S3-03: services/tenant_ai_keys.py resolves keys with precedence tenant->platform->none. 3 owner-only endpoints on /tenant/ai-keys (GET list with masked previews, PUT replace map with audit_log per-provider-change rotation events, DELETE revert to platform pool). Never logs the raw key value — regression-guarded in tests. | services/plans.py (new: plan model + effective_plan + enforce_seat_limit); services/tenant_ai_keys.py (new: resolve_ai_key + normalize + summarize); server.py (GET /tenant/plan + 3 /tenant/ai-keys endpoints + backfill migration); routers/auth.py (register initializes plan fields via new_tenant_plan_fields); routers/team.py (create_user enforces seat limit) | tests/test_plans_and_ai_keys.py — 38 tests (7 effective_plan, 3 trial expiry, 3 has_feature, 1 defaults, 3 enforce_seat_limit, 1 register wire, 1 bootstrap migration, 5 resolve_ai_key precedence, 2 source, 3 normalize, 1 no-secret-leak, 4 endpoint gates, 3 PUT audit + no-leak guard, 1 delete revert, 1 seat-limit BEFORE-insert order) | Done | P0 | 2026-08-10 | 2026-08-10 | afbf9b8 | Sprint 3: 2/5 shipped (+ 3 RBAC items TBD). Billing provider = Razorpay (India-primary). S3-01 deferred until we're ready for external integration. Follow-ups: FIX-FUP-33 (secrets manager for ai_keys), FIX-FUP-34 (provider outage transparent fallback).
FIX-FUP-33 | Follow-up (from FIX-005-A) | (logged during S3-03) | Move tenant.ai_keys to a real secrets manager | tenant.ai_keys stored plain-text in Mongo. Fine for MVP, red flag on a security review. Move to AWS Secrets Manager / HashiCorp Vault / Cloudflare Secrets Store. Wrap services/tenant_ai_keys.resolve_ai_key to fetch from the secrets manager instead of the tenant doc; keep the current in-doc storage as a fallback during migration. | services/tenant_ai_keys.py + new services/secrets_manager.py | test: rotate key in secrets manager, verify resolve returns new value on next call | Not Started | P1 |  |  |  | Sprint 5 (DevOps/security). Blocks enterprise-tier sales.
FIX-FUP-34 | Follow-up (from FIX-005-A) | (logged during S3-03) | AI provider outage transparent fallback (tenant key -> platform) | When a tenant's key returns 429/500, transparently fall back to the platform pool for that request + notify the tenant. Improves reliability without exposing platform quota to abuse (rate-limit the fallback to a low ceiling per tenant/hr). | core.py LLM wrappers + services/tenant_ai_keys.py | test: mock 429 on tenant key, verify fallback + notification + rate-limit on fallback | Not Started | P2 |  |  |  | Depends on RBAC-23 (2FA) being live so admin can rotate the key confidently after an outage.
FIX-005-B | Sprint 3 / Usage Quotas | S3-04 | Usage-quota enforcement (402 on exceed) | New services/quotas.py: check_quota reads current-month usage_events aggregation, compares to plan cap from FIX-005-A. cost param lets caller pre-block a request that would push over. Fail-open on Mongo blip — quota infra failure never blocks AI. 4 resources: llm_tokens_total (sums usage_events.tokens_total), stt_minutes (sums usage_events.units where unit_type=minutes), storage_bytes (sums files.size), brain_docs (counts brain_documents). Aggregation window = current UTC calendar month, resets on 1st. guarded_llm now reads _ctx_tenant contextvar and enforces quota BEFORE taking semaphore slot — raises HTTPException(402) with structured detail {code, resource, message, usage, cap, plan}. NEW skip_quota_check kwarg bypasses check for admin key-probe (would be user-hostile). GET /tenant/usage returns every quota with usage/cap/percent/over — powers frontend dashboard. | services/quotas.py (new); services/ai/llm_limits.py (guarded_llm quota check + skip_quota_check kwarg); server.py (GET /tenant/usage endpoint); routers/admin.py (probe passes skip_quota_check=True) | tests/test_quotas.py — 16 tests (6 check_quota incl. unlimited/under/over/cost-projection/last-month/tenant-isolation, 2 storage + brain_docs sources, 2 status shape, 1 status_all row-per-quota, 4 guarded_llm wiring incl. fail-open, 1 endpoint) | Done | P1 | 2026-08-10 | 2026-08-10 | 29d2238 | Sprint 3: 3/5 shipped (S3-02, S3-03, S3-04). Only S3-01 (Razorpay billing, deferred) + 3 RBAC items (23/24/25) remain. FIX-FUP-35 logged for soft-limit warning emails (75/90/100% thresholds).
FIX-FUP-35 | Follow-up (from FIX-005-B) | (logged during S3-04) | Soft-limit warning emails at 75/90/100% quota thresholds | Backend reports percent + over flag via quota_status. A scheduler task should sweep daily, compare current percent to previously-notified threshold on tenant (persist last_notified_thresholds dict), and send an email at each crossing so tenants hit the cap with warning not surprise. Templates in services/auth_emails.py. | new services/quota_alerts.py + scheduler hook | test: 75% threshold triggers email once, subsequent runs don't re-send unless dropped + re-crossed | Not Started | P2 |  |  |  | Post-Wave-5 polish; not go-live blocker but big UX improvement.
FIX-005-C | Sprint 3 / Compliance | RBAC-25 | DPDP AI-consent tracking (India-mandatory) | New services/ai_consent.py: tenant.ai_consent = {granted_at, granted_by_user_id, granted_by_email, ip, ua, version, revoked_at}. CURRENT_CONSENT_VERSION='1.0' — bump when scope changes, tenants must re-consent. has_active_consent hot-path reader. consent_status frontend shape deliberately OMITS IP/UA (audit-only). needs_reconsent flag for version-drift. require_ai_consent raises HTTPException(451 'Unavailable For Legal Reasons') with structured detail — frontend maps to consent modal. 3 endpoints: GET (any user, banner state), POST (owner grants + captures IP/UA/UA/version), DELETE (owner flips revoked_at + preserves grant history). Both mutations emit audit_log rows. Enforcement wired at guarded_llm BEFORE quota check — single tenants.find_one reused for both consent + plan-quota reads (no double round-trip). Fail-open on Mongo blip, skip_quota_check bypasses (admin probe). | services/ai_consent.py (new: has_active_consent + require_ai_consent + build_grant/revoke + consent_status); services/ai/llm_limits.py (guarded_llm calls require_ai_consent BEFORE quota check, reuses tenant fetch); server.py (3 /tenant/ai-consent endpoints + AiConsentGrantInput model) | tests/test_ai_consent.py — 23 tests (5 has_active_consent state matrix, 3 consent_status incl. no-IP-leak, 3 require_ai_consent, 2 build_grant, 1 build_revoke, 7 endpoint gates + audit emission, 2 guarded_llm gate + fetch reuse) | Done | P1 | 2026-08-10 | 2026-08-10 | 4115624 | Sprint 3: 4/5 shipped. India DPDP-blocker closed. FIX-005-D (RBAC-23 2FA + RBAC-24 ownership transfer) next — the two go together since transfer needs 2FA confirm. S3-01 (Razorpay billing) deferred. FIX-FUP-36 (email nudge on version bump) + FIX-FUP-37 (extend gate to STT/vision) logged.
FIX-FUP-36 | Follow-up (from FIX-005-C) | (logged during RBAC-25) | Consent-doc versioning UX: email nudge on version bump | When CURRENT_CONSENT_VERSION bumps, consent_status flags needs_reconsent=True but nothing emails the owner. Add scheduler task that sweeps tenants where ai_consent.version < CURRENT and sends a re-consent email once per version bump. Suppress duplicate sends via last_reconsent_notified_version on tenant doc. | new services/consent_alerts.py + scheduler hook + services/auth_emails.py template | test: bump version, sweep sends email once per tenant, not on subsequent sweeps | Not Started | P2 |  |  |  | Non-blocker; adds compliance smoothness.
FIX-FUP-37 | Follow-up (from FIX-005-C) | (logged during RBAC-25) | Extend AI consent gate to non-LLM paths (Sarvam STT/TTS + Gemini vision) | guarded_llm is the choke point for LLM calls but Sarvam STT/TTS (server.py transcribe_audio_full, signup /tts /stt) and Gemini vision calls (services/tasks OCR paths) don't route through it. Extend the consent check to those code paths so all AI processing is uniformly gated. | server.py transcribe_audio_full + routers/signup.py tts/stt + Gemini vision call sites | test: STT call without consent returns 451; consented STT returns 200 | Not Started | P1 |  |  |  | Compliance completeness — DPDP considers STT + vision as AI processing too.
FIX-005-D | Sprint 3 / Security + Auth | RBAC-23 + RBAC-24 | TOTP 2FA + tenant ownership transfer | RBAC-23: pyotp-based TOTP flow. services/auth/totp.py: begin_enrollment (secret + provisioning URI for QR), confirm_enrollment (verify pending + generate 10 bcrypt-hashed backup codes returned once), verify_totp (valid_window=1 = 30s drift), consume_backup_code (single-use), disable_totp, regenerate_backup_codes (requires current TOTP not backup). 5 endpoints on /auth/2fa: enroll, confirm, verify-login, disable, regenerate-backup-codes. All emit audit_log events (two_factor_enabled/success/failure/disabled/backup_regenerated/challenge_issued). Login flow: when user.two_factor.enabled_secret set, /login returns {two_factor_required:True, challenge_token} instead of session JWT. 5-min challenge JWT encodes {sub, tenant_id, role, type=2fa_challenge}. Client calls /2fa/verify-login with challenge+code. RBAC-24: POST /auth/tenant/transfer-ownership. Owner-only inline check. Refuses self-transfer + validates target is live member. If caller has 2FA enabled, MUST supply totp_code (prevents session-theft workspace seizure); non-2FA callers still allowed but audit marks two_fa_used=false. Atomic promote+demote in memberships (target->owner, caller->sales safe default). Legacy user.role fields synced too. Audits tenant_ownership_transferred with before/after {owner_id}. | services/auth/totp.py (new: pyotp-based TOTP + bcrypt-hashed backup codes); services/auth/__init__.py (exports); routers/auth.py (5 2FA endpoints + transfer-ownership + login 2FA gate + _mint_challenge/_decode_challenge helpers + 4 input models); requirements.txt (pyotp==2.10.0) | tests/test_totp_and_ownership.py — 26 tests (3 enrollment flow, 4 backup codes incl. regen invalidates, 1 disable wipes, 3 is_enabled state, 2 login challenge shape, 2 challenge token roundtrip + type-guard, 5 endpoint guards, 6 ownership transfer incl. self-refuse + live-member validation + 2FA gate + atomic swap + audit) | Done | P1 | 2026-08-10 | 2026-08-10 | a8da19b | SPRINT 3 COMPLETE (minus S3-01 Razorpay billing, deferred). 5/5 backlog items shipped this sprint: S3-02, S3-03, S3-04 + RBAC-23, RBAC-24, RBAC-25. 3 follow-ups logged: SMS 2FA fallback (FIX-FUP-38), tenant-level enforce-2FA policy (FIX-FUP-39), Razorpay subscription rebind on transfer (FIX-FUP-40).
FIX-FUP-38 | Follow-up (from FIX-005-D) | (logged during Sprint 3) | SMS 2FA fallback + WhatsApp OTP fallback | Many Indian SME employees don't use authenticator apps. Add SMS-OTP as an alternative second factor (integrate Twilio + Razorpay MSG91 or Sarvam) and/or a WhatsApp OTP path (we already have WA infra from FIX-002-A). Same user.two_factor storage, new services/auth/sms_2fa.py. | services/auth/* + relevant routers | test: integration with the new provider / policy | Not Started | P1 |  |  |  | Post-Sprint 3 improvement.
FIX-FUP-39 | Follow-up (from FIX-005-D) | (logged during Sprint 3) | Tenant-level enforce-2FA policy | Add tenant.security_policy.require_2fa_for_owners (bool) + require_2fa_for_admins. When set, login for a matching role refuses to complete without 2FA enrolled first — user is prompted to enroll before session issued. Enterprise-grade compliance ask. | services/auth/* + relevant routers | test: integration with the new provider / policy | Not Started | P2 |  |  |  | Post-Sprint 3 improvement.
FIX-FUP-40 | Follow-up (from FIX-005-D) | (logged during Sprint 3) | Razorpay subscription rebind on ownership transfer | Ownership transfer currently changes DB state only. When S3-01 lands (Razorpay integration), the transfer must also re-point the subscription billing contact to the new owner. Coupled with S3-01. | services/auth/* + relevant routers | test: integration with the new provider / policy | Not Started | P1 |  |  |  | Post-Sprint 3 improvement.
FIX-006-A | Sprint 0 / Security P0 | S0-01 + S0-08 + S0-09 + S0-10 | Auth credential hardening (4 launch-blockers) | S0-01: seed_platform_admin no longer ships hardcoded default creds. Prod (ENV=prod) refuses to boot when SUPERADMIN_EMAIL/PASSWORD missing. Existing admin hash is NEVER overwritten on restart -- refresh path requires an explicit SUPERADMIN_ALLOW_HASH_REFRESH=1 one-off flag. S0-08: login / register / switch-workspace / 2fa-verify-login / admin-login / OTP-verify (6 sites) no longer include the raw JWT in the JSON body when AUTH_RETURN_TOKEN is off. HttpOnly cookie is the source of truth. Env defaults: off in prod, on elsewhere. New login_response() helper centralises the shape. S0-09: Platform-admin tokens now signed + verified with PLATFORM_ADMIN_JWT_SECRET (falls back to JWT_SECRET when unset for dev back-compat). A compromise of the tenant JWT_SECRET can no longer forge platform-admin sessions. type='platform_admin' claim remains as second gate either way. S0-10: verify_otp invalidates invite_token + expiry on successful accept, so the invite link stops resolving on /auth/invite/{token} (no more leaked name / masked phone) and a second /auth/invite/{token}/start can't bomb the invitee's phone with fresh SMS OTPs. Records invite_consumed_at for the paper trail. | config.py (PLATFORM_ADMIN_JWT_SECRET, AUTH_RETURN_TOKEN, SUPERADMIN_ALLOW_HASH_REFRESH env plumbing + env-driven defaults); core.py (create_admin_token + get_platform_admin use admin secret; new login_response() helper); server.py (seed_platform_admin prod refuse + no-silent-refresh + verify_otp invite invalidation + login_response wiring; login_response import); routers/auth.py (register + login + switch-workspace + 2fa-verify-login all route through login_response); routers/admin.py (admin_login routes through login_response) | tests/test_auth_hardening.py -- 23 tests: 4 login_response helper (flag on/off/kwargs/no-shared-state); 5 AUTH_RETURN_TOKEN env semantics (prod default off, dev default on, explicit overrides, truthy/falsy accepted); 4 platform-admin secret split (fallback, distinct, admin verifies with admin secret, tenant secret cannot forge admin); 6 seed_platform_admin (prod refuses, dev fallback, env creds, hash NOT overwritten by default, opt-in refreshes, opt-in noop when password matches); 2 invite invalidation source-inspection guards; 2 no-raw-token endpoint guards (grep-style regression backstop) | Done | P0 | 2026-08-11 | 2026-08-11 | c57b550 | Sprint 0 batch A. 4 launch-blockers shipped together. 337 pre-existing auth/RBAC/session/plans/consent/totp tests still green (zero regressions). Deployment note for ops: set PLATFORM_ADMIN_JWT_SECRET + SUPERADMIN_EMAIL + SUPERADMIN_PASSWORD as distinct high-entropy env values before flipping ENV=prod. AUTH_RETURN_TOKEN defaults off in prod; explicitly set =1 only if a native-mobile client needs the bearer path.
FIX-006-B | Sprint 0 / Security P0 | S0-02 | Strict CORS allow-list + CSRF double-submit cookie | CORS lockdown: removed allow_origin_regex='.*'+allow_credentials=True combo that echoed back any origin and let evil.com make credentialed cross-origin calls carrying the user's auth cookie. CORS_ORIGINS env is now required in prod (unset or containing '*' makes config.py raise at boot). Dev defaults to local frontend origins. CSRF (double-submit cookie): set_auth_cookie + set_admin_cookie now also set a non-HttpOnly dos_csrf cookie carrying a fresh secrets.token_urlsafe(32) token. Frontend JS reads it and echoes as X-CSRF-Token on every mutating request. New services/csrf.py middleware compares header (constant-time) to cookie on each cookie-authed mutating request. Safe verbs, exempt paths (webhooks + login), and bearer-authed requests bypass. Rollout via CSRF_ENFORCE env -- defaults OFF so this batch ships without a breaking frontend change; middleware logs match/mismatch metrics so ops watches adoption before flipping enforcement on. | config.py (CORS_ORIGINS strict allow-list parser + prod boot refusal; CSRF_COOKIE_NAME/HEADER_NAME/EXEMPT_PATHS/ENFORCE env plumbing); core.py (set_csrf_cookie/clear_csrf_cookie helpers; set_auth_cookie + set_admin_cookie now mint CSRF cookie; clear paths also clear CSRF); server.py (replaced regex-CORS block with strict allow-list + CSRFMiddleware registration + startup log); services/csrf.py (new: CSRFMiddleware + _check + metrics counters) | tests/test_cors_csrf.py -- 31 tests: 7 CORS parsing (prod refuses empty/wildcard/wildcard-mixed, accepts explicit list, strips whitespace/empty, dev fallback, dev override); 6 CSRF cookie minting (auth/admin sets, fresh token per call, clear also clears CSRF, explicit token); 8 check contract (safe verbs, exempt paths, bearer bypass, missing cookie/header, value mismatch, admin cookie equivalence); 3 metrics (counter shape, reset, snapshot returns copy); 4 enforce toggle parsing; 5 middleware dispatch (shadow passes, enforce 403s, matching passes, bearer bypasses, exempt-path bypasses). test_auth_hardening.py refactored to use monkeypatch.setattr on module attrs instead of importlib.reload(config) -- kills the cross-test config pollution that surfaced when TestClient closes shared asyncio loop. | Done | P0 | 2026-08-12 | 2026-08-12 | ababc06 | Sprint 0 batch B. 405/405 pass across adjacent auth/RBAC/session/plans/consent/totp/tenancy/dockerfile surfaces. test_workflows_dynamic excluded from regression -- pre-existing asyncio.run() vs get_event_loop() interaction is unrelated to this batch (FIX-FUP-41 logged). Deployment: set CORS_ORIGINS to comma-separated exact origins before ENV=prod. Frontend follow-up (FIX-FUP-42): read dos_csrf cookie in JS, send X-CSRF-Token header on mutating requests, then flip CSRF_ENFORCE=1 in prod once staging shows ~100% match rate.
FIX-FUP-41 | Follow-up (from FIX-006-B) | (logged during Sprint 0) | Kill test-suite asyncio-loop flakiness | test_workflows_dynamic.py uses asyncio.run() which closes the shared event loop, breaking test_deprovisioning/quotas/email_verification that use asyncio.get_event_loop(). Under xdist loadscope both can land on the same worker in an order that trips this. Fix: standardize on asyncio.new_event_loop() everywhere (or asyncio.run everywhere). | tests/* (FUP-41) or frontend/src/api (FUP-42) | test: cross-worker asyncio stability / frontend integration | Not Started | P2 |  |  |  | Post-FIX-006-B improvement.
FIX-FUP-42 | Follow-up (from FIX-006-B) | (logged during Sprint 0) | Frontend: read dos_csrf, send X-CSRF-Token, flip CSRF_ENFORCE | Read the dos_csrf cookie via document.cookie (non-HttpOnly). Wrap fetch/axios to send X-CSRF-Token header on every POST/PUT/PATCH/DELETE. Watch staging csrf_check_failed logs. Once ~100% match rate, set CSRF_ENFORCE=1 in prod. Middleware will start returning 403 on mismatch. | tests/* (FUP-41) or frontend/src/api (FUP-42) | test: cross-worker asyncio stability / frontend integration | Not Started | P0 |  |  |  | Post-FIX-006-B improvement.
FIX-006-C | Sprint 0 / Security P0 | S0-03 + S0-04 + S0-05 | Endpoint P0s (files / OTP / WhatsApp) | S0-03: GET /api/files/{fname} legacy local-disk fallback is now off-by-default. The old branch served any file on disk to any authenticated caller -- no tenant-ownership check on the legacy path. Gated behind SERVE_LEGACY_LOCAL_DISK env (default False); denied hits logged for observability. S0-04: /auth/otp/request no longer surfaces dev_otp in the JSON body unless DEV_OTP_IN_RESPONSE=1 is explicitly set. server.py now refuses to boot in prod when neither APM_SMS_API_KEY nor TWILIO_* is configured -- silent dev-mode fall-through would hand working login codes to any /auth/otp/request caller. S0-05: WhatsApp webhook rejects (403) on X-Hub-Signature-256 mismatch instead of logging + processing. Also refuses missing WA_APP_SECRET in prod (dev/staging accept with WARN so local tunnels work). hmac.compare_digest preserved for constant-time compare. | config.py (SERVE_LEGACY_LOCAL_DISK + DEV_OTP_IN_RESPONSE env parsing); server.py (get_file legacy-branch gate + logging; _issue_otp dev_otp gate; TWILIO/APM boot-check raise; whatsapp_webhook 403 on mismatch + prod refuses missing WA_APP_SECRET) | tests/test_endpoint_hardening.py -- 14 tests: 4 legacy-disk fallback (source has gate, default off, opt-in works, tenant scope preserved on non-legacy branches); 5 dev-OTP (source gates on flag, default off, opt-in works, prod-boot check exists, end-to-end prod-without-SMS refuses to boot); 5 WhatsApp signature (rejects on mismatch not processes, constant-time compare stays, missing secret rejected in prod, not-configured branch unchanged, HMAC recomputes correctly) | Done | P0 | 2026-08-12 | 2026-08-12 | 685141d | Sprint 0 batch C. 419/419 pass across adjacent auth/RBAC/session/plans/consent/totp/tenancy surfaces. test_workflows_dynamic still excluded per FIX-FUP-41. Deployment: set APM_SMS_API_KEY (India) or TWILIO_* (global) before ENV=prod. Set WA_APP_SECRET whenever WhatsApp ingestion is enabled in prod. Leave SERVE_LEGACY_LOCAL_DISK unset in prod.
FIX-006-D | Sprint 0 / Security P0 | S0-06 + S0-07 | Unauth-AI rate-limit/captcha + tenant login lockout | S0-06: new shared services.rate_limit.guard_unauth_ai_endpoint() extracts the 3-check pattern (hourly quota + burst quota + CAPTCHA) that signup.py already used, and applies it to the two /api/onboarding/* endpoints that were still unguarded. Both call claude_chat unauthenticated, so drive-by traffic burns real LLM credit. onboarding/os-blueprint is the biggest per-call spend on the pre-auth surface. Per-(service, kind) buckets so signup-drained quotas don't affect onboarding and vice-versa. S0-07: tenant /api/auth/login now has a 5-attempt / 15-min lockout -- parity with admin login. db.user_login_attempts keyed by (IP, email), X-Forwarded-For preferred for real client IP. Lock check runs BEFORE db.users.find_one so timing doesn't leak whether an email exists. Cool-down clears on natural expiry AND on successful login so a slow attacker can't share the cooldown with the legitimate user. Emits login_locked_out audit event. | services/rate_limit.py (new public guard_unauth_ai_endpoint() with per-service, per-kind buckets + configurable quotas + require_captcha opt-out); routers/onboarding.py (import shared helper; apply guard to onboarding_suggest + onboarding_os_blueprint; both handlers gain request: Request param); routers/auth.py (LOGIN_MAX_ATTEMPTS=5, LOGIN_LOCKOUT_MIN=15 constants; _login_ident/_login_locked_out/_login_record_failure/_login_clear_attempts helpers; login endpoint wires lock check + record-on-fail + clear-on-success + audit login_locked_out event) | tests/test_ratelimit_and_lockout.py -- 23 tests: 7 unauth-AI guard (first hit ok, hourly 429, burst 429, captcha required, service isolation, kind isolation, captcha opt-out); 3 endpoint wire-up guards (both onboarding endpoints call shared helper, module imports it); 7 lockout unit tests (ident shape, XFF preference, below/at threshold, window expiry clears, increment upserts, clear wipes, bad iso doesn't perma-lock); 4 login source-inspection guards (lock check before DB find, records on failure, clears on success, 429 not 401, parity numbers with admin login) | Done | P0/P1 | 2026-08-12 | 2026-08-12 | 93a9f1c | Sprint 0 batch D. CLOSES SPRINT 0. 442/442 pass across all adjacent auth/RBAC/session/plans/consent/totp/tenancy/dockerfile test surfaces. test_workflows_dynamic still excluded per FIX-FUP-41. Deployment: consider adding a Mongo TTL index on user_login_attempts.last (mirrors platform_login_attempts) so expired rows auto-clean -- logged as FIX-FUP-43. In prod, set CAPTCHA_REQUIRED=1 + TURNSTILE_SECRET to hard-enforce captcha on all pre-auth AI endpoints (currently permissive in dev/staging where no secret is set).
FIX-FUP-43 | Follow-up (from FIX-006-D) | (logged during Sprint 0) | TTL index on user_login_attempts.last | Mirror the scheduler_locks / platform_login_attempts TTL pattern: create index on db.user_login_attempts.last with expireAfterSeconds = LOGIN_LOCKOUT_MIN * 60 * 2 (double the window so a fresh row can still exist for its full useful life). Kills row buildup for attackers who spray many (IP, email) pairs. | server.py bootstrap indexes block; services/auth or routers/auth (where LOGIN_LOCKOUT_MIN is defined) | test: index exists on collection after bootstrap; row inserted at T=0 gone after T=LOGIN_LOCKOUT_MIN*2 | Not Started | P2 |  |  |  | Post-Sprint-0 hygiene.

## Kanban Board
Roadmap Kanban Board — swimlanes = Sprints, cards color-coded by Priority
Snapshot view for planning. To track day-to-day status changes, edit the Task Backlog tab.
Sprint 0 Critical Security & Auth (GATE) | Sprint 1 Scale & Operational Blockers (GATE) | Sprint 2 Tenancy Hygiene & Data Integrity (parallel) | Sprint 3 Billing & Multi-Tenant AI Keys (GATE) | Sprint 4 AI Brain / Agentic Enhancement (parallel) | Sprint 5 DevOps, Deployment & Data Migration (GATE)
[S0-01] Remove hardcoded superadmin default credentials (Security/Auth) | [DONE][S1-01] Externalize the follow-up scheduler (Scale/Ops) | [DONE][S2-01] Add _ensure_owned() helper (Tenancy/Data) | [S3-01] Integrate real billing (Stripe or Razorpay) (Billing/AI-Keys) | [S4-01] Fix text-index stemming + index db.memory (AI/Brain) | [S5-01] Stand up a staging environment (DevOps/Migration)
[S0-02] Fix CORS wildcard + credentials (Security/Auth) | [DONE][S1-02] Index phone, drop Python-side filter (Scale/Ops) | [DONE][S2-02] Complete TENANT_COLLECTIONS wipe (Tenancy/Data) | [DONE][S3-02] Add plan / entitlement fields to tenant doc (Billing/AI-Keys) | [S4-02] Fix task-done Brain write-coverage gap + link provenance (AI/Brain) | [S5-02] Run a load test at target scale (DevOps/Migration)
[S0-03] Auth-gate file downloads (Security/Auth) | [DONE][S1-03] Move all uploads to obj_store (Scale/Ops) | [DONE][S2-03] Tenant-scope OTP + WhatsApp phone routing (Tenancy/Data) | [DONE][S3-03] Per-tenant AI key resolver (Billing/AI-Keys) | [S4-03] Rename brain_contexts -> brain_query_cache (AI/Brain) | [S5-03] Add observability (Sentry + structured logs + APM) (DevOps/Migration)
[S0-04] Kill dev-mode OTP leak (Security/Auth) | [DONE][S1-04] Commit real deployment config (Scale/Ops) | [DONE][S2-04] Fix cross-tenant WhatsApp log leak (Tenancy/Data) | [DONE][S3-04] Enforce usage quotas (402 on exceed) (Billing/AI-Keys) | [S4-04] Unify /ask and /brain/agent retrieval reach (AI/Brain) | [S5-04] Write + TEST a backup/restore runbook (DevOps/Migration)
[S0-05] Fix WhatsApp signature bypass (Security/Auth) | [DONE][S1-05] Timeout + concurrency-limit LLM calls (Scale/Ops) | [DONE][S2-05] Fix unfiltered enrich_decisions fetch (Tenancy/Data) |  | [S4-05] Extract + chunk + embed documents at ingest (AI/Brain) | [S5-05] Data migration plan for schema changes above (DevOps/Migration)
[S0-06] Rate-limit + captcha unauth AI endpoints (Security/Auth) | [DONE][S1-06] Fix hardcoded purchase_payment key (Scale/Ops) | [DONE][S2-06] Add session invalidation on logout/password-change (Tenancy/Data) |  | [S4-06] Adopt vector search + hybrid retrieval (AI/Brain) | [S5-06] Stand up CI/CD (DevOps/Migration)
[S0-07] Add login rate limiting (Security/Auth) |  | [DONE][S2-07] Add email verification + password reset (Tenancy/Data) |  | [S4-07] Formalize a tool registry (AI/Brain) | [S5-07] Define a rollback procedure (DevOps/Migration)
[S0-08] Stop returning raw JWT in response body (Security/Auth) |  | [DONE][S2-08] Fix dead contacts.kind index (Tenancy/Data) |  | [S4-08] Add bounded planner-executor loop + native function-calling (AI/Brain) | [S5-08] Move secrets to a real secrets manager (DevOps/Migration)
[S0-09] Split JWT secret: tenant vs platform admin (Security/Auth) |  | [DONE][S2-09] Fix denormalized-name staleness (Tenancy/Data) |  | [S4-09] Add per-conversation agent memory (AI/Brain) | [S5-09] Staged rollout plan (5 -> 20 -> 50 -> 100) (DevOps/Migration)
[S0-10] Invalidate invite tokens after use (Security/Auth) |  | [DONE][S2-10] Handle concurrent-registration race (Tenancy/Data) |  | [S4-10] Expand Brain write coverage to finance/workflow/meetings (AI/Brain) | [S5-10] Final go/no-go review (DevOps/Migration)
|  | [DONE][S2-11] Flag AI-operating-model generation failures (Tenancy/Data) |  | [S4-11] Make tag vocabulary tenant/industry-configurable (AI/Brain)
[DONE][S2-12] Fix 'active workflows' hardcoded terminal stages (Tenancy/Data)
Card color = Priority:
P0 — ship blocker
P1 — before real customer
P2 — hardening

## Testing Plan
Testing Plan — from automated tests through Alpha, Beta, and GA
Every test type required before going live, sequenced by phase, plus the Alpha -> Closed Beta -> Staged Beta -> GA rollout milestones.
Rollout Milestones
Stage | Tenant Count | Duration | Entry Criteria | Exit Criteria / Pass Bar
Internal Alpha | 0 (internal only) | 1-2 weeks | Sprint 0 + 1 P0 Done, automated suite green | Zero open P0/P1 after full manual walkthrough of every module + baseline load test
Closed Beta | 3-5 design partners | 2-4 weeks | Alpha exit met + Sprint 2 + 3 Done + backup/restore drill passed | No P0 incidents, daily active usage from most partners, isolation matrix 100% pass, 1+ non-textile tenant validated
Staged Open Beta | 10 -> 30 -> 50 tenants | 3-6 weeks (tiered) | Closed Beta exit met + Sprint 5 Done | SLO held at every tier, zero scheduler/cross-tenant incidents, support load manageable
General Availability | 100+ / self-serve | Ongoing | Staged Beta exit met + Go-Live Checklist 100% + go/no-go held | Sustained SLA at target traffic, zero open P0s for a full monitoring cycle
Detailed Test Plan — by phase
Phase | Test Type | What It Verifies | Scope / Method | Entry Criteria | Exit Criteria / Pass Bar | Environment | Linked Sprint | Status | Owner
A | Unit Testing | Individual functions/handlers behave correctly in isolation (auth, RBAC, compute handlers, operating-model resolver, etc.) | pytest, run on every PR (backend/pytest.ini, backend/tests/) | Code written | 100% of new/changed code has a passing unit test; suite green in CI | Dev / CI | Sprint 0-5 (continuous) | In Progress — 279/279 offline suite green across 15 test files
A | Integration Testing | Full request/response flow across routers + DB for each domain (auth, tasks, decisions, workflows, brain, ledger) | pytest against a real test Mongo instance, one suite per router domain | Unit suite green | Every endpoint touched by Sprints 0-3 has at least one integration test; suite green | Dev / CI | Sprint 0-3 | Not Started
A | Regression Testing | Nothing that used to work broke as a result of this round of fixes | Full automated suite re-run after each sprint merges to the branch | Each sprint's tasks marked Done | Zero net-new failures vs. the pre-sprint baseline run | CI | Every sprint | In Progress — 279/279 offline suite green across 15 test files
B | Multi-Tenant Isolation Test Matrix | No cross-tenant read/write is possible on ANY collection, endpoint, or background job | Scripted test: create 2+ tenants with overlapping data (incl. same phone number per S2-03), attempt cross-tenant read/write/delete on every collection + every _ensure_owned call site from S2-01 | Sprint 2 tasks Done | 100% pass — zero cross-tenant access possible, incl. OTP/WhatsApp phone routing and tenant deletion completeness | Staging | Sprint 2 | Not Started
B | Dynamic-Workflow Multi-Tenant Test | A NON-textile tenant (e.g. restaurant/clinic) gets a correctly working approval + payment-tracking loop, not just the textile demo | Onboard a synthetic non-textile tenant, run its AI-designed pipeline end to end incl. owner approval + dashboard KPIs | S1-06 Done | Approval gate, pending-purchases dashboard, and payment-overdue alerts all fire correctly for the non-textile pipeline | Staging | Sprint 1 | Not Started
C | Security / Penetration Testing | Every Sprint 0 vulnerability is actually closed, not just patched in one spot | Manual + tool-assisted (OWASP ZAP or similar): CORS/CSRF exploit attempt, unauth file access, JWT tampering, WhatsApp signature bypass, brute-force login, superadmin default creds | Sprint 0 tasks Done | Zero exploitable findings on the Sprint 0 issue list; independent reviewer (or external pentest) sign-off | Staging | Sprint 0 | Not Started
C | RBAC / Permission Audit | Every role sees exactly what it should and nothing more (finance data, admin routes, brain visibility rules) | Scripted test matrix: role x endpoint x expected access, incl. brain_rbac intents and document visibility rules | Sprint 0-2 Done | 100% pass on the role x endpoint matrix | Staging | Sprint 0-2 | Not Started
D | Load / Performance Testing — Baseline | Normal-traffic response times meet SLO before adding concurrency | k6 or Locust against staging, single-tenant, ramping requests per endpoint | Sprint 1 Done, staging live (S5-01) | P95 latency within target (e.g. <500ms for reads, <3s for AI-backed endpoints) at expected steady load | Staging | Sprint 5 | Not Started
D | Load Testing — Multi-Tenant Concurrency | The system holds up with ~100 tenants' worth of simultaneous traffic, not just one tenant at a time | k6/Locust simulating 100 tenants concurrently hitting dashboards, /ask, and voice-capture together (S5-02) | Baseline load test passed | No error-rate spike, no shared-LLM-key 429 cascade (validates S1-05), DB pool holds under SUMMED load | Staging | Sprint 5 | Not Started
D | Spike / Burst Testing | A sudden burst (e.g. many tenants' morning login + voice-capture rush) doesn't cascade into an outage | Short high-intensity burst against the follow-up-scheduler window and login/OTP path | Multi-tenant load test passed | System recovers within target time with no dropped requests beyond configured rate limits | Staging | Sprint 5 | Not Started
D | Soak / Endurance Testing | No slow memory leak, connection-pool exhaustion, or gradual degradation over sustained runtime | Run realistic traffic continuously for 24-48h on staging | Spike test passed | No degradation in latency/error-rate/memory over the full run | Staging | Sprint 5 | Not Started
D | Database Query Performance at Volume | Indexes actually get used and stay fast as data grows, not just at demo-tenant scale | Seed staging with ~50k tasks / 10k contacts / 20k invoices across many tenants; profile the hot dashboard + /ask queries | Schema fixes (S2-08, SCALE items) Done | No full-collection scans on hot paths; dashboard/brief load within SLO at seeded volume | Staging | Sprint 1-2 | Not Started
E | Multi-Replica / Concurrency Testing | Running 3+ app replicas doesn't duplicate scheduled work or race on startup | Deploy 3 replicas on staging; verify the follow-up scheduler fires exactly once per interval, not 3x (validates S1-01); verify index/migration bootstrap doesn't race | Sprint 1 Done, real deploy config (S1-04) exists | Zero duplicate escalation emails/alerts observed across a full scheduler interval with 3 replicas running | Staging | Sprint 1 | Not Started
E | Failure-Injection / Chaos Testing | The system degrades gracefully, not catastrophically, when a dependency fails | Kill a replica mid-request, simulate the LLM provider timing out/erroring, simulate a DB connection drop | Multi-replica test passed | In-flight requests fail cleanly with a user-visible error, no data corruption, service recovers automatically | Staging | Sprint 5 | Not Started
F | Data Migration Dry-Run | Every schema change introduced by Sprints 0-3 applies cleanly to real-shaped data with no loss | Run the migration plan (S5-05) against a full staging copy of realistic seeded data; diff before/after | All schema-changing tasks (S1-02, S2-01/02/08, S3-02) Done | Migration completes with zero data loss and a documented rollback path; re-run is idempotent | Staging | Sprint 5 | Not Started
F | Backup & Disaster-Recovery Drill | A real restore works within the defined RPO/RTO, not just a backup file existing | Actually delete/corrupt a staging DB copy and restore from the S5-04 backup process, timed | S5-04 backup runbook written | Restore completes within the target RTO with data loss within the target RPO | Staging | Sprint 5 | Not Started
F | Tenant-Deletion Completeness Test | Deleting a tenant removes 100% of their data (DB + files), nothing orphaned | Create a tenant with data in every collection incl. brain_context/brain_documents/files, delete it, verify zero remaining rows/files | S2-02 Done | Zero rows or files remain referencing the deleted tenant_id anywhere | Staging | Sprint 2 | Not Started
G | Internal Alpha Testing | The team itself can run real day-to-day operations on the product without a P0/P1 bug surfacing | Internal team + demo data, every module used daily for the alpha window | Sprint 0 + Sprint 1 P0 all Done; automated suite green | Zero open P0/P1 bugs after the alpha window; baseline load test passed | Staging (alpha) | After Sprint 1 | Not Started
H | Closed Beta — Design Partners | A small set of REAL external tenants (ideally incl. a non-textile business) run real operations and the product holds up without hand-holding beyond normal support | 3-5 hand-picked design-partner tenants, high-touch support, 2-4 weeks, daily monitoring | Alpha exit criteria met; Sprint 2 + Sprint 3 Done; backup/restore drill passed | No P0 incidents; majority of design partners show daily active usage; tenant isolation matrix 100% pass with real data; at least 1 non-textile tenant validates the workflow fix | Production (limited) | After Sprint 3 | Not Started
I | Staged Open Beta | Controlled expansion in tiers with a monitoring checkpoint before each step, so a problem is caught at 10 tenants, not 100 | Expand 10 -> 30 -> 50 tenants; hold at each tier for a monitoring window before advancing (ties to S5-09) | Closed Beta exit criteria met; Sprint 5 Done (load test, observability, migration dry-run) | Error rate + latency within SLO at every tier; no scheduler double-fire or cross-tenant incident observed; support volume stays manageable | Production | Sprint 5 | Not Started
J | General Availability / Self-Serve Launch | The product is ready for unassisted signup at the full target scale | Open self-serve signup; remove any beta gating | Staged Beta exit criteria met; Go-Live Checklist 100% TRUE; final go/no-go held (S5-10) | Sustained SLA at ~100-tenant traffic with no open P0s for a full monitoring cycle | Production | After Sprint 5 | Not Started
Phase key:
A | Automated (Unit/Integration/Regression)
B | Multi-Tenant Isolation
C | Security / Pentest
D | Load & Performance
E | Resilience / Concurrency / Chaos
F | Migration & Backup/DR
G | Internal Alpha
H | Closed Beta
I | Staged Open Beta
J | General Availability

## RBAC & People Access
RBAC & People Access — Product-Level Audit
Deep audit of who-can-do-what across DecisionOS. Written product-developer style: map the current model, catalog every gap that stops the product from being sold to a multi-employee SME, ship each gap as a tracked task with tests. Companion to Sprint 2 (which fixed tenancy plumbing); this tab covers the human-facing layer on top.
1. Current-state model — what exists TODAY (verified in code)
Core primitives (backend/core.py)
# | Primitive | What it does | Evidence (file:line) | Verdict |  |  |  | Notes
1 | require_role(*roles) | FastAPI dependency; 403 unless user.role in roles. | core.py:347 | OK |  |  |  | Simple, works. Only 8 endpoints use it.
2 | require_perm(perm) | FastAPI dependency; 403 unless perm in user_perms(user). | core.py:384 | OK |  |  |  | Only ~35 route uses; most endpoints use bare get_current_user.
3 | user_perms(user) | Owner -> ALL permission keys. Else user.permissions[] (if set) filtered to known keys. Else ROLE_DEFAULT_PERMS.get(role, _BASE_PERMS). | core.py:364-370 | WEAK |  |  |  | Owner is a magic god-role. No way to say 'owner minus finance'.
4 | _BASE_PERMS | {inbox, data_input, people, workflows, tasks, brain, ask} — 7 keys. | core.py:357 | OK |  |  |  | Sane starter set.
5 | ROLE_DEFAULT_PERMS | Maps only 'sales' -> _BASE_PERMS and 'finance' -> _BASE_PERMS ¦ {finance, ledger}. No entry for 'production', 'operations', or any custom role — they all silently fall through to _BASE_PERMS. | core.py:358-361 | GAP |  |  |  | Custom roles created via /tenant/roles have NO way to add perms without editing each user.
6 | PERMISSION_KEYS | 14 keys: inbox, voice_capture, data_input, people, finance, ledger, workflows, tasks, brain, ask, approvals, decisions_approve, leave_approve, team_manage. | config.py:38-42 | OK |  |  |  | Reasonable granularity. But 'approvals', 'leave_approve', 'inbox', 'tasks', 'ledger' are unused as decorators.
7 | ROLES vs DEFAULT_ROLES | config.ROLES = [owner, sales, production, finance]. DEFAULT_ROLES = [sales, operations, finance]. Mismatch: 'production' vs 'operations'. | config.py:36, 44-48 | BUG |  |  |  | Silent inconsistency — tenants get 'operations' but permission logic expects 'production'.
Identity + membership model
# | Aspect | What exists | Evidence | Verdict |  |  |  | SaaS impact
1 | User-to-tenant link | Single `tenant_id` field on user doc. No memberships collection. | team.py:143 | GAP |  |  |  | One user = one workspace. Accountants/consultants who serve multiple SMEs cannot exist as a single user account — must register N times with N emails.
2 | Email uniqueness | Globally unique — find_one({'email': email}) with no tenant_id in the check. | team.py:122, auth.py:136, signup.py:106 | GAP |  |  |  | Blocks multi-tenant membership. Same anti-pattern we JUST fixed for phones (FIX-003-A). Email needs the same treatment.
3 | Passwordless (OTP-only) users | Empty password -> random hash + passwordless=True; phone >= 10 digits required; OTP-only login enforced downstream. | team.py:126-136, auth.py:398/487/525 | OK |  |  |  | Good for field employees without email discipline.
4 | Invite tokens | invite_token + invite_expires_at (+7d) written on user creation if phone given; regeneration endpoint. | team.py:154-157, 169 | OK |  |  |  | But: no 'accepted' vs 'pending' state tracking, and invited users are already listed in /users same as active ones (no visible pending state to admin).
5 | Suspension flags | user.suspended + tenant_suspended; both checked in get_current_user -> 403. | core.py:341-342 | OK |  |  |  | But there's no session revocation on suspend — the token stays cryptographically valid until it expires (though get_current_user WILL 403 next request). Combine with FIX-003-C's jti revocation.
6 | Platform admin | Completely separate auth system (platform_admins collection, separate JWT type, cookie name). | core.py:240-277, admin.py | OK |  |  |  | Good separation. But: platform admins can do cross-tenant reclassify/delete — no super-audit trail visible.
Tenant-level custom roles
# | Aspect | What exists | Evidence | Verdict |  |  |  | SaaS impact
1 | Custom role CRUD | POST/rename/DELETE roles per tenant via /api/tenant/roles. Structure {key, label}. 'owner' key reserved. delete_role blocks if users still assigned. | server.py:1759 (add), 1775 (rename), 1794 (delete) | OK |  |  |  | Good baseline.
2 | Per-role permission map | NONE. Custom roles get whatever ROLE_DEFAULT_PERMS.get(key) returns (miss -> _BASE_PERMS). | core.py:369 | GAP |  |  |  | Creating a 'warehouse_manager' role and expecting it to see finance requires editing EACH user's permissions[] override. No way to say 'this ROLE always gets finance perm'.
3 | Per-user permission override | user.permissions[] takes precedence over role defaults. clean_perms filters to known keys. | core.py:365-370, 373-381 | OK |  |  |  | Fine as an escape hatch, but shouldn't be the ONLY way to grant a permission.
2. Gap findings — ranked by severity
Endpoint enforcement + data-model gaps that would embarrass us with a multi-employee SME customer.
A. Endpoint enforcement gaps (from 211-endpoint sweep)
# | Severity | Endpoint / area | Current gate | Why it's bad |  |  | Evidence | Fix task
A1 | P0 | GET /onboarding/draft/{draft_id} + PATCH | Public — no auth | Any client can guess a draft ID and read/write another founder's onboarding data (industry, description, roles, phone). draft_id is a UUID but there's zero enumeration protection. |  |  | onboarding.py:146, 156 | RBAC-01
A2 | P0 | POST /register | Public, no CAPTCHA | Anyone can spin up unlimited tenants. AI credit burn + storage cost + noisy dashboard. |  |  | auth.py:96 | RBAC-02
A3 | P0 | POST /website-intel + /signup/tts + /signup/stt | Public | Server-side URL fetch (SSRF potential) + unauthenticated AI calls burning credits. Any attacker can drain quota. |  |  | signup.py:125, tts, stt | RBAC-03
A4 | P1 | POST /workflows (create) | Auth-only | Any employee can create workflows. But DELETE /workflows/{id} requires owner. Asymmetric. |  |  | server.py:2484 vs 2596 | RBAC-04
A5 | P1 | POST /captures/{cid}/approve¦reject¦reassign¦patch | Auth-only | Approving a captured draft turns it into real workflow/task data. Should be role/perm-gated. |  |  | server.py:5167-5211 | RBAC-05
A6 | P1 | POST /follow-up/run | Auth-only | Any employee can trigger a full tenant follow-up sweep (LLM cost, notification spam). |  |  | server.py:3205 | RBAC-06
A7 | P1 | 17/17 endpoints in routers/tasks.py | Auth-only | Reassign, DELETE execution-plan, prioritize (LLM), bulk delete — all open to every logged-in user. Inline `role!=owner` check only on /tasks/{id} DELETE. |  |  | tasks.py all | RBAC-07
A8 | P1 | POST /voice-notes text/audio + /meetings audio | Auth-only | Every employee can burn STT/LLM credits without any quota. Voice notes attach to any task by id. |  |  | server.py:2141, 2161 | RBAC-08
A9 | P1 | POST /leaves/{id}/approve¦reject¦request-info | Auth-only + inline helper | Decorator gives no auth signal at endpoint level — reviewers reading the route can't tell what's gated. Move to require_perm('leave_approve'). |  |  | team.py:322, 328, 335 | RBAC-09
A10 | P2 | POST /brain/export | perm(ask) | 'ask' is the QUERY permission. Export = bulk data extraction, higher privilege. |  |  | brain.py:64 | RBAC-10
A11 | P2 | POST /memory (create) | Auth-only | Any employee can insert into shared tenant memory. No 'memory_write' permission. |  |  | server.py:3264 | RBAC-11
B. Data-model gaps (multi-workspace membership + role granularity)
# | Severity | Finding | Current behavior | Product impact |  |  | Evidence | Fix task
B1 | P0 | One email = one workspace | users.email is globally unique. | An accountant serving 5 SMEs must register 5 emails. Founders switching between their bakery + consulting workspace must log out/in. Standard SaaS SME buyers reject this. |  |  | team.py:122, auth.py:136 | RBAC-12
B2 | P0 | No memberships table | user.tenant_id is a single foreign key. | Blocks (B1) permanently. Cannot model 'is member of Tenant A as employee + Tenant B as owner'. Every fix downstream (invite, delete, list users) must be rewritten later — cheaper to do now. |  |  | team.py:143 + all users.find_one users | RBAC-13
B3 | P1 | Custom roles cannot have permissions | ROLE_DEFAULT_PERMS is hardcoded to sales + finance only. | Founder creates 'warehouse_manager' role, must then edit each user's permissions[] individually. Role loses its meaning as a policy unit. |  |  | core.py:358-361 | RBAC-14
B4 | P1 | Owner is a magic god-role | user_perms shortcuts owner to ALL permission keys. | Cannot have 'Co-founder with everything EXCEPT finance visibility' — a common early-stage founder ask. No 'break-glass' pattern (grant admin temporarily, log it). |  |  | core.py:365 | RBAC-15
B5 | P1 | config.ROLES / DEFAULT_ROLES mismatch | 'production' in ROLES, 'operations' in DEFAULT_ROLES. | Any code that switches on ROLES silently misses tenants who got 'operations' as a default role. |  |  | config.py:36 vs 44-48 | RBAC-16
B6 | P1 | No pending vs accepted invite state | invite_token exists but /users returns invited users same as active. No 'pending_invite' flag on the user. | Admin cannot see 'you invited 3 people, 1 has accepted, 2 are pending'. Also blocks off-boarding: cannot uninvite before accept. |  |  | team.py:158-165, GET /users | RBAC-17
B7 | P2 | No department / branch scope | A Finance Manager in Store A sees Store B's data. | Multi-branch SMEs are common in India (kirana chains, salon franchises). Blocks selling to any tenant with >1 physical location. |  |  | N/A (missing entirely) | RBAC-18
B8 | P2 | No user groups | Permissions attach only to (role) + (user override). | Cannot say 'all Regional Managers get inventory perm' — must edit 12 individual users. |  |  | N/A (missing entirely) | RBAC-19
C. Missing SaaS RBAC surface area (product-developer view)
# | Severity | Missing capability | Why an SME buyer expects it |  |  |  | Precedent | Fix task
C1 | P0 | Immutable audit log (who-did-what) | SOC2/DPDP/GDPR compliance + 'who deleted this decision?' operational forensics. Today log_activity is human-readable free text, not queryable, and can be deleted with a normal update. |  |  |  | Standard in QuickBooks / Zoho One / Odoo. | RBAC-20
C2 | P0 | Session management UI (/me/sessions) | User needs to see 'I'm logged in on 3 devices, revoke the phone I lost'. Backend has FIX-003-C jti revocation infra — no UI endpoint exposes it. |  |  |  | Every consumer + B2B tool for 10 years. | RBAC-21
C3 | P0 | Off-boarding workflow (deprovisioning) | Departing employee must: revoke all sessions, reassign owned tasks, transfer decisions in-flight, mark authored contacts as reassigned, revoke invite tokens. Today only role-change/suspend/delete exist — the cleanup is manual. |  |  |  | Enterprise-must-have; SMEs benefit too. | RBAC-22
C4 | P1 | MFA (TOTP / SMS second factor) | Insurance, banking-adjacent, finance-team users demand it. Also 'sign-in from a new device' second-factor. |  |  |  | Universal. | RBAC-23
C5 | P1 | Ownership transfer flow | Founder leaves the company. Today, delete owner blocks 'last owner'; there's no clean promote-then-demote sequence with tenant billing rebind. |  |  |  | Common at series-A/B. | RBAC-24
C6 | P1 | Consent tracking for AI features | DPDP-2023 requires explicit consent for AI processing of PII. Today the app just sends employee names/tasks to Anthropic without a per-tenant consent gate. |  |  |  | Legal requirement for India. | RBAC-25
C7 | P2 | Approval delegation ('acting-as') | On-leave approvers block the workflow. Should be able to say 'while I'm out, X approves for me'. FIX-001-D and team.py have plumbing but no delegation surface. |  |  |  | Standard in HRIS / procurement. | RBAC-26
C8 | P2 | Time-bounded elevated permissions | Contractor gets finance perm for month-end close, auto-revokes at end of month. Today it's manual add/remove. |  |  |  | Nice-to-have. | RBAC-27
C9 | P2 | SSO (Google / Microsoft / SAML) | Enterprise gate. Most SMEs don't ask, but any 50+ employee prospect will. |  |  |  | SAML for enterprise; Google/MS OAuth for SME. | RBAC-28
C10 | P2 | Per-user API keys | Programmatic access (Zapier, custom scripts). Today the only path is JWT extraction from a browser session. |  |  |  | Standard. | RBAC-29
C11 | P2 | Client / customer read-only portal | Share a workflow status with a customer without giving them a full account. Common ask from procurement flow. |  |  |  | Common for procurement / support tools. | RBAC-30
3. New backlog items (RBAC-01 through RBAC-30)
Each row is a shippable task. Priority = same P0/P1/P2 scale as Task Backlog. Effort = S(<1d) / M(1-3d) / L(1w+). Blocks-Go-Live = whether the item must ship before we sell to a real multi-employee SME.
ID | Priority | Effort | Task title | Blocks? | Depends on | Category | Sprint | Description + acceptance
RBAC-01 | P0 | S | Auth-gate onboarding drafts | Yes | - | Endpoint gate | Sprint 2.5 | GET/PATCH /onboarding/draft/{draft_id} become 'signed link only': add a signed HMAC on the draft URL (draft_id + issued_at + signature). Only the client that created the draft can read/write. Add rate-limit per IP. Accept: cannot access another draft even with a leaked UUID.
RBAC-02 | P0 | M | CAPTCHA + IP rate-limit on /register | Yes | - | Endpoint gate | Sprint 2.5 | Turnstile (Cloudflare, free) or hCaptcha on POST /register. IP rate limit: 3 registrations/hour/IP. Accept: bot creating 100 tenants gets blocked at #4.
RBAC-03 | P0 | M | Auth-gate + rate-limit signup AI endpoints | Yes | - | Endpoint gate | Sprint 2.5 | /website-intel, /signup/tts, /signup/stt need: CAPTCHA on first call per IP + per-IP 10-req/hour ceiling. SSRF guard on /website-intel (block private IP ranges, allowlist protocols). Accept: unauth attacker cannot burn > $0.10 of AI credit.
RBAC-04 | P1 | S | Symmetric role gate on /workflows create+delete | No | - | Endpoint gate | Sprint 2.5 | POST /workflows: add require_perm('workflows') at minimum, ideally require_perm('workflow_create') if we split it. Accept: employee without workflow perm gets 403 on create.
RBAC-05 | P1 | S | Gate /captures approve/reject/reassign | No | - | Endpoint gate | Sprint 2.5 | Approving/rejecting a capture creates real records — must be require_perm('approvals') or role-gated. Accept: employee without approvals perm gets 403.
RBAC-06 | P1 | S | Gate /follow-up/run to owner or team_manage | No | - | Endpoint gate | Sprint 2.5 | Manual follow-up trigger burns LLM. Restrict to owner or perm(team_manage).
RBAC-07 | P1 | M | Role gates across tasks router | No | - | Endpoint gate | Sprint 2.5 | 17 endpoints in routers/tasks.py are auth-only. Group: reassign + priority-change + delete-execution-plan need perm('team_manage'); prioritize (LLM) needs perm('tasks'). Add explicit decorators. Accept: cross-role matrix test passes.
RBAC-08 | P1 | S | Gate voice/meeting AI on perm(voice_capture) | No | - | Endpoint gate | Sprint 2.5 | voice_capture permission exists in PERMISSION_KEYS but only used by 3 endpoints. Add to /voice-notes text+audio and /meetings audio. Accept: perm-less employee can't burn STT credits.
RBAC-09 | P1 | S | Add decorator gate to leaves approve/reject | No | - | Endpoint gate | Sprint 2.5 | Move inline _can_approve_leave into require_perm('leave_approve'). Keep inline check as defense-in-depth. Accept: reviewer reading the route sees the gate in the signature.
RBAC-10 | P2 | S | Split brain export permission | No | - | Endpoint gate | Sprint 2.5 | POST /brain/export requires perm('brain_export') (new key) instead of perm('ask'). Accept: user with 'ask' but not 'brain_export' gets 403.
RBAC-11 | P2 | S | Gate memory write on perm(brain) | No | - | Endpoint gate | Sprint 2.5 | POST /memory is auth-only. Restrict to perm('brain'). Accept: memory list still readable by all, write gated.
RBAC-12 | P0 | L | Email-per-tenant uniqueness (kill global unique) | Yes | RBAC-13 | Data model | Sprint 2.5 | Move email uniqueness from `users.email` global unique to compound `(tenant_id, email)`. Register + login flow accept optional tenant hint the same way FIX-003-A did for phones (single-tenant fast path + ambiguity picker for multi-tenant email). Migration ledger entry. Accept: same email registered in 2 workspaces works; login prompts workspace picker.
RBAC-13 | P0 | L | Introduce memberships collection (many-to-many) | Yes | - | Data model | Sprint 2.5 | New `memberships` collection: {user_id, tenant_id, role, permissions, status, invited_by, invited_at, accepted_at}. `users` collection becomes tenant-agnostic. All find_one({tenant_id, id}) become find_one via memberships. Big refactor — do it BEFORE Sprint 3 billing so plans attach to tenants not users. Accept: full test-suite passes with the new model + a user with 2 memberships can list both from /me/workspaces.
RBAC-14 | P1 | M | Per-role permission editor | No | RBAC-13 | Data model | Sprint 2.5 | Store role permissions on tenant.roles[i].permissions[]. New endpoint PATCH /tenant/roles/{key}/permissions. UI on the roles admin page. Accept: editing 'warehouse_manager' to include 'finance' immediately gives every warehouse_manager finance access without touching individual users.
RBAC-15 | P1 | S | Owner exclusion list | No | - | Data model | Sprint 2.5 | tenant.owner_exclusions[] = ['finance', 'ledger']. user_perms treats owner+exclusion as 'all perms minus exclusion'. Accept: co-founder marked with finance exclusion gets 403 on /ledger.
RBAC-16 | P1 | S | Fix ROLES/DEFAULT_ROLES 'production' vs 'operations' | No | - | Data model | Sprint 2.5 | Pick one canonical name. Add migration that renames any existing 'production' role to 'operations' (or vice versa) on tenant.roles + user.role. Accept: grep finds only one canonical name; existing tenants unaffected.
RBAC-17 | P1 | S | 'Pending invite' status on user | No | - | Data model | Sprint 2.5 | Add user.invite_status = 'pending' ¦ 'accepted'. Set 'pending' on create-with-invite; flip to 'accepted' on first OTP verify. GET /users returns the flag; admin UI shows a 'Pending' badge. Add resend-invite + revoke-invite endpoints. Accept: invited user shows Pending; revoked user cannot verify.
RBAC-18 | P2 | L | Department/branch scope on permissions | No | RBAC-13 | Data model | Sprint 4 | Add `branches` collection + membership.branch_id + permission modifier '[perm]:branch_X'. Blocks multi-location SMEs. Accept: Finance Manager in Store A sees zero Store B invoices.
RBAC-19 | P2 | M | User groups | No | RBAC-13 | Data model | Sprint 4 | New `user_groups` collection: {tenant_id, name, member_ids, permissions[]}. user_perms merges (role) + (user override) + (union of groups). Accept: adding 'inventory' perm to 'Regional Managers' group instantly grants it to all group members.
RBAC-20 | P0 | M | Immutable audit log (audit_log collection) | Yes | - | Compliance | Sprint 2.5 | New collection audit_log with append-only writes: {actor_id, actor_email, actor_ip, actor_ua, action, entity_type, entity_id, before, after, timestamp, tenant_id}. Wrap every mutating endpoint with a middleware or decorator. Read-only endpoint /admin/audit-log. Accept: deleting a decision leaves an audit row; audit rows cannot be updated/deleted via API.
RBAC-21 | P0 | M | /me/sessions endpoint + revoke by device | Yes | - | UX + security | Sprint 2.5 | Track session metadata on jti (device UA, IP, last-seen). Add GET /me/sessions returning active sessions; DELETE /me/sessions/{jti} revokes one; DELETE /me/sessions revokes ALL except current. Uses FIX-003-C session_revocation infra. Accept: user can see + revoke individual devices.
RBAC-22 | P0 | L | Off-boarding workflow (deprovisioning wizard) | Yes | RBAC-21 | UX + security | Sprint 2.5 | POST /users/{id}/deprovision runs: revoke all sessions, reassign owned tasks to specified user, transfer in-flight decisions, mark authored contacts as reassigned, invalidate all invite tokens. Idempotent. Owner-only. Accept: after deprovision the departing user has zero owned entities.
RBAC-23 | P1 | M | TOTP-based 2FA | No | - | Security | Sprint 3 | Standard pyotp-based flow: enroll (QR + secret), verify, backup codes. Second-factor on login when enabled. Recovery via email + backup code. Accept: user with 2FA enabled cannot log in with password alone.
RBAC-24 | P1 | M | Ownership transfer flow | No | RBAC-13 | UX | Sprint 3 | POST /tenant/transfer-ownership {new_owner_user_id}: promote target to owner, demote current to specified role, cascade billing rebind. Requires 2FA confirm from current owner. Accept: last owner promoted successfully, previous owner remains as employee.
RBAC-25 | P1 | M | Consent tracking for AI features (DPDP) | No | - | Compliance | Sprint 3 | tenant.ai_consent = {granted_at, granted_by_user_id, ip, ua, version}. Show a first-run modal 'DecisionOS uses AI (Anthropic) to process operational data. Consent required.' Gate all AI endpoints on tenant.ai_consent. Log revocations. Accept: fresh tenant cannot use /ask until consent granted.
RBAC-26 | P2 | M | Approval delegation ('acting-as') | No | - | UX | Sprint 4 | user.acting_as: {delegate_user_id, from, to}. When present, approvals routed to `delegate_user_id`. Combines with leaves. Accept: on-leave approver's tasks auto-route to their delegate; badge shows 'Acting for X'.
RBAC-27 | P2 | M | Time-bounded elevated permissions | No | RBAC-13 | UX | Sprint 4 | membership.temp_grants[] = [{perm, granted_by, expires_at, reason}]. Bootstrap TTL sweep to auto-revoke. Audit log entry on grant + revoke. Accept: contractor gets 'finance' perm for 30 days, auto-revoked.
RBAC-28 | P2 | L | SSO (Google + Microsoft OAuth) | No | RBAC-12 | Auth | Sprint 4 | Add /auth/oauth/{provider}/start + callback. Map OAuth email to user via membership lookup. Handle first-time users (auto-provision if tenant allows). Accept: user with matching email can sign in with Google.
RBAC-29 | P2 | M | Per-user API keys | No | - | Programmatic | Sprint 4 | New api_keys collection: {user_id, tenant_id, name, prefix, hash, scopes, created_at, last_used_at}. UI to create/revoke. Bearer-token auth reads api_key instead of JWT. Rate limits per key. Accept: script hits /tasks with key, works, revoke kills it.
RBAC-30 | P2 | L | Client/customer read-only portal | No | - | UX | Sprint 5 | Share a workflow (procurement order, complaint) with an external email via a signed link. Recipient sees status timeline + can add comments, no login. Accept: customer email link opens read-only page; commenting works without account.
4. Test matrix — every RBAC item's exit criteria
The test SHAPE we owe alongside each backlog item. Unit tests + integration tests + cross-role matrix.
# | Test type | What it verifies | Scope | Backlog items covered |  |  |  | Exit criteria
T1 | Cross-role permission matrix | Every endpoint x every default role = expected 200/403. Parameterize via a role_endpoint_matrix.json fixture. | All routers | RBAC-04..11, 14, 15, 16 |  |  |  | 100% pass on the matrix. New route = new row in the matrix (enforced by a test that greps for @router decorators).
T2 | Multi-tenant membership integration test | Same email registered in 2 tenants can list both workspaces, switch, and see only that workspace's data. | auth + team | RBAC-12, 13 |  |  |  | Test creates user X in tenant A and B, verifies /me/workspaces returns both, /tasks in A does not leak B.
T3 | Invite lifecycle test | Invite -> pending -> accept -> active. Also: invite -> revoke -> cannot verify. Also: invite expiry. | auth | RBAC-17 |  |  |  | All 3 paths pass.
T4 | Draft-URL signing test | Guessing a draft_id without the signature = 401. Correct signature = 200. Expired signature = 401. | onboarding | RBAC-01 |  |  |  | All 3 cases + rate-limit test.
T5 | CAPTCHA/rate-limit test | 11th register call from same IP in an hour = 429. CAPTCHA missing = 401. | register + signup AI | RBAC-02, 03 |  |  |  | Bot simulation blocked at expected threshold.
T6 | SSRF guard test | /website-intel called with private-IP URL (localhost, 169.254.x.x, 10.x, 192.168.x) = 400. | signup | RBAC-03 |  |  |  | All private ranges blocked.
T7 | Audit-log append-only test | Every mutating endpoint writes an audit row. Audit row cannot be updated or deleted via any API. Audit row includes before+after diff. | audit_log middleware | RBAC-20 |  |  |  | Random-sampled 20 mutating endpoints all leave audit trails.
T8 | Session revocation UX test | User with 3 sessions revokes one -> that jti gets 401 next request; other 2 still work. Revoke-all keeps current session alive. | session mgmt | RBAC-21 |  |  |  | All 3 flows pass.
T9 | Deprovisioning idempotency test | Deprovision user U. Verify: all sessions revoked, tasks reassigned, decisions transferred, contacts reassigned, invite tokens killed. Running deprovision again is a no-op. | team | RBAC-22 |  |  |  | Zero owned entities remain; second call returns 'already deprovisioned' cleanly.
T10 | 2FA enrollment + login test | Enroll -> confirm with valid TOTP -> login requires TOTP -> backup code works -> lockout after N bad TOTPs. | auth | RBAC-23 |  |  |  | All 4 flows pass.
T11 | Consent-gate test | Fresh tenant hitting /ask before consent = 403 with 'consent_required'. After consent = 200. Consent revocation blocks subsequent AI calls. | AI endpoints | RBAC-25 |  |  |  | 3 states all pass.
T12 | Custom-role-permission propagation test | Edit 'warehouse_manager' role to add 'finance'. Existing warehouse_manager user immediately gets /ledger access without editing their user record. | team + core | RBAC-14 |  |  |  | Propagation confirmed on next request.
T13 | Owner-exclusion test | Owner with finance in owner_exclusions gets 403 on /ledger endpoints. All other owner privileges intact. | core | RBAC-15 |  |  |  | One denied endpoint + one allowed endpoint confirm behavior.
5. Sequencing — what to ship first
Do NOT do 30 items in parallel. Order matters: data model changes (RBAC-12/13) unblock the endpoint gates that check them.
Recommended order
Wave 1 — Endpoint P0s (fast wins, no model changes) |  | RBAC-01, 02, 03. Ships this week. Closes the obvious public exposures. ~2 days.
Wave 2 — Data-model refactor (the big one) |  | RBAC-12 + RBAC-13 together. Introduces memberships collection, moves email to per-tenant unique. ~1 week including migration + full-suite regression. BLOCKS Wave 3.
Wave 3 — Endpoint P1s + role editor |  | RBAC-04..11, 14, 15, 16, 17. Batchable. ~1 week.
Wave 4 — Audit + session + off-boarding P0s |  | RBAC-20, 21, 22. ~1 week. These are what make the product feel enterprise-safe.
Wave 5 — Advanced (Sprint 3+) |  | RBAC-18, 19, 23-30. Sprint 3 (billing) + Sprint 4 (agentic + admin). Individual items scheduled during those sprints.

## Go-Live Checklist
Final Go-Live Checklist — before selling as SaaS at scale
Set Done? to TRUE only when verified, not just coded. Row 24 gives the overall verdict.
Area | Checklist item | Verified in | Done?
Security | All Sprint 0 P0 items closed and verified (not just coded) | Sprint 0 | FALSE
Security | Secrets rotated out of .env into a real secrets manager | Sprint 5 | FALSE
Scale | Follow-up scheduler runs as a single external job, not in-process | Sprint 1 ¦ FIX-002-D (scheduler_locks TTL leader lock, single-fire under N replicas) | TRUE
Scale | All file uploads route through obj_store; local-disk path removed | Sprint 1 ¦ FIX-002-E (voice notes / meetings / ledger / ingestions all obj_store) | TRUE
Scale | Real Dockerfile/Procfile committed with pinned worker count | Sprint 1 ¦ FIX-002-F (multi-stage Docker + Procfile + .dockerignore, 25 static tests) | TRUE
Scale | LLM calls have timeouts + a concurrency limit | Sprint 1 ¦ FIX-002-B (guarded_llm: asyncio.wait_for + semaphore) | TRUE
Multi-tenant | Dynamic workflow approval loop works for a non-textile tenant | Sprint 1 ¦ FIX-001-A + FIX-001-F (tenant_procurement_pipeline + tenant_terminal_stages) | TRUE
Multi-tenant | OTP login + WhatsApp routing are tenant-scoped | Sprint 2 ¦ FIX-003-A (otp_codes keyed by (phone,tenant_id) + cross-tenant WA safety) | TRUE
Multi-tenant | Tenant deletion removes ALL tenant data incl. files | Sprint 2 ¦ FIX-001-E (TENANT_COLLECTIONS wipe + obj_store delete_object) | TRUE
Billing | Real payment provider integrated (Stripe/Razorpay) | Sprint 3 | FALSE
Billing | Per-tenant AI key isolation with usage quota enforcement | Sprint 3 ¦ FIX-005-A (afbf9b8) — services/tenant_ai_keys.resolve_ai_key + services/plans.py ¦ FIX-005-B (29d2238) — services/quotas.py + guarded_llm enforcement + /tenant/usage endpoint | TRUE
Billing | Plan / entitlement fields exist on every tenant | Sprint 3 ¦ FIX-005-A (afbf9b8) — services/tenant_ai_keys.resolve_ai_key + services/plans.py | TRUE
Ops | Staging environment mirrors production | Sprint 5 | FALSE
Ops | Load test completed at ~100-tenant equivalent traffic | Sprint 5 | FALSE
Ops | Sentry / error tracking is live in production | Sprint 5 | FALSE
Ops | Backup restore has been TESTED, not just documented | Sprint 5 | FALSE
Ops | Data migration for all schema changes dry-run on staging | Sprint 5 | FALSE
Ops | Rollback procedure written and rehearsed | Sprint 5 | FALSE
Ops | Staged rollout plan approved (5->20->50->100) | Sprint 5 | FALSE
Testing | Every Testing Plan phase (A-J) hit its exit criteria, incl. Closed + Staged Beta | Testing Plan | FALSE
Sign-off | Final go/no-go review held with the full team | Sprint 5 | FALSE
VERDICT