## Dashboard
DecisionOS - Epic 5 - Workflow Engine
Turn workflows from data blobs into a proper engine. Kickoff: 2026-08-16.
Epic 5 progress: 0 of 16 items Done (0%)
Sprint | Sprint / Epic name | Done | Total | % | Status | Theme
Sprint 1 | Phase 1 - Data model | 0 | 5 | 0% | Backlog | Tasks carry workflow_id + stage_key; pipelines become structured objects; ghost collections retired; Settings redesign lands. Ends with exit gate WE-05.
Sprint 2 | Phase 2 - Backend engine | 0 | 5 | 0% | Backlog | services/workflow_engine.py with on_stage_enter + check_stage_ready + advance. Single-writer contract, side-effects framework, idempotency + concurrency safety. Ends with exit gate WE-10.
Sprint 3 | Phase 3 - UI | 0 | 4 | 0% | Backlog | Stage chips on every task in My Work, inline workflow board with assignee avatars, manual-advance reason prompt with audit entry, retire the Board sub-tab.
Sprint 4 | Cross-cutting - Tests | 0 | 2 | 0% | Backlog | E2E golden path (Kapoor Retail / Delhi Retail scenarios) + full regression + rollback docs per phase.

## Moving to Next Epic
Moving to Next Epic - parked items
Items scoped in Epic 5 but deferred. Empty at kickoff.
ID | Origin sprint | Title | Status | Why parked | Decision needed

## Cover
DecisionOS
Epic 5 - Workflow Engine
Kickoff | 2026-08-16 (Epic 1 split)
Origin | Imported from Epic 1 Stability tracker on 2026-08-16 per founder ask 'park WE-* to Epic 5'.
Epic 5 goal
Ship the Workflow Engine that Epic 1 scoped but never built. Today workflows.stage is written by many callers with no shared contract; this epic centralises it in services/workflow_engine.py with on_stage_enter / check_stage_ready / advance hooks, adds structured stage objects, and gives every task a first-class workflow_id + stage_key so 'Order #4821 . Confirmed' can show up on every task card. 4 phases with exit gates.
Working principles | 1. Single-writer contract - only services/workflow_engine.py writes workflows.stage. All other paths delegate via advance(). 2. Each phase ends with an exit gate that proves behaviour unchanged / engine green / UI regressions clear. 3. Backfill migrations run via services/migrations.py ledger. 4. Same tracker discipline as Epic 2 -- side-by-side updates, Dashboard reflects reality, 'Moving to Next Epic' is the discipline for anything that needs more thought.
Sprint breakdown
Sprint 1 -- Phase 1 - Data model
Status | Backlog (kickoff)
Items | WE-01, WE-02, WE-03, WE-04, WE-05
Why | Tasks carry workflow_id + stage_key; pipelines become structured objects; ghost collections retired; Settings redesign lands. Ends with exit gate WE-05.
Sprint 2 -- Phase 2 - Backend engine
Status | Backlog (kickoff)
Items | WE-06, WE-07, WE-08, WE-09, WE-10
Why | services/workflow_engine.py with on_stage_enter + check_stage_ready + advance. Single-writer contract, side-effects framework, idempotency + concurrency safety. Ends with exit gate WE-10.
Sprint 3 -- Phase 3 - UI
Status | Backlog (kickoff)
Items | WE-11, WE-12, WE-13, WE-14
Why | Stage chips on every task in My Work, inline workflow board with assignee avatars, manual-advance reason prompt with audit entry, retire the Board sub-tab.
Sprint 4 -- Cross-cutting - Tests
Status | Backlog (kickoff)
Items | WE-15, WE-16
Why | E2E golden path (Kapoor Retail / Delhi Retail scenarios) + full regression + rollback docs per phase.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends on | Notes / evidence | Source
WE-01 |  | 1 | Data model (Phase 1) | Add tasks.workflow_id + stage_key + backfill migration | Every task gets first-class fields tying it to its parent workflow card + the specific stage that owns it. Backfill runs once via the migration ledger, keyed on decision_id when a matching workflow exists. Tasks with no parent workflow keep both fields null and continue to work as ad-hoc tasks. | P1 | M | Backlog |  | Imported from Epic 1 WE-01 (sprint: Workflow as Engine). Foundational — unlocks WE-06..WE-09 (the engine needs to read these). See Spec deck slide 9 (data model table). | Epic 1 split 2026-08-16
WE-02 |  | 1 | Data model (Phase 1) | Drop the ghost collections (workflow_templates + lexicon.workflows) | tenant.workflow_templates is a dead brainstorm list; lexicon.workflows is three hardcoded labels. Both cause the 'three cards, three shapes, one concept' Settings confusion the founder sees today. Migration removes them cleanly. No reader depends on either post-refactor. | P2 | S | Backlog |  | Imported from Epic 1 WE-02 (sprint: Workflow as Engine). Enables WE-04 Settings redesign. Idempotent via migration ledger. | Epic 1 split 2026-08-16
WE-03 |  | 1 | Data model (Phase 1) | Convert pipelines[].stages[] from strings to structured objects | Each stage becomes {key, label, tasks:[{title, role, evidence_required}], approval:{role, required}, side_effects:[...]}. Old flat-string entries auto-convert to the object shape with empty tasks + null approval so existing tenants' behaviour is preserved verbatim until owners edit in their stage templates. | P1 | M | Backlog |  | Imported from Epic 1 WE-03 (sprint: Workflow as Engine). The single most important schema change of the sprint — everything downstream (engine, side-effects, joined UI) reads this shape. | Epic 1 split 2026-08-16
WE-04 |  | 1 | UI (Phase 1) | Settings redesign: 8 scattered cards → 4 tabs (Business / Operations / Money / Account) | Kills the 'three cards, three shapes, one concept' confusion by collapsing Settings into a tabbed interface with Operations as the ONE place workflow config lives. Each pipeline shows its stages inline, each stage shows its task templates + approval rule. Add-task-template is an inline row on the stage. | P1 | M | Backlog |  | Imported from Epic 1 WE-04 (sprint: Workflow as Engine). Depends on WE-03 (stage-object shape). See Spec deck slide 12. | Epic 1 split 2026-08-16
WE-05 |  | 1 | Testing (Phase 1) | Phase 1 exit gate — behaviour unchanged, 553 baseline green | Full pytest suite green. Zero behaviour diff for existing tenants who don't touch Settings. Ghost collections gone (no reader errors). Both migrations idempotent + replica-restart-safe. 4-tab Settings functional. | P1 | S | Backlog |  | Imported from Epic 1 WE-05 (sprint: Workflow as Engine). See Testing Plan deck slide 4 (Phase 1 exit gate). | Epic 1 split 2026-08-16
WE-06 |  | 2 | Backend engine (Phase 2) | services/workflow_engine.py — on_stage_enter + check_stage_ready + advance | The three transition operations. on_stage_enter spawns the stage's template tasks for the named roles, records a timeline entry, dispatches notifications. check_stage_ready returns true only when every stage task is done AND every required approval is present. advance runs the check, transitions on pass, re-enters on_stage_enter for the next stage (chained). Terminal stage fires side-effects + marks card done. | P1 | L | Backlog |  | Imported from Epic 1 WE-06 (sprint: Workflow as Engine). The core of the sprint. See Spec deck slide 10 (function table). | Epic 1 split 2026-08-16
WE-07 |  | 2 | Backend engine (Phase 2) | Single-writer contract — only engine writes workflows.stage | Contract test scans every writer in the codebase; only the engine may mutate workflows.stage. Manual advance from the UI STILL exists but routes through engine with override=true + a required 'reason' string that lands in audit_log. Kills the 'silent kanban drag' problem identified in the spec. | P1 | M | Backlog |  | Imported from Epic 1 WE-07 (sprint: Workflow as Engine). Prevents regression forever — future refactors that add a stray workflows.update_one({stage:...}) fail the contract test at CI. | Epic 1 split 2026-08-16
WE-08 |  | 2 | Backend engine (Phase 2) | Side-effects framework — entry/exit hooks per stage | The procurement-terminal → awaiting-bill expense we already have (FIX-001-B) generalises to any stage. side_effects[] on the stage object declares hooks; engine invokes them on enter/exit. Registry of built-in hooks: create_expense, notify_role, post_to_slack. Extensible for tenant-specific hooks later. | P1 | M | Backlog |  | Imported from Epic 1 WE-08 (sprint: Workflow as Engine). Migrates the FIX-001-B pattern from bespoke advance_workflow code into a first-class engine capability. Every future 'when stage X, do Y' request land | Epic 1 split 2026-08-16
WE-09 |  | 2 | Backend engine (Phase 2) | Idempotency + concurrency safety | Calling advance twice on a satisfied stage doesn't double-spawn tasks or skip a stage. Two tasks closing near-simultaneously trigger EXACTLY ONE transition — no double-advance, no lost update. Mongo-level guard via findAndModify + a stage_version field. | P1 | M | Backlog |  | Imported from Epic 1 WE-09 (sprint: Workflow as Engine). Prevents the two hardest-to-diagnose classes of workflow bugs. Regression tests in Testing Plan deck slide 6. | Epic 1 split 2026-08-16
WE-10 |  | 2 | Testing (Phase 2) | Phase 2 exit gate — engine unit + integration green, contract holds | Engine unit tests green (on_stage_enter spawns correctly, check_stage_ready boolean matrix, advance chains + terminal). Integration: task closer → engine → transition → next-task spawn. Single-writer contract holds across all writers. Stage-object migration replica-safe. Side-effects fire exactly once. | P1 | S | Backlog |  | Imported from Epic 1 WE-10 (sprint: Workflow as Engine). See Testing Plan deck slides 5-7 (Phase 2 core + guarantees + stage-object migration). | Epic 1 split 2026-08-16
WE-11 |  | 3 | UI (Phase 3) | My Work — stage chips on every task ('Order #4821 · Confirmed') | Every task in My Work carries a stage chip showing its parent card + current stage. Clicking the chip opens the parent workflow card. Ad-hoc tasks (null workflow_id) show no chip — behaviour unchanged. This is the small change that finally makes tasks and workflows feel like one thing to the user. | P1 | S | Backlog |  | Imported from Epic 1 WE-11 (sprint: Workflow as Engine). See Spec deck slide 13 (My Work + Workflow, joined). | Epic 1 split 2026-08-16
WE-12 |  | 3 | UI (Phase 3) | Workflow board — inline task lists with assignee avatars | Every card on the pipeline board lists its current-stage open tasks inline, with the assignee's avatar. Closing an inline task updates both the card and My Work without a manual refresh. Same data, two lenses. | P1 | M | Backlog |  | Imported from Epic 1 WE-12 (sprint: Workflow as Engine). The other half of WE-11 — from the workflow-board side. | Epic 1 split 2026-08-16
WE-13 |  | 3 | UI (Phase 3) | Manual advance UX — reason prompt + audit entry | The Advance button stays but is rarely needed (cards auto-advance when the stage contract is satisfied). When a user clicks Advance manually the app prompts for a 'reason' string, which lands in the workflow's history AND the tenant's audit_log so ops can see why the engine was overridden. | P2 | S | Backlog |  | Imported from Epic 1 WE-13 (sprint: Workflow as Engine). Pairs with WE-07 (single-writer contract). The override IS allowed — but never invisible. | Epic 1 split 2026-08-16
WE-14 |  | 3 | UI (Phase 3) | Retire the Board sub-tab under Workflows | The 'Board' sub-tab becomes redundant once WE-12 lands. Retire it + clean up its route. Any deep-links redirect to the primary pipeline view. | P2 | S | Backlog |  | Imported from Epic 1 WE-14 (sprint: Workflow as Engine). Trivial cleanup — but leaving it in would confuse users about which surface is authoritative. | Epic 1 split 2026-08-16
WE-15 |  | 4 | Testing (Cross-cutting) | E2E golden-path test — Kapoor Retail / Delhi Retail scenarios | The exact live scenario I ran on 2026-08-13 becomes a codified E2E test: capture 'Big rush order from Delhi Retail...' → decision approval → 3 tasks auto-assigned → each assignee closes their task → card AUTO-ADVANCES stage by stage → side-effect fires on terminal → history shows every transition. No manual Advance clicks in the whole flow. Also the negative case: task incomplete → check_stage_ready returns false → card stays put. | P1 | M | Backlog |  | Imported from Epic 1 WE-15 (sprint: Workflow as Engine). This is THE test that proves the sprint delivered. See Testing Plan deck slide 9 (Kapoor golden path). Adds ~15-20 assertions. | Epic 1 split 2026-08-16
WE-16 |  | 4 | Testing (Cross-cutting) | Full regression + rollback docs per phase | Baseline pytest suite (currently ~520 tests) stays green at every phase boundary. Each of the 3 migrations has a tested reverse or forward-fix path documented in ops-runbook so a bad deploy is revertable in <30 minutes. App stays shippable if any phase is paused. | P1 | M | Backlog |  | Imported from Epic 1 WE-16 (sprint: Workflow as Engine). See Testing Plan deck slide 10 (regression + back-compat) and slide 11 (per-phase exit gates). | Epic 1 split 2026-08-16

## Page Redesign Log
Date | Ticket | Page | What changed | Before | After | Screenshot | Commit
2026-08-16 | Epic 5 kickoff | (no code -- planning) | Epic 5 tracker created from Epic 1 split. 16 items imported. | Items were open in Epic 1 backlog under WE-* sprint(s). | Own epic file, own dashboard, ready to prioritise. | N/A | (next commit)