## Cover
DecisionOS
Epic 11 -- New Features
Kickoff | 2026-10-21 (Requests). Founder 2026-10-22: every new feature the client asks for is a sprint of this epic, and the substantial bugs fixed along the way are Sprint 4 - Bugs.
Origin | Client feature requests: the Requests plan (Requests_Feature_Plan.png, decisions 2026-10-21), FEATURE-08 Notification history and FEATURE-03 Preferred name (2026-10-22), Finance delete (2026-10-22); bugs from the client's Play Store build and the XCODITS QA report (2026-10-21).
Epic 11 goal | Take each client feature from ask to shipped as one sprint: validate it against the code and the data, plan it, build backend + web in the design system, test it, check it in the browser, ship it.
Current state | Sprint 1 Requests shipped (58ce262) - Phase 3 items open. Sprint 2 Notification history shipped (46bb6a0). Sprint 3 Preferred name shipped (6c9bdf1). Sprint 4 Bugs: 12 of 13 fixed (e46b7cc, e352141); WhatsApp no-reply open. Sprint 5 Finance delete shipped (e352141).
Working principles | 1. Validate first: what the code and data say, feasible or not, then the plan. 2. The server holds every rule. 3. The app's design system (components/neuglass). 4. Full test suite green before a push. 5. A plan doc per feature in docs/.
Note on backlog | IDs NF-<sprint>.<n>. Requests was first Epic 6 Sprint 26 (U7-26.x), then its own Epic 11 (RQ-*); Notification history was briefly Epic 12 (NH-*). Each row's Notes names its earlier IDs.
Sprint breakdown
Sprint 1 -- Requests
Files | services/staff_requests.py, routers/staff_requests.py, components/requests/*, pages/Requests.js, pages/MyWork.js
Why | Employees ask for material, money or equipment in one request with many items; their reporting manager (default) or the owner approves; approval books the expense in Finance, Finance marks it paid and purchases go into stock; a General request is a yes, not money. Web shipped 58ce262. Open: Phase 3 (voice via Dex, bill-photo reading, reports, WhatsApp).
Plan | docs/REQUESTS_PLAN.md
Status | In progress -- 14 of 18 Done
Sprint 2 -- Notification history
Files | routers/brief.py, services/notifications.py, pages/Notifications.js, components/notifications/*, pages/Settings.js, components/Layout.js
Why | Client FEATURE-08: read notifications stay reachable. New and History on the Notifications page, Notification history under Settings -> Account, the list pages back past the newest 100, true counts, Move back to New; the bell's always-0 'need you' badge fixed.
Plan | docs/NOTIFICATION_HISTORY_PLAN.md
Status | Done
Sprint 3 -- Preferred name
Files | models/auth.py, routers/auth.py, shared/names.py, routers/desk.py, routers/brief.py, components/ProfileDialog.js, lib/names.js
Why | Every greeting takes the first word of the full name, so 'S Rhea' is greeted 'S' - and initial-first names are the normal way to write a name in Tamil Nadu.
Plan | docs/PREFERRED_NAME_PLAN.md
Status | Done
Sprint 4 -- Bugs
Files | routers/desk.py, routers/tasks.py, hooks/useUiScale.js, services/ingestion.py, pages/Captures.js, components/mobile/Walkthrough.jsx, lib/native/files.js, services/finance_trash.py
Why | The substantial bugs fixed along the way: the client's four from the Play Store build, the XCODITS QA bugs, App Store 5.1.2 AI consent, the old Finance delete getting the books wrong, and files that would not save inside the app. Open: WhatsApp gave no reply to a PDF on 2026-10-22.
Plan | XCODITS QA report 2026-10-21 (BUG-16, BUG-04, BUG-14, ACCESS-12, BUG-15); client fixes 1-4
Status | In progress -- 12 of 13 Done
Sprint 5 -- Finance delete
Files | services/finance_trash.py, routers/finance_trash.py, pages/finance/FinanceDelete.jsx, components/neuglass/DataList.jsx, pages/finance/FinanceRecords.jsx, pages/Captures.js
Why | The client imported wrong records from Tally and could not take them out. One delete for every door that asks first, says what goes with it, keeps issued GST invoices, and can be put back for 30 days; Undo this import; select and delete; delete everything (owner, after a copy).
Plan | docs/FINANCE_DELETE_PLAN.md
Status | Done

## Dashboard
DecisionOS - Epic 11 - New Features
Features the client asks for, one sprint each: plan, build, test and ship the feature as a unit. Sprint 4 collects the substantial bugs fixed along the way.
Epic 11 progress: 48 of 53 items Done (91%). Sprint 1 Requests (shipped 58ce262; Phase 3 open), Sprint 2 Notification history (46bb6a0), Sprint 3 Preferred name (6c9bdf1), Sprint 4 Bugs (e46b7cc, e352141; WhatsApp open), Sprint 5 Finance delete (e352141).
Sprint | Sprint name | Done | Total | % | Status | Theme
Sprint 1 | Requests | 14 | 18 | 78% | In progress | Employees ask for material, money or equipment in one request with many items; their reporting manager (default) or the owner approves; approval books the expense in Finance, Finance marks it paid and purchases go into stock; a General request is a yes, not money. Web shipped 58ce262. Open: Phase 3 (voice via Dex, bill-photo reading, reports, WhatsApp). Plan: docs/REQUESTS_PLAN.md.
Sprint 2 | Notification history | 9 | 9 | 100% | COMPLETE | Client FEATURE-08: read notifications stay reachable. New and History on the Notifications page, Notification history under Settings -> Account, the list pages back past the newest 100, true counts, Move back to New; the bell's always-0 'need you' badge fixed. Plan: docs/NOTIFICATION_HISTORY_PLAN.md.
Sprint 3 | Preferred name | 5 | 5 | 100% | COMPLETE | Client FEATURE-03: a Preferred name in the profile, used by the greetings ('Good afternoon, Rhea', not 'S'); people who never set one are greeted by the first word of their name that is not an initial. Plan: docs/PREFERRED_NAME_PLAN.md.
Sprint 4 | Bugs | 12 | 13 | 92% | In progress | Substantial bugs fixed along the way: the client's four fixes from the Play Store build (Delayed vs Overdue, people on a task, the Workflows tile, phone scale with a bigger font), the XCODITS QA bugs (BUG-16, BUG-04, BUG-14, ACCESS-12, BUG-15), App Store 5.1.2 AI consent, the old Finance delete, files saving inside the app. Open: WhatsApp gave no reply to a PDF (2026-10-22).
Sprint 5 | Finance delete | 8 | 8 | 100% | COMPLETE | Client: a wrong Tally import and no way to delete it. One delete for every door - one record, a selection, an import undone, everything - that asks first, says what goes with it, keeps issued GST invoices, and can be put back for 30 days. Plan: docs/FINANCE_DELETE_PLAN.md.

## Backlog
ID | Screen / Feature | Sprint | Category | Title | Description | Priority | Effort | Status | Depends | Notes | Source
NF-1.1 | services/staff_requests.py, models/staff_requests.py | 1 | Requests | The rules: seven types, approver choice, who may read / decide / fulfil | Types (Purchase & materials, Expense reimbursement, Advance, Travel, Equipment & assets, Repairs & services, General) with their expense-category hint; approver = the requester's choice, reporting manager by default or the owner, no amount rule; no manager falls to the owner and says so; an owner's own request is recorded approved. Access: requester, approver or delegate, owner, Finance once approved; everyone else 404. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.1, first U7-26.1 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.2 | routers/staff_requests.py | 1 | Requests | The HTTP surface, every state change an atomic claim | GET /api/requests?view=mine¦approvals¦fulfil¦all, GET approver-options, GET one; POST create, approve, reject (reason required), request-info, respond, withdraw, fulfil. Each update names the status it moves from, so two Approves make one approval and one expense; REQ-0001 numbering is one atomic increment per company with a unique index behind it. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.2, first U7-26.2 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.3 | routers/staff_requests.py _book_expense, routers/ledger.py create_expense | 1 | Requests / Finance | Approval books the expense in Finance | create_expense(source='request', request_id); the category is found in the company's own words (Raw Materials, Machine Maintenance) before the keyword guess; equipment books Asset Purchase so the asset register gets it; a reimbursement names the employee as payee. A failed booking keeps the approval and says so on the request. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.3, first U7-26.3 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.4 | routers/staff_requests.py fulfil, routers/ledger.py update_expense / delete_expense | 1 | Requests / Finance | Finance closes it: paid, and purchases into stock | Mark paid marks the booked expense paid and can put purchase items with a quantity into inventory (unit cost = line amount / quantity). Paying the expense in Finance closes the request on its own; deleting it unlinks the request and says why. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.4, first U7-26.4 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.5 | services/notifications.py, routers/staff_requests.py | 1 | Requests | Told at every step | Approver (and delegates) on a new request and an answer; requester on approve / reject / question / done; Finance and owners when something is approved to pay; approver when a request is withdrawn. Push titles: Request declined, Request withdrawn. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.5, first U7-26.5 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.6 | bootstrap/routing.py, bootstrap/lifecycle.py, services/tenant_wipe.py, routers/pulse.py, routers/files.py | 1 | Requests | Wired in on day one | Router registered; indexes (tenant+created, requester, approver+status, status, unique number); 'requests' in the tenant wipe list; pulse watches it; a bill attached to a request opens for whoever may open the request; read-gate inventory and API-parity baseline (+10 routes) updated. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.6, first U7-26.6 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.7 | tests/test_staff_requests.py, tests/fake_mongo.py | 1 | Requests | 31 tests: routing, access, money, ask-back, attachments | Manager default / owner choice / no-manager fallback, numbering per company, validation, owner auto-record; access 404s, no self-approval, owner and delegate decide; one expense under two simultaneous approvals, failed booking keeps the yes, company categories, equipment asset, reimbursement payee, fulfil -> paid + stock, expense paid -> request done, delete unlinks; reject needs a reason, question/answer, withdraw rules; own-files-only attachments. FakeDB gains $push and find_one_and_update. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.7, first U7-26.7 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.8 | services/staff_requests.py goes_to_finance, routers/staff_requests.py, components/requests/* | 1 | Requests | A General request is a yes, not money | Yokesh 2026-10-21: General is not financial. No amount on the form (any sent are dropped); approval closes it - no expense booked, Finance not told, never in To pay and cannot open it, Mark paid refused (409). The card reads 'Approved' and sits with the closed ones; the owner's own General request is recorded with no money. 3 tests. | P0 | S | Done |  | Done 2026-10-21 - 58ce262. Was RQ-1.8, first U7-26.18 (Epic 6 Sprint 26). | Founder 2026-10-21
NF-1.9 | components/requests/NewWorkMenu.jsx, pages/MyWork.js, pages/Tasks.js | 1 | My Work | The + asks: New task or New request | My Work's + (phone circle and desktop '+ New') opens a glass menu with the two choices, the CRM add-menu pattern. NewTaskDialog gains a controlled mode (open / hideTrigger) so the menu can open it. | P0 | S | Done |  | Done 2026-10-21 - 58ce262. Was RQ-2.1, first U7-26.8 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.10 | components/requests/NewRequestDialog.jsx, lib/requests.js | 1 | Requests | New request form | Type chips; many items with quantity / unit / amount and a live total; needed-by date; bill or photo attached; why it is needed; Send to: reporting manager (default) or owner, with the no-manager and owner-records-it cases said up front. Words kept as a draft. Same sheet shape as New Task. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-2.2, first U7-26.9 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.11 | components/requests/RequestCard.jsx | 1 | Requests | The request card | Status and type chips, number, total, items, reason, files, question and answer together, reject reason, where the money is (in Finance / paid / in stock / why not), history timeline; Approve / Reject / Ask, Send answer, Withdraw and Mark paid shown from the server's can-flags. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-2.3, first U7-26.10 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.12 | pages/Requests.js, components/requests/RequestsPanel.jsx, pages/MyWork.js | 1 | Requests / My Work | Requests page and My requests in My Work | /requests: Mine, To approve, To pay, All (owner), summary, ?tab= and ?request= deep links. My Work gets a 'My requests' view (phone view picker and desktop segment) with its own + New. | P0 | M | Done |  | Done 2026-10-21 - 58ce262. Was RQ-2.4, first U7-26.11 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.13 | pages/MyWork.js approvals hub, pages/Desk.js | 1 | Approvals / Desk | Approvals hub Requests tab and a Desk card | Approvals gets a Requests tab beside Tasks and Leave, counted in the number on the way in; the Desk's Watch column shows a Requests card when something waits on you. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was RQ-2.5, first U7-26.12 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.14 | components/mobile/AllAppsPanel.jsx, lib/notif.js, hooks/usePulse.js, App.js | 1 | Requests | Phone More tile, notification links, live refresh | More -> Requests; a request notification opens the approver's queue, Finance's list to pay or the requester's own list on the card; pulse refreshes requests, the Desk and expenses. | P1 | S | Done |  | Done 2026-10-21 - 58ce262. Was RQ-2.6, first U7-26.13 (Epic 6 Sprint 26). | Client plan 2026-10-21
NF-1.15 | services/voice.py, Dex | 1 | Requests | Raise a request by voice through Dex | Phase 3. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.14. | Client plan 2026-10-21
NF-1.16 | services/ingestion.py | 1 | Requests | Reimbursement read from a bill photo | Phase 3: fill the items and amount from the photographed bill. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.15. | Client plan 2026-10-21
NF-1.17 | reports | 1 | Requests | Spend reports from requests | Phase 3: who asked for what, approved and paid, by type and month. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.16. | Client plan 2026-10-21
NF-1.18 | services/whatsapp.py | 1 | Requests | Requests on WhatsApp | Phase 3: raise and approve from WhatsApp. | P2 | M | Backlog |  | Phase 3 (later) per the client plan. Was U7-26.17. | Client plan 2026-10-21
NF-2.1 | routers/brief.py list_notifications | 2 | Notifications | Paged feed by state | GET /api/notifications?status=unread¦read&before=<created_at>&limit= on the existing (tenant, user, read, created_at) index. No parameters = today's answer, so nothing that reads it now changes. | P0 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Was NH-1.1 (briefly Epic 12). | Client FEATURE-08
NF-2.2 | routers/brief.py | 2 | Notifications | The true unread count | Counted in the database, not inside the newest 100 - the badge is wrong today past 100 unread (11 of 62 dev users are past it). | P0 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Also fixed: the bell's 'need you' badge tested a `kind` field no notification carries, so it was always 0; the server counts the asks now (services/notifications.NEEDS_YOU_TYPES). Was NH-1.2 (briefly Epic 12). | Client FEATURE-08
NF-2.3 | routers/brief.py read endpoints | 2 | Notifications | read_at stamped; Move back to New | read_at set on read and read-all so history can say when; POST /api/notifications/{id}/unread so reading by mistake loses nothing. | P1 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Was NH-1.3 (briefly Epic 12). | Client FEATURE-08
NF-2.4 | services/retention.py, routers/brief.py | 2 | Notifications | History says how long it is kept | The company's retention window for notifications when switched on (Epic 9 S9), 'kept until deleted' when off. | P2 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Was NH-1.4 (briefly Epic 12). | Client FEATURE-08
NF-2.5 | tests/, test_rbac_reads_are_gated.py, api_route_baseline.json | 2 | Tests | Tests, read-gate and API baseline | Paging both ways, counts past 100, read_at, unread restore, other people's rows never returned; +1 route in the baseline. | P0 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md tests/test_notification_history.py: 8 tests. Was NH-1.5 (briefly Epic 12). | Client FEATURE-08
NF-2.6 | pages/Notifications.js | 2 | Notifications | New and History tabs | New = unread; History = read, paged with Show older; marking read moves the row to History with an Undo. | P0 | M | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Was NH-2.1 (briefly Epic 12). | Client FEATURE-08
NF-2.7 | pages/Settings.js (Account, owner + member) | 2 | Settings | Settings -> Account -> Notification history | The client's ask: a dedicated Notification history section under the profile settings, showing the full history. | P0 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Opens on the latest five with Show more, so the sections below stay in reach; links to Notifications. Was NH-2.2 (briefly Epic 12). | Client FEATURE-08
NF-2.8 | components/Layout.js bell, mobile Notifications tile | 2 | Notifications | Bell: unread only, History link, true badge | The dropdown lists what is new, links to History, and its badge uses the true unread count; the phone tile the same. | P1 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Was NH-2.3 (briefly Epic 12). | Client FEATURE-08
NF-2.9 | browser, scratch database | 2 | Tests | Browser check on a scratch database | Read -> moves to History -> Undo -> back to New; Settings section; a user past 100 reaches the oldest. | P1 | S | Done |  | Done 2026-10-22 - 46bb6a0. docs/NOTIFICATION_HISTORY_PLAN.md Checked as Priya on the scratch DB: badge 3 need you / 24 new; read -> History with Undo; History paged to the oldest (36); Move back to New; Settings section; phone width. Was NH-2.4 (briefly Epic 12). | Client FEATURE-08
NF-3.1 | models/auth.py ProfileUpdateInput, routers/auth.py update_profile | 3 | Profile | Preferred name on the profile | preferred_name on the user (each company's record, like the name): set from PATCH /api/auth/profile, trimmed, max 40, blank clears; /auth/me returns it. | P0 | S | Done |  | Done 2026-10-22 - 6c9bdf1. docs/PREFERRED_NAME_PLAN.md | Client FEATURE-03
NF-3.2 | shared/names.py; routers/desk.py, routers/brief.py, services/ai/brain_rbac.py | 3 | Greeting | One greeting-name rule | Preferred name if set, else the first word of the name that is not an initial ('S Rhea' -> Rhea, 'K. Ramesh' -> Ramesh), else 'there'. Desk greeting, phone brief greeting, Dex's messages. | P0 | S | Done |  | Done 2026-10-22 - 6c9bdf1. docs/PREFERRED_NAME_PLAN.md Also skips a title (Mr, Mrs, Ms, Dr, Prof, Er, Smt) and two-or-three capitals before another word; 'S.Rhea' counts as 'S. Rhea'. | Client FEATURE-03
NF-3.3 | components/ProfileDialog.js ProfileForm (Settings -> Your profile) | 3 | Settings | Preferred name field with a live preview | Under the name: 'We'll greet you as: Good afternoon, Rhea'. Owner and member views. | P0 | S | Done |  | Done 2026-10-22 - 6c9bdf1. docs/PREFERRED_NAME_PLAN.md | Client FEATURE-03
NF-3.4 | lib/names.js; pages/Brain.js DexWelcome, pages/OperatingScore.js | 3 | Greeting | The same rule on the screen side | The Dex welcome and the Ops 'Hi ...' line use it. | P1 | S | Done |  | Done 2026-10-22 - 6c9bdf1. docs/PREFERRED_NAME_PLAN.md | Client FEATURE-03
NF-3.5 | tests/, browser (scratch DB) | 3 | Tests | Tests and a browser check | The rule (initials, dotted initials, preferred name wins, blank clears), the profile save, the Desk greeting; browser: set 'Rhea', Desk says Good ..., Rhea. | P0 | S | Done |  | Done 2026-10-22 - 6c9bdf1. docs/PREFERRED_NAME_PLAN.md tests/test_preferred_name.py: 23 tests incl. a guard that the screen-side rule matches the server's. Browser (scratch DB, 'S Rhea'): Desk 'Good morning, Rhea.' with nothing set; preferred 'Riya' -> Desk, Dex welcome and Ops all say Riya; preview updates as you type. | Client FEATURE-03
NF-4.1 | routers/desk.py _delayed_count, routers/tasks.py list_tasks, pages/MyWork.js | 4 | Desk / My Work | Delayed tile opens the same list it counts | Client, on the Play Store build: Desk said Delayed 18 and the Overdue list it opened was empty. The task list returned only the newest tasks, so on a company with hundreds finished the late ones fell off. The list now returns every open task plus the newest 500 finished, and the tile counts with the list's own query, in IST days. | P0 | M | Done |  | Done 2026-10-21 - e46b7cc (client Fix 1). | Client 2026-10-21
NF-4.2 | services/tasks.py, lib/taskAccess.js, pages/MyWork.js, pages/Tasks.js | 4 | Tasks | Any number of people on a task, and Everyone | A task held at most 10 helpers. No cap now, and the people picker starts with Everyone (N) once there are two or more. | P1 | S | Done |  | Done 2026-10-21 - e46b7cc (client Fix 2). | Client 2026-10-21
NF-4.3 | pages/desk/WorkflowsTile.jsx, pages/Workflows.js, index.css | 4 | Desk / Workflows | Workflows tile: no Approve, one Open in Workflows | Approve left the tile (approving belongs on the card). One full-width Open in Workflows opens the board on the card's stage with the card glowing; picking another board no longer jumps back. | P1 | S | Done |  | Done 2026-10-21 - e46b7cc (client Fix 3). | Client 2026-10-21
NF-4.4 | hooks/useUiScale.js, android MainActivity.java | 4 | Phone | Phone scale on OnePlus / OPPO / Realme (OxygenOS, ColorOS 16) | With the system font size above normal, the web view zoomed the text twice and the Desk broke (tiles cut off). useUiScale measures type and boxes separately; the fallback viewport sets setUseWideViewPort. Checked on a OnePlus 13s and the emulator. | P0 | M | Done |  | Done 2026-10-21 - e46b7cc (client Fix 4). | Client 2026-10-21
NF-4.5 | services/ingestion.py upload_scope, routers/finance.py, pages/Captures.js, pages/finance/ReviewPanel.js | 4 | Finance / Inbox | BUG-16: uploaded bills appear in Pending and Filed | A bill read but not filed waited nowhere, and one filed was never seen again by someone without Finance. Pending and Filed list uploads (the owner and Finance: the company's; others: their own), Discard works, and the toast says where the record went. | P0 | M | Done |  | Done 2026-10-21 - e46b7cc. | XCODITS QA 2026-10-21
NF-4.6 | routers/tasks.py, services/recurrence.py, services/task_timing.py, pages/MyWork.js, bootstrap/lifecycle.py | 4 | Tasks | BUG-04: how late a task was stays after it closes | Closing from the checklist did not stamp the completion, so the lateness was lost. Overdue shows 'Overdue - N days', finished shows 'Finished N days late' or 'on time', a finished task's due date is locked until reopened, and a recurring task's next one is due today, not in the past. Migration task_completed_at_v2 backfills. | P0 | M | Done |  | Done 2026-10-21 - e46b7cc. | XCODITS QA 2026-10-21
NF-4.7 | android AndroidManifest.xml, pages/MyWork.js | 4 | Phone | BUG-14: camera buttons open the camera | On Android 11 and later the camera intent was invisible to the app (no <queries>), so Photo opened the gallery; picking the same photo twice did nothing. | P1 | S | Done |  | Done 2026-10-21 - e46b7cc. | XCODITS QA 2026-10-21
NF-4.8 | components/mobile/Walkthrough.jsx | 4 | Onboarding | ACCESS-12: the walkthrough teaches only what you can do | It taught Decide and the books to people without them. The steps follow the person's role and permissions. | P1 | S | Done |  | Done 2026-10-21 - e46b7cc. | XCODITS QA 2026-10-21
NF-4.9 | pages/Ledger.js | 4 | Finance | BUG-15: the Money 'index box' button | An unlabelled tray icon on the phone's Quick capture card that did nothing on the Inbox. Gone (the Inbox tab carries the count), and a one-cell tab bar is no longer drawn. | P2 | S | Done |  | Done 2026-10-22 - e46b7cc, e352141. | XCODITS QA 2026-10-21
NF-4.10 | MicDictateButton.js, useDexCapture.js, lib/aiConsent.js, pages/Settings.js | 4 | AI / App Store | App Store 5.1.2: AI consent asked first, every provider named | Dex sent voice and text to AI providers before asking. It asks first, and names each provider. | P0 | S | Done |  | Done 2026-10-21 - c6182c3. | App Store review
NF-4.11 | routers/ledger.py deletes -> services/finance_trash.py | 4 | Finance | Deleting in Finance got the books wrong | A deleted payment left its invoice 'received'; a deleted invoice deleted a payment split across other invoices; a deleted expense left its bill in Bills to pay and its asset behind; one tap deleted with no question, no undo and no record; deleting the latest issued invoice reissued its number; Dex kept quoting deleted records. Fixed by Sprint 5's one delete. | P0 | M | Done | NF-5.1 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-4.12 | lib/native/files.js; MoneyActions, BrainDocuments, DexAnswer, Captures, RequestCard, MyWork, financeKit, ReviewPanel | 4 | Phone | Files save inside the Android and iOS apps | The app's web view has no download handler: invoice PDF, Brain document and Dex export buttons did nothing, and links to bills and attachments opened a browser that was not signed in. In the app a file now goes to the share sheet (save to Files or Drive, or send on WhatsApp or mail); the web is unchanged. @capacitor/filesystem 8.1.4, @capacitor/share 8.0.3. | P0 | M | Done |  | Done 2026-10-22 - e352141. Checked on the Android emulator; iOS has the plugins, not yet run on a device. | Found 2026-10-22
NF-4.13 | services/whatsapp.py, integrations/whatsapp.py, routers/whatsapp.py | 4 | WhatsApp | A PDF sent on WhatsApp got no reply | 2026-10-22: the client's PDF got no 'Received' reply. No inbound WhatsApp code changed since 8 Oct, so likely an expired Meta token, the sender not routed to a workspace (pending member, number in two workspaces), or the webhook not delivered. A reply Meta refuses is never logged today. Next: a read-only look at production wa_events for that number, then log Meta's refusals on each event. | P0 | M | Backlog |  | Investigated 2026-10-22 in code; waiting on the production check. | Client 2026-10-22
NF-5.1 | services/finance_trash.py, routers/finance_trash.py, routers/ledger.py | 5 | Finance | One delete for every door | Plan (what goes with it, what changes on what stays) -> remove (a copy in finance_trash_rows first, then put right what stays, then out of the books) -> restore. Payment applications, invoice balances, a bill's expense and stock, an expense's asset, request links, standalone payments; the Brain's notes go too. The old DELETE endpoints route through it; an activity and an audit row each time. | P0 | L | Done |  | Done 2026-10-22 - e352141. docs/FINANCE_DELETE_PLAN.md | Client 2026-10-22
NF-5.2 | pages/finance/FinanceDelete.jsx, pages/Ledger.js | 5 | Finance | Every delete asks first, and has Undo | The sheet lists what it deletes, what goes with it because they belong together, and what changes on what stays; the toast after it has Undo. | P0 | M | Done | NF-5.1 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-5.3 | components/neuglass/DataList.jsx, pages/finance/FinanceRecords.jsx, MoneyActions.jsx, routers/ledger.py list_payables | 5 | Finance | Select and delete on every list | Select, tick (cards on a phone, a column on a laptop), a bar above the dock. Supplier bills and payments made can be deleted; Payments made is listed under Expenses. | P0 | M | Done | NF-5.2 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-5.4 | routers/finance_trash.py imports, services/ingestion.py, routers/finance.py, pages/Captures.js | 5 | Finance / Inbox | Undo this import | On each filed upload in Money > Inbox > Filed: everything the import filed goes, with the payments it matched to older invoices taken off them; contacts used elsewhere and tasks already started are kept. The card then says Undone, with Put back. Imports now stamp their id on stock and follow-up tasks; older imports are found by the moments they were filed. | P0 | M | Done | NF-5.1 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-5.5 | services/finance_trash.py list_trash / restore / purge_expired, workers/schedulers.py | 5 | Finance | Recently deleted, for 30 days | Finance > ... > Recently deleted puts any delete back for 30 days; the scheduler empties older ones. | P1 | S | Done | NF-5.1 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-5.6 | routers/finance_trash.py everything / export | 5 | Finance | Delete all Finance records (owner) | A copy first (a one-time link to the books as a spreadsheet), then the company's name typed. Contacts, tasks and requests are not touched. | P1 | M | Done | NF-5.1 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-5.7 | services/finance_trash.py is_issued, routers/invoicing.py _next_number | 5 | Finance / GST | Issued GST invoices kept; their numbers never reissued | Kept by default with credit-note advice; only the owner can override. A retired number, or one in Recently deleted, is skipped by the next number and refused when typed. | P0 | S | Done | NF-5.1 | Done 2026-10-22 - e352141. | Client 2026-10-22
NF-5.8 | tests/test_finance_records_can_be_deleted_and_put_back.py, browser, Android emulator | 5 | Tests | Tests and checks | 11 tests on a throwaway database plus the route baseline; checked in the browser at phone size and on the Android emulator. | P0 | S | Done |  | Done 2026-10-22 - e352141. | Client 2026-10-22